## Open Tasks
Task # | Task Description | Date Opened | Reported By | Pri | Assigned To | Notes | Estimate (hrs)
To be Assigned or Discussed
2126 | State Vector -> remove coord keyword |  | Pat/Jim L | tbd | tbd
2116 | fac_matrix_make: do a better job putting the inputs into the correct coordinate system |  |  | tbd | tbd
1061 | Add capability to control Legend text, font, format, size, color |  |  | tbd | tbd |  | 4 days
808 | IDL Format Code -currently have no way to insert a different font in the middle of a string (e.g. adding a symbol to a string in NewTimesRoman). Possibly enable formatting like we did for the z axis labels |  |  | tbd | tbd |  | 1 day
24 | • Page Options (for printing) o allow user to toggle landscape/horizontal o ungray widget to allow user to modify canvas settings o add window size to page settings template o need algorithm to print a large canvas |  |  | tbd | tbd |  | 3 days
759 | Automatically load data if user scrolls forward or backward out of current range. |  | China | tbd | tbd
714 | Add a set all button to the Z axis. |  |  | tbd | tbd |  | 3 hrs
802 | Add THEMIS color palette, maybe a dropdown menu with the 5 themis colors, or a check box to say use 5 default colors? Or add a special area in the existing color palette. |  |  | tbd | tbd |  | 1/2 day
1135 | The call_sequence object needs to track calls to the Overplot routine. That way if you save a themis document with data from an overview plot, you will still be able to get it back. |  | Pat | tbd | tbd |  | 3 hrs
1197 | Add titles to the x and y axes. Jim M partially accomplishes this in the overplots by adding an extra label object, but there's no way for the user to do this on their own. I envision the user entering x and y t |  | Bryan | tbd | tbd |  | 1 day
1141 | Store the angle parameters that you used in get spec. |  | Pat | tbd | tbd |  | 1/2 day
227a | Variable options - 1) It looks like the variable options panel doesn't have an apply button. It probably should, this issue must have just slipped through the cracks. 2)After removing a variable the '-' delete button remains sensitive yet no variables are selected and clicking it does nothing. Either the button should be desensitized or another trace (first or adjacent maybe) should be selected after a delete. 3) I also noticed that the attributes text boxes still contains the old information in them from the variable that was just deleted. It is purely aesthetic but we may want to clear these fields if nothing is selected. 4) Move variable text settings from page options to variable options window. |  | EL | Open | tbd | 2 days
944 | Step 7. Load THEMIS data --Step 7. FGM data: I did not get fge data for THC. Maybe there is none for that day (2008-1-1), but the running history also did not issue a "some data not loaded" error, unless only that datatype is requested. Running histor |  | Michael | tbd | tbd |  | 2 hr
1464 | Calculate: Once a quantity is selected in the Insert Field, expanding/collapsing events cause that selection to be inserted into the Program Area. |  | Bryan | tbd | tbd
1311 | Add capability to go into landscape mode (page pull down menu) |  | Pat/Jim L | tbd | tbd | related to task 24
806a | Markers -1) Allow feature for user to control marker lines (style, color,size) marker text (font, format, color, size), and marker shaded region (color, opacity) 2) Add logic to check when tracking all is on so that selected markers will be selected for all panels. 3) If multi-panel tracking is on, subset all visible panels at the same time-range. |  |  | tbd | tbd |  | 1 week
2175
2176
2177
2178
2179
2180
General
| Review EFI web pages on beta site |  | David |  | John B
| Create web pages for FFT, FBK |  | David |  | Chris Cully
| Format FFT and FBK info from C Cully into web pages |  | David |  | David
| Work on acquiring FIT web info |  | David |  | David
| Enhanced SST and MOM Instrument Web Pages |  | David |  | Davin
| EFI Wiki Pages |  | David |  | John B
| SST Wiki Pages |  | David |  | Davin
| New Server Installation |  | Vassilis |  | Jon L
| Greenland data total magnetic field is only about 250 nT even if no baseline subtracted (from Harald). |  | Vassilis |  | J Weygand | Waiting for student to have time.
| Review corrections to the EFI Web pages from Amanda |  | David |  | John B
| Move EFI Web Pages from beta to official web site |  | David |  | Amanda | After John has verified changes
| Problem with the front page of the web site. When you hover the mouse over the "Data" link near the top of the page, then move down to the "Data processing" or "Collaboration tools" menu items, the next level of fly-out menus is unreadable -- they're blocked by one of the images next to the "Latest News & Events" section. I'm using Firefox 2.0.0.20 on Windows. When I look at the site in Internet Explorer instead of Firefox, the menus comes out on top of the image like they're supposed to. |  | David |  | Amanda | Amanda not yet notified
2160 | ESA Processing Web Page revision | 2009-07-01 | David |  | Amanda
2161 | Handle Tony's Pub | 2009-07-01 | Tony |  | Amanda
| SST, ESA and EFI Wiki pages - initial entries |  | Vassilis |  | Vladimir
| Calibration - send sample to Vassilis and David Sibeck |  | Vassilis |  | Vladimir
| Link to Plots |  | Vassilis |  | Vladimir
| Data contain engineering, deployment, maneuver, and science data are in the same stream. From the data description, only maneuver flag state_man is provided. Do you provide information about the time intervals when the data are on, say, engineering level? This data, though valuable in many respects, may be confusing if interpreted as science data. To provide such information, it is possible, for example, to add some bits to existing state_man flag. (from Vladimir) Quality flags (for each instrument to be added to L2 State cdf). |  | Vassilis |  | Vladimir
| L2 File Definitions Document - awaiting L1 document to be completed to use as template. |  | Vassilis |  | Andreas
| Clean-up the power ripples from the FGM data. |  | Krishan |  |  | awaiting programmer
| Revise the Data Products Web page and send to Amanda |  | David |  | David
2163 | Send to Jim McFadden the format of the beginnings of the Operations Log for on board changes that will effect the instrument data | 2009-07-06 | Jim McFadden |  | Deron and John McDonald
Harald
| Keograms being updated. |  |  |  |  | Current status ASK through October 5 2008
The THEMIS movies are now up to date and finished through the end of April. There will be a ~4 days delay because we wait with the mosaic generation until that all the station data have been transmitted
| Mosaic reprocessing post-February 2008 (Full Resolution). |  |  |  |  | Process full resolution for March 1-15 2008, Jan 15 2009 and onward. (Jim M)
Overview plots for web site done though 4/30/2009.
CDF file up to date through 4/30/2009. During the tail season I kept these up to date every 10 days. Now I planned to keep up with this task only once a month somewhere around the 10th of the following month.
Summary Plots through March 2008.
L2 ASI cdf’s
When L2 ASI available Quality Flags and History Status?
Tim
2174 | Reprocess VC files -> L0 packets, L0 packets -> L1 CDFs, and L1->L2 CDFs for all VC files from TH-D since the clock was reset. L1->L2 will probably take care of itself once the L1 files are made. VC->L0 and L0->L1 will need manual intervention. |  |  | 1 | Tim | Pending deployment of patch to processing software, Jim L. task 2173. Tim and Jim L. will work out the details and let the rest of the team know when the deed is done.
2068 | Data Recovery |  | Vassilis | 1 | Tim | Awaiting info from Jon
2069 | Support Mirror Sites |  | Vassilis | 1 | Tim
2069a | Japan (ISAS) |  | Vassilis | 1 | Tim
2069b | Austria |  | Vassilis | 1 | Tim
2069c | France |  | Vassilis | 1 | Tim | (Rumi - not always up to date for gmags)
2069d | UCLA – mirror site set-up |  | Vassilis | 1 | Tim | UCB sent 08T UCLA loaded 06T. Four bricks sent to UCLA - UCLA must reconfigure server first . UCLA will need to supply SSH key - RSYNC Key
2070 | Support gmag data remote sites |  | Vassilis | 1 | Tim
2070a | Augsburg (MACC’s) |  | Vassilis | 1 | Tim
2070b | Alberta |  | Vassilis | 1 | Tim | gmag attributes - reprocess with fix - On Hold for IT
2070c | Greenland |  | Vassilis | 1 | Tim
2071 | Processing full resolution ASI data disks (Apr-Nov 2008). |  | Vassilis | 1 | Tim | On Hold for IT to complete backup.
2072 | Reprocess of ESA L2 data from these dates and all days after until 5/31. This is needed to fill in a missing energy bin in 88x15 full electron mode. |  | Jim M | 1 | Tim | MOM reprocessing on hold, esa completed
2137 | The CDF attributes for some of our GMAGs list the wrong location for the calibration files in the attribute: dl.cdf.gatt.logical_source_description It lists the cal files at: CAL files at http://www-ssc.igpp.ucla.edu/themis_data/calib_files/ But the calibration files for: ATHA, FSIM, FSMI, GILL, PINA, RANK, SNKQ will be found somewhere on this site: http://portal.cssdp.ca:8080/ssdp/jsp/logon.jsp |  | Pat | 2 | Tim
Hannes
2073 | New FGM offsets for tail season |  | Vassilis | 1 | Hannes | in progress
2074 | V03 STATE |  | Vassilis | 1 | Hannes
2074a | Test FGM with new V03 STATE cdf |  | Vassilis | 1 | Hannes
2074b | See email concerning parms ("thx_sci_mode", "thx_hsk_issr_mode") sci_mode - know fast survey, issr_mode - when IDPU thinks fast survey |  | Vassilis | 2 | Hannes
2074c | quality flag for FGM data |  | Vassilis | 2 | Hannes | talk to Uli
2075 | Spin Axis offsets – Improve the new spin axis offsets calibration routine – In progress. A new technique has been developed for inside magnetosphere with high accuracy. Once complete a paper to be published. Sent data to Karl Heinz, included in the distribution |  | Vassilis | 1 | Hannes
2082 | Spin modeling during shadows BugZid=43 |  | Vassilis | 3 | Hannes
Aaron
2033 | VMO file generation |  | David | 1 | Aaron
2033a | One variable change to ASI files and possibly the whole repository |  | David | 1 | Aaron | changes sent to Jan
2033b | SCM and EFI L2 variables |  | David | 1 | Aaron
2033c | L2 STATE (?) |  | David | 1 | Aaron
37 | Add horizontal slider bar to top of draw area, slider vertical as well |  |  | 1 | Aaron |  | 16
1196 | Overview plots - nodownload flag bugs 1.Catch error FILE_LINES: Error opening file. File: /Users/pcruce/data/themis/tha/l1/fgm/0000/tha_fgmcal.txt No such file or directory. Execution halted at: THM_CAL_FIT 79 2. Catch Error - Expression must be a structure in this context: DAT. Execution halted at: SPLIT_VEC 41. 4. Catch error - Expression must be a structure in this context: TMP. Execution halted at: THM_UI_OVERPLOT 561. |  | Pat | 1 | Aaron |  | 2
1065 | Another bug is that when Apply is hit (continuing from the procedure in bug #1, separate e-mail), the fixed scaling (both limits) is updated in log space when I had asked for only the lower limit to be changed to center^2/(upper limit). This is not a difficult mod, but it seems to be in the draw object, and I do not know how to step through the code b/c the focus shifts away from the command line. |  | Michael | 1 | Aaron |  | 2
1572 | The # of Minor Ticks spinner isn't reset to a valid value after a non-numerical value is applied. |  | Aaron | 2 | Aaron
1573 | No message is given to the user within the gui if an overview plot fails due a date that is too early or too late (e.g. a date in 2001 or a week from today). |  | Aaron | 2 | Aaron
2152 | Layout Options produced multiple errors then crashed upon startup after I imported a tplot variable composed of byte data. I could not open the window until the data was deleted. % TIME_STRUCT: Improper time input % TIME_STRING: Improper time input 1) Type conversion error: Unable to convert given STRING to Integer. 2) Detected at: THM_UI_WIDGET_TREE::ADDGROUP 585 3) Type conversion error: Unable to convert given STRING to Integer.Detected at: THM_UI_WIDGET_TREE::ADDGROUP 618 4) WIDGET_TREE: String expression required in this context: <INT ( 0)>. % Execution halted at: THM_UI_WIDGET_TREE::ADDGROUP 618 THM_UI_LAYOUT_OPTIONS 2130 |  | Aaron | 2 | Aaron | message to users
2164 | Just a quick summary of the task we were discussing to fix the issue Christine reported. If we decided to do the task, it would require modifying thm_gen_overplot.pro to use a fixed zrange for all spectral plots rather than autoscaling the plots. It should be trivial. We may also want to make the same changes to thm_ui_gen_overplot.pro, so we can be sure that the GUI overviews match the online overviews. | 2009-07-06 | Pat | 2 | Aaron
2168 | Add a task for the page options window to add font/color/size/alignment control for a panel title. Currently there is no way to control the way a panel title is displayed. | 2009-07-13 | Cindy | 2 | Aaron
Bryan
2020 | If requesting 1 hour of data using timespan, then load data using one of our load data routines. Recommend if there is a fix at the load cdf level and generic. |  | Vassilis | 1 | Bryan | to be discussed at software meeting eta 7/20
2013 | Think about making 2D slices through distribution. See medical imaging code in IDL demo." |  | Vassilis | 2 | Bryan | wait until July
2013a | 2D first migrate code into crib |  | Vassilis | 2 | Bryan | done - talk to Vassilis about checking in
2013b | 2D with med imaging code |  | Vassilis | 2 | Bryan
2013c | 3D slices |  | Vassilis | 2 | Bryan
2027 | thm_load_state - phase II (consult with Ken) |  |  | 2 | Bryan
2027e | Finishing the coordinate transformation of the thm_load_state data at input, to include transformation of spinaxis attitude, need to determine keyword switch, implement the rotation of the spinaxis elevation/azimuth from gei to arbitrary coordinates (consult with Pat, Vassilis and Ken) |  | Vassilis | 2 | Bryan | await discussion of 2126
2041 | thm_load_state out_coord velocity calculations wrong |  | Vassilis | 2 | Bryan
2135 | I didn't realize the cotrans messed up the velocities for earth centered coordinates. Maybe what we really need to do is modify cotrans so that it correctly transforms velocities. Users can incorrectly transform velocities just as easily using thm_cotrans on the command line, as they can using the coord keyword. |  | Pat/Jim L | 3 | Bryan | Discuss at Software Meeting - also related to 2141 and 2135
2028 | Variable units – generic solution - thm_load_spin, _state, _hsk, _sst, _esa, _bau, _fgm, _fbk, _fft, _fit, _scm, _efi, _trg, _asi, _gmag, _ask, _mom, _esa_pkt |  | Vassilis | 3 | Bryan
2029 | From Hannes |  | Hannes | 3 | Bryan
2029a | Provided is the most common plot used by scientists that look at magnetic field data. Four panels Bx By Bz Bt and the position X Y Z as variables. Often the radial distance R is another variable. It would be great if someone enters e.g. tplot,'tha_fgs_gsm' such a useful default plot would appear. I am currently not able to produce such a plot using tplot. Another useful plot would be instead of one trace per panel, 5 traces per panel. One for each spacecraft and 5 sets of positions as variables at the bottom. For example: tplot,'th?_fgs_gsm' could produce such a plot. Also some standard plots that combine ground and spacecraft data could be useful. Notes from Vassilis: define keyword /positions default 'none', allow GSM X Y Z, R Lat Long,....... |  | Hannes | 3 | Bryan
2029b | The level 2 CDF files at http://themis.ssl.berkeley.edu/data_download.shtml should contain position in various coordinate systems as well. Preferably in the same resolution as the data. Otherwise Scientists need to get the position from another source. Notes from Vassilis: option to introduce the data in RE with keyword (one RE =6,478 kilometers ???). Like thm_load_fgm /pos_units= 'RE'. Also thm_load_state keyword out_coord = 'GSM', 'GSE',...etc. |  | Hannes | 3 | Bryan
2029c | If one loads fgm data from probe 'a' and let's say there are no data for the chosen interval. The variables tha_fgl and tha_fgl_gsm etc. should all be empty. It could be those variables still contain data from the previously loaded interval. |  | Hannes | 3 | Bryan
2030 | upgrade thm_load to work with probe assignments |  | Vassilis | 3 | Bryan
2031 | move functionality of thm_load_state2 into thm_load_state and delete thm_load_state2 |  | Vassilis | 3 | Bryan
2032 | Multiple enhancements concerning keywords, valid_names and thm_load routines |  | Vassilis | 3 | Bryan
Cindy
962 | When selecting data, L1 and L2 can be selected at the same time and the result was confusing. since the low-level commands can only load one or the other, the GUI interface should enforce the same restriction. |  | David Sibeck | 1 | Cindy
2113 | Many of the data processing routines that are tested here do not inherit the plotting options from the tplot variable that they take as input. For data processing routines that I've written Vassilis has had me modify them so that they inherit these options. It shouldn't be very hard to do this, but whether we do it or not depends on whether we think these data processing routines are useful only for the gui or for the command line user as well. ( |  | Pat | 1 | Cindy | in progress
2114 | Load routines to all support keywords suffix and relpathnames_all. |  |  | 1 | Cindy | in progress
2119 | There's a possible bug thm_gen_overplot when an illegal device is set with the DEVICE keyword. The code doesn't check to make sure if the graphics device is valid. It passes the test script because thm_gen_overplot has its own catch error statement embedded in the code. The catch statement does report, "Graphics device not available: a", but only after data have been loaded and tplot vars have been created. If a long time range is requested this could be a significant waste of time to the user. |  |  | 1 | Cindy
2120 | NO_DOWNLOAD keyword missing from thm_load_fbk. |  |  | 1 | Cindy
2122 | THM_LOAD_MOM doesn't recognize the datatype keyword for L1 data. (It does for L2). |  |  | 1 | Cindy
2165 | Update FBK Test Suite | 2009-07-06 | David - Pat | 2 | Cindy
1551 | The hourglass cursor does not stay on consistently while an overview plot is being generated. |  | Aaron | 2 | Cindy
1578 | When calling: timespan,'2008-01-29/00:00:00',1,/day thm_load_state,probe='d',coord='dsl',/get_support_data It is printing the following error: % THM_COTRANS: input tplot variable is not a 3-vector. This may not be a big deal, or it may be indicative of the coord argument failing. |  | Pat | 2 | Cindy | on hold - may be solved by 2126
2134 | In the current version, if you rename a quantity in the manage data panel, it automatically changes the labels. This may not be appropriate now that we read label defaults when import, as it can sometimes replace a perfectly good label. We probably want to fix this code, so that it is more careful before replacing a plot label. |  | Pat | 2 | Cindy
2136 | When we implemented tplot_gui, we gave it support for the most important tplot options, but not many of the more obscure ones. It might be worthwhile to create a task for someone to go through exhaustively and implement as many tplot options as is feasible. That way people can more easily use the gui like an interactive version of tplot. Right now I feel like the more obscure options end up leading to gui plots that still look reasonably different from tplot plots. |  | Pat | 2 | Cindy | use tplot crib sheets to identify tplot options
1302 | After we had zoomed in a crazy amount, an error in the x-axis rendering showed up. It is probably not a likely case, but may be worth looking into. I've attached a document & png that should demonstrate the error. | Pat | BL | Open | tbd
2124 | I loaded a plot which had the line color as white. Because the legend plots in the same color as the line, the legend text did not show up. We should probably just put in a check for this case. If the line is white and the background is white then draw the text in black |  | Pat | 3 | Cindy
1579 | When importing a variable with a valid 'V' component in its data struct, but no spec flag set in its meta data, the loaded data object fails to load the y-axis. This should be fixed, as it ends up incorrectly loading certain spectral quantities. |  | Pat | 3 | Cindy
2098 | An IDL crib sheet has been provided that generates magnetic field and position data with the same resolution. Scientists very often like to have a set of dayfiles of magnetic field data and position. So the crib heet could be called inside a loop and for each day an output ASCII file could be produced. An option could be all 5 spacecraft merged with only one time column. Additionally a desired resolution could be another option |  | Hannes | 3 | Cindy | wait until end of July | 32
2115 | tplot does not fail gracefully after illegal margin set. In this case: tplot_options,'xmargin',[100,100], tplot does not fail gracefully after illegal margin set. In this case: tplot_options,'xmargin',[-1,-1] -tplot does not fail gracefully after illegal margin set. In this case: tplot_options,'ymargin',[100,100] |  |  | 3 | Cindy
2117 | minvar_matrix_make documentation is a little sparse, so it couldn't hurt to improve the function header. |  |  | 3 | Cindy
2118 | With a pre-mission and future dates, thm_gen_overplot does not exit gracefully. The user sees a lot of "Remote file not found messages", but is not offered any indication that the date requested is before the mission began. It would also be useful to have a check for when DATE plus DUR is greater than the current date, and then ignore the requested days beyond the current. |  |  | 3 | Cindy
2121 | When thm_load_fit is called requesting a single data type it will also return some auxiliary data types. For example: thm_load_fit,probe='b',datatype='fgs' returns: 1 thb_fit_code 2 thb_fit_npts 3 thb_fgs. load bug or test script bug) b. The relpathnames all keyword is broken. |  |  | 3 | Cindy
Hithesh
2014 | Peter wrote code to reset ETC Kicker (1/8 or 1/9) after hang-up. |  | Peter | 1 | Hithesh | Will run test on model sim until flatsat is available.
2014c | First try to simulate in Modelsim. If unable to freeze ETC, then move to hardware simulation. If the problem is caused by Asynchronous signal (sun pulse), we won't be able to simulate the problem |  | Peter | 1 | Hithesh | Need to find some time on flatsat. Flatsat busy with Artemis.
2015 | Logic Analyzer setup |  | Vassilis | 1 | Hithesh | Dorothy will look at 7/13-7/17. Need to get update from her.
2157 | The ground-computed SC_POT to on-board computed SC_POT do not agree all the time. Jim McFadden thinks it is because of sampling jitter. |  | Jim McFadden | tbd | Hithesh | ETU not responding. Peter is looking into it.
2167 | Helping Deron with SDT test on Probes. |  | Deron |  | Hithesh
Jim L
2024 | GUI Training for Stephen Mende |  | David | 1 | Jim L
2173 | Add patch to VC->L0 and L0->L1 processing to fix TH-D clock anomaly |  |  | 1 | Jim L | in progress
2130 | FGM offset study/debug for European Folks |  | Vassilis | 1 | Jim L | Sent FGM folks data and plots and awaiting their response
2146 | Eclipse times from spin model -- user should be able to get some kind of feedback as to whether the spin phase and spin period are derived from "fresh" sun pulses or interpolated between eclipse start/end times. (From Edita G.) |  | FGM Team | 1 | Jim L
2159 | Complete L1 File Definitions Document |  | David | 1 | Jim L | eta 7/10
2034 | V03-L2 cdf STATE |  | Vassilis | 1 | Jim L
2034c | writing some code to fill in the position and velocity variables for GSE and GSM coordinates. |  | Vassilis | 1 | Jim L | automation in progress
2034d | I need to add support to thm_load_state (and any load/cal routines that call thm_load_state, e.g. thm_cal_fgm) for specifying which version V00, V01, V02, V03 should be used for cotrans and calibration |  | Vassilis | 1 | Jim L | in progress enough data for Hannes to start testing
2034e | I need to enhance the spinmodel routines to use Hannes' spin phase correction, if present With these code changes in place, we can hopefully make some kind of comparison between FGM data calibrated/cotrans-ed with V02 vs. V03 state to verify that the V03 attitude and spin phase corrections are working properly. |  | Vassilis | 1 | Jim L | In progress -- won't happen before 5.1 is released, so this work will occur in a private branch instead of the trunk. Testing of V03 spin axis orientation (by Hannes) can start now, then we'll do another round of tests when the spinmodel code is modified to use the V03 spin phase corrections.
2034f | revised QA script for STATE (path finder for other scripts to be revised later) |  | Vassilis | 1 | Jim L | Still in progress. V03 missing variables are fixed. QA scripts for thm_load_state in progress, but probably won't be ready for 5.1 release. Waiting for Hannes to complete his testing.
2149 | They were also asking when we'll be getting rid of the spikes in the L1 FGM data (Bugzilla #44 and #67). I told them that this is already in the queue, and I should be getting to it very soon. Maybe now is the time? |  | FGM Team | 1 | Jim L
2149a | Packet lookahead in L0->L1 processing (Bugz #67) |  | FGM Team | 1 | Jim L |  | 16
2149b | Apply despike algorithm to current packet if next packet has different range (Bugz #44) |  | FGM Team | 1 | Jim L |  | 16
2149c | When a and b are coded and tested, build new tmtools release and start using it for automated processing. |  | FGM Team | 1 | Jim L |  | 8
2149d | Reprocess all L1 FGM data (which should trigger L2 FGM reprocessing as well) will run for several days, should probably wait until "new justice" is operating reliably) |  | FGM Team | 1 | Jim L | Set-up only, then goes to Tim or Jim M | 1
2035 | Split L1 ESA (using Thomas’s routine) in master ESA data cdf |  | Vassilis | 2 | Jim L | On Hold - awaiting Jim McFadden release: Then send David Sub Task List; Calibration variables removed from L1 data master CDF. (Side note: found and reported a bug in SKTEditor, which the Goddard team has agreed to fix...) Waiting for feedback from Jim McFadden about how calibration data should be handled (TH-A ASCII calibration file (used for all probes) doesn't match anything I removed from the data CDF).
2076 | SM coord transformation in thm_cotrans does not work: fixing that would be too drastic a change for a patch release, because it might break a lot of existing code. The issue is: if the in_coord parameter is not explicitly specified, and the dlimits structure also does not specify the coordinate system, do we want to try to figure it out from the "in_suffix" argument (current behavior, doesn't work for SM coords), or just fail with a message that a coordinate system must be specified with either the in_coord argument or dlimit structure (probably a better solution, but might break existing code). |  | Vassilis | 2 | Jim L | Issue Warning and not to let it fail. Clarification Needed
1563 | We were just griping about how long the Overview plots take to load, and I was thinking, what if the Overview Plot window, had a list of check boxes that would enable the user to turn off certain plots? That way if they don't care about the AE index plot, they could turn it off and speed up the load of the rest of overview plots. Here's some more food for thought: didn't we recently discuss the possibility of making an AE index CDF, and let the users download that instead of downloading all the data necessary to recalculate it client-side? Another candidate for that sort of treatment might be the time intervals for slow survey, fast survey, particle burst, and wave burst -- that's another calculation that requires a large volume of data to be downloaded to produce a tiny product, but only a trivial amount of extra work if it's done on the server side. |  | Bryan/JimL | 2 | Jim L | Separate L1
2147 | FGM spin harmonics correction (remove interference from solar array currents). David Fisher has produced several tables (each table valid for a few months; correction varies with sun angle) of FGM correction vs. spin phase |  | FGM Team | 2 | Jim L and/or Hannes
2147a | Decide on how to represent tables for use in thm_cal_fgm (keep as ASCII? convert to CDF?), get full set of corrections, convert to the desired format, install somewhere under /disks/themisdata (probably alongside FGM cal files?) |  | FGM Team | 2 | Jim L and/or Hannes |  | 16
2147b | Add a step to thm_cal_fgm to load the appropriate correction tables for the probe & time interval being processed, use spin phase at each sample and interpolate within table to find correction at that point, apply correction. There should be a way to disable this correction (e.g. /NO_HARMONIC_CORRECTION keyword or similar, since David F. will need to periodically create new tables from the uncorrected data as data continues to accumulate). |  | FGM Team | 2 | Jim L and/or Hannes |  | 40
2147c | Reprocess L2 FGM products with enhanced code |  | FGM Team | 2 | Jim M or Tim | It might make sense to delay 2147c and 2148b L2 reprocessing until the 2149d L1 reprocessing is performed.
2148 | ADC non-linearity correction: This was proposed as a correction to (i.e. reprocessing) the L1 FGM CDFs, but I think it really belongs in thm_cal_fgm as the very first step. There are jumps in the X, Y, and Z components of the FGM data when the field increases or decreases past some thresholds. Dragos Constantinescu has sent some IDL code to implement the correction, but today I'm told that this code doesn't work that well, and Dragos will be rewriting it to reflect that the size of the jump depends strongly on the rate of change as well as the threshold value. |  | FGM Team | 2 | Jim L and/or Hannes
2148a | 3a) Incorporate Dragos' code in thm_cal_fgm (hold off on implementing until Dragos delivers improved algorithm; estimate 2 days from receipt of revised code?) |  | FGM Team | 2 | Jim L and/or Hannes |  | 16
2148b | Reprocess L2 FGM products with enhanced code (Jim McT, combine with 2147c?) |  | FGM Team | 2 | Jim M or Tim | It might make sense to delay 2147c and 2148b L2 reprocessing until the 2149d L1 reprocessing is performed.
2036 | GOES 10-12 Test data: h. update labels (Howard’s request - minor tweak) |  | Vassilis | 2 | Jim L
2038 | STATE Web Page (s) |  | Vassilis | 2 | Jim L | revew web pages
2039 | bad timing sun pulse times (early January 2009) |  | Vassilis | 2 | Jim L | Clarification needed
2040 | L1 Data Processing History Info: SCM, EFI, STATE |  | Vassilis | 2 | Jim L
2042 | FGM range changes in the mid packet. Post Proc maybe a solution to eliminate the spike. BugzID=44. Bfield mid-packet jumps. |  | Vassilis | 2 | Jim L
2043 | Refactor repeated CDF library code in CDF processing tools BugZid=50 |  | Vassilis | 2 | Jim L
2046 | Create a more efficient & productive prototype QA Instrument Command Line Script - first template (s) functional blocks then scripts for FGM, ASK, SCM, FIT, MOM, ASI, EFI, FFT, FBK, Gmag, State, SST, ESA |  | Vassilis | 2 | Jim L
2047 | Separate E and B timestamps for spin fits: a) make a revised V02 master CDF with E and B separated b) change thm_load_fit to support V01 and V02 of the L1 CDFs c) change the L0->L1 processing code d) change the L1->L2 processing code e) test the changes, then reprocess to create the V02 CDFs (keeping the V01 files around for a while to ease the transition) BugzID=45 |  | Vassilis | 2 | Jim L
2047a | FGS sample times and values, showing repeated timestamps. BugzID=113 (BugzID=67 must be done first) |  | Vassilis | 2 | Jim L
2047b | Repeated timestamps and gaps in spin fit data BugZid=113 (#67 may fix this one as well). |  | Vassilis | 2 | Jim L
2077 | Non Monotonic timestamps. BugzID=72 |  | Vassilis | 2 | Jim L
2078 | bau_sunpulse_met assumes x86 endiannes (BugzID=13) |  | Vassilis | 2 | Jim L
2080 | Phantom packets" cause non-monotonic distribution times. BugzID=25, low priority. |  | Vassilis | 3 | Jim L
2081 | Evaluate CDF compression algorithms BugZid=81 |  | Vassilis | 3 | Jim L
2083 | Add "last processed" time to L1 (and L2?) CDFs BugZid=115 |  | Vassilis | 3 | Jim L
2084 | . transforming one data point from SM coordinates to GSM coordinates. ct=time_double('2008-02-16/04:50:00') dipole=[[0],[0],[1]] v=[1,2,3] store_data,'dipole_sm',data={x:ct,y:dipole,v:v} cotrans,'dipole_sm','dipole_gsm',/SM2GSM cotrans,'dipole_gsm','dipole_gse',/GSM2GSE get_data,'dipole_gse',data=dipole_gse xdipgse=dipole_gse.y[0] ydipgse=dipole_gse.y[1] zdipgse=dipole_gse.y[2] tilt=atan(xdipgse,zdipgse) When I check the data for 'dipole_gsm', the values are 0,0,0. I'm not sure what they SHOULD be, but I know that their magnitude should equal 1. sqrt(x^2+y^2+z^2)=1 |  | Christine | 3 | Jim L
Jim M
2048 | Process full resolution for March 1-15 2008, Jan 15 2009 and onward. |  | Vassilis | 1 | Jim M | on March 8, 2008. Stopped On hold for IT
2049 | MOM Quality Flags and MOM Processing History |  | Vassilis | 1 | Jim M | Ready to go. Waiting for ESA reprocessing to complete.
2050 | Incorrect adjustment on S/C potential. Effects L2 cdfs. Fix in thm_cal_mom |  | Vassilis | 1 | Jim M | In progress. Received dates from Deron.
2951 | New ESA Quality flag for Jim McFadden |  | Jim McFadden | 1 | Jim M | in progress, processing to wait until current reprocessing done
2052 | Add quality flag verbiage to ESA and MOM Data Description web page. |  | David | 1 | Jim M | Talk to Jim McFadden > 7/13
2053 | Revise ESA Processing History Web Page |  | David | 1 | Jim M | Awaiting reprocessing completion
2054 | Issue with ESA data and Overview Plots. Pgm Change and reprocessing from Feb 2009-current ? |  |  | 1 | Jim M | Ready to go. Waiting for reprocessing to complete.
ETC-sst-esa table load TH-A 2009-02-02 22:30:14.
ETC-sst-esa table load TH-D 2009-02-13 20:36
ETC-sst-esa table load TH-E 2009-02-13 22:27
ETC-sst-esa table load TH-B 2009-02-17 23:50:38
ETC-sst-esa table load TH-C 2009-02-18 00:52:20
2145 | Problem with ASI crib when using the command 'ctime,/cut' to generate the movies, it generates an error if you scroll out of bounds. The exact error message produced is: Error: -161 Attempt to subscript <PtrHeapVar289> with I is out of range. % Stop encountered: $MAIN$ 58 /home/pcruce/IDLWorkspace/themis/examples/thm_crib_asi.pro % Program caused arithmetic error: Floating illegal operand |  | Pat | 2 | Jim M | email from Harald
2125 | I received an error in the smoothing function with the no_time_interp keyword set (through the gui). I was using mag data from drby on 2009-6-9 at 500 sec resolution. Traceback Report from THM_UI_LOADED_DATA::DPROC: $MAIN$ THM_UI_DPROC_PANEL_EVENT<C:\GUI\THEMIS_GUI\themis\thm_ui_new\panels\thm_ui_dproc_panel.pro( 123)> THM_UI_NEW_DPROC<C:\GUI\THEMIS_GUI\themis\thm_ui_new\utilities\thm_ui_new_dproc.pro( 179)> CALL_DPROC <C:\GUI\THEMIS_GUI\themis\thm_ui_new\utilities\thm_ui_new_dproc.pro( 57)> THM_UI_LOADED_DATA::DPROC <C:\GUI\THEMIS_GUI\themis\thm_ui_new\objects\thm_ui_loaded_data__dproc.pro( 104)> ERROR_MESSAGE <C:\GUI\THEMIS_GUI\themis\thm_ui_new\utilities\error_message.pro( 256)> Last IDL Error: Unable to concatenate variables because the dimensions do not agree: ARRAY. % Execution halted at: SMOOTH_IN_TIME 153 C:\GUI\THEMIS_GUI\ssl_general\misc\smooth_in_time.pro |  | Aaron | 2 | Jim M
2055 | ESA L2 from L1 (not packets) - create L2 and test thoroughly, then reprocess ESA |  | Vassilis | 2 | Jim M | On Hold; awaiting Jim L to split L1 into master cdf
2056 | SCM L2 cdf |  | Vassilis | 2 | Jim M | in progress
2057 | SCM CAL File Processing Doc |  | Vassilis | 2 | Jim M | text completed. Put into std document format and send to Olivier for review
2058 | found 3 errors in the new th*_l2_esa masters - the good news is, with them fixed in our masters, all plotting issues w/ the ESA files (in CDAWeb) seem to have been resolved. |  | Vassilis | 2 | Jim M
2059 | L2 Data Processing History Info Completed: ESA Still to be Done: SST, MOM, FGM, FBK, FFT, FIT |  | Vassilis | 2 | Jim M
2060 | L2 cdf Quality Flags: for SST |  | Vassilis | 2 | Jim M
2061 | Data Description Paragraphs |  | David | 2 | Jim M
2062 | Alberta - At the moment the data files are from Dawson (daws), Churchill (fchu), Island Lake (isll) and Fort McMurray (mcmu). I will add Rabbit Lake and Taloyoak at some time but we have some issues with mag pointing at those 2 sites. If you recall, the agreement between Ian and Vassilis was that this data wouldn't be copied to become part of a mirrored archive like the existing data we provide. Instead, each file would be obtained from this site each time it is requested (using curl or some such). This means we can use our own logs to monitor data usage. Themis Software to be able to retrieve from Alberta |  | Vassilis | 2 | Jim M
2085 | Summary Plot mods |  | Vassilis | 2 | Jim M
2085a | Fix duplicate velocity units by removing 'km/s' from ytitle and maintaining 'km/s' in ysubtitle |  | Vassilis | 2 | Jim M
2085b | Either make velocity labels into ('X','Y','Z') or make velocity labels into 'VX','VY','VZ'. So that the components are easier to distinguish. |  | Vassilis | 2 | Jim M
2085c | Modify ytitles on esa eflux and sst eflux so that they do not collide. (Insert '!C's or change setting to make tplot do this automatically). |  | Vassilis | 2 | Jim M
2085d | Set the scales on the zoomed out(24 hr) plots so that they are not autoscaled. Information on appropriate yranges should come from Vassilis. |  | Vassilis | 2 | Jim M
2085e | Change labels on temperature lines so that they are done in different colors (and possibly different linestyles). |  | Vassilis | 2 | Jim M
2085f | If necessary, Update the plot key so that it reflects any of the changes above. It'd probably be best to give this task to me, since I've done the past modifications of the plot key. |  | Vassilis | 2 | Jim M
2086 | Orbit Plot on Summary Plot web page - on the right side, 3 plots vertically, each overview plot there would be orbit panels (coordinate with Harald). |  | Vassilis | 2 | Jim M
2087 | Administrator’s Guide |  | Vassilis | 2 | Jim M
2088 | Themis Developers Guide |  | Vassilis | 2 | Jim M
| thm_load_mom: for quantities like velocity, the coordinate system isn't stored in the meta data, and none of the units are stored in the place we normally try to store them (from Pat - Vassilis concurs) Will take a look. |  | Vassilis | 2 | Jim M
2089 | Thm_fgm_overviews currently loads the data out of the fit file. It should probably load the data out of the fgm file. Only needs to load from one data source. Jim M thinks the thm_load_fit can be deleted |  | Vassilis | 2 | Jim M
2090 | that streamlines the generation of gmag stackplots and a crib to show how to do this. (< than a day) |  | Vassilis | 2 | Jim M
2091 | Once Jim McFadden completes his mods for n_3d_new_3 reprocess L2 cdf's - entire mission |  | Vassilis | 2 | Jim M
2092 | thm_load_mom changes - reconcile mods with Davin at an appropriate time. |  | Vassilis | 2 | Jim M
2093 | AE Indexes Issue Jan 8-12, keyograms Jan 12-13, Stripes- Vassilis: minor nuisance |  | Vassilis | 3 | Jim M
2094 | Overview plot change: mode bar seems thick |  | Vassilis | 3 | Jim M | nothing we can do easily
2095 | Mosaic Processing - permanent script needed |  | Vassilis | 3 | Jim M
Michael
2169 | LASP code appears to label SPG coords w/ DSL. Investigate and fix. | 2009-07-13 | John Bonnell | 1 | Michael
2170 | Port LASP axial calibration to eff datatype -> can we? | 2009-07-13 | John Bonnell | 1 | Michael
2171 | Update THM_CRIB_EFI (adding _0 and _dot0 examples, if absent) giving examples for recent upgrades to THM_CAL_EFI. | 2009-07-13 | John Bonnell | 1 | Michael
2172 | Change THM_CRIB_EFI time interval to one of the Mozer intervals. | 2009-07-13 | John Bonnell | 1 | Michael
2100 | EFI calibration |  | John Bonnell | 1 | Michael | in progress
2100d | DC offset between 4sdo and 2sdo in boom plane |  | John Bonnell | 3 | Michael | Which is better? Assigned to J. B. (low priority).
2100h | Try to track down frequency scaling problem in DPWRSPC (dlimit setting? Compare to old plots?). |  | John Bonnell | 3 | Michael | On Hold
2100k | "Case-by-case" calibration parameters ("short-term" high accuracy corrections). LASP does this, but needs integration. |  | John Bonnell | 2 | Michael | On Hold
2100n1 | better define the behavior of THM_LOAD_EFI if multiple coord are specified. |  | John Bonnell | 1 | Michael | in progress
2100n2 | add an example to the EFI crib demonstrating the behavior. |  | John Bonnell | 1 | Michael | in progress
2100p | Modify THM_CAL_FIT to treat efs datatype - Install E12/E34 conditional based on th?_fit_code TPLOT variable. If E12 switched to E34 software needs to be revised to handle |  | John Bonnell | 3 | Michael
2100r | Add the DATATYPE kw to KYOTO_AE_LOAD , and load only AE data by default |  | John Bonnell | 3 | Michael | Check with Andrea if still needed
2100s | Get the downloader (KYOTO_AE_DOWNLOAD based on the new version of FILE_HTTP_COPY ) working |  | John Bonnell | 3 | Michael | Check with Andrea if still needed
2101 | THM_SPINFIT simulates the on-board spin fits |  | John Bonnell | 2 | Michael | in progress
2101a | Check input coord and boom selection (offset is boom dependent) and reflect in TPLOT var name and metadata. Check offsets against C. Cully's example. | Revised 7/13/2009 | John Bonnell | 2 | Michael | in progress
2099 | npot computation |  | Jim McFadden | 1 | Michael
2099a | Formula |  | Jim McFadden | 1 | Michael | McFadden has found bugs in the pipeline. I am on hold until he works those out (he is working with Bonnell and Mozer).
2099c | McFadden requires more information on the bias changes from John as of 6/5 |  | Jim McFadden | 1 | Michael | J.B. to send Jim McFadden info
2099d | Integrate Nishamura's Npot routine as an option into THM_SCPOT2DENS |  | Vassilis | 1 | Michael | On Hold
2102 | FBK frequencies |  | John Bonnell | 2 | Michael
2102c | Make sure that bin center assignment from L2 works with any changes that Jim M. makes |  | John Bonnell | 2 | Michael | Talk to Jim M on 7/13
2102d | John wants to calibrate by signal source – thm_cal_fbk |  | John Bonnell | 2 | Michael
2103 | EAC offsets |  | John Bonnell | 2 | Michael | John has taken AC coupled data -> he will get me the offsets and the switch-over times.
2104 | L2 CDF |  | John Bonnell | 2 | Michael | J. B. to talk to Vassilis about expectations for users. Michael to find out what the programming task is.
2105 | EFI Calibration Document |  | David | 2 | Michael
Pat
2006 | boundary normal coordinates. BugzID=59. |  | Pat | 1 | Pat
2162 | talking with Mcfadden this week, as well as doing some of my own work, it seems that it would be very useful to have THM_LOAD_HSK be able to produce TPLOT variables with housekeeping data in physical (calibrated) units; ie. IEFI_IBIAS in nA instead of RAW TM units. The conversions are straightforward and well-documented, although we should check with the MOC folks to get the latest versions of the calibration parameters. | 2009-07-02 | John B | 1 | Pat | Verified data with output from Bryce. Waiting for John B to verify units on tplot output.
1303 | While I was documenting the draw object I noticed a bug in the way variables are drawn. The routine that calculates the space variables occupy, ignores layout row/column, so if variables are in the left column and right column, it will overestimate the amount of space that variables take and draw the panels with too much space. I'm not sure that this is might priority because we aren't putting a lot of effort into deal with multi-column layouts. But bugs like this are probably replicated in a number of places. Specifically, code that: (1) assumes panels will be lined up in a single column. (2) assumes that panel index will correspond to display position. Will have problems. We may want to put a note to test this in the next phase of testing, so that we can identify all the problems in this set. Another example: The variable panel assumes (2), so that if panels are arranged out of order it selects the incorrect default when opened. |  | Pat | 1 | Aaron Pat | Aaron completed Part 1 - Part 2 to Pat. | 4
2141 | When adding the wavpol crib to the distribution, Olivier mentioned a limitation in the TDAS pwrspc & dpwrspc routines, that we may want to consider fixing. We may want to add a keyword so that "they allow to change the frequency resolution by merging near frequency channels." |  | Pat/Olivier | 1 | Pat
2037 | J. Kissinger’s cotrans routine (from GSE to SSE coordinates) |  | Vassilis | 2 | Pat | SPICE/ICY lib installed. Routines to generate data in progress. Talk with Jim L. re: integration of this data into a cdf.
2009 | Be able to plot ASI & GMAG observatory positions and GOES data on the same plots that are generated by THEMIS Station keyword executing thm_crib_trace.pro |  | Pat | 2 | Pat | Wait until Vassilis comes back in July
1565 | I noticed while trying to export an EPS of some FGH that the fan compression algorithm can be very slow. A little while back, I thought of a way to make the algorithm much faster at the expensive of slightly worse compression ratios. I think this could be well worth implementing after this release and I don't think it would take too long. |  | Pat | 2 | Pat
2063 | Make A-E Index an L1 cdf. |  | Pat | 2 | Pat | in progress - talk to Tim
2139 | I noticed that when calc performs an operation that reduces the number of dimensions on a tplot variable, it doesn't reduce the number of labels and/or colors, which can cause tplot to issue a warning when a result is plotted. |  | Pat | 2 | Pat
1121 | Overview plots - need to figure out how to handle memory issues with tplot variables. |  | Bryan | 2 | Pat
2155 | The manage data window crashes when I try to load ASI data into the gui. Two pop-up messages are produced prior to the crash notifying the user that the data has the wrong dimensions to be loaded (this should happen), the first of the messages below was from one of those pop-ups. Traceback Report from THM_UI_LOADED_DATA::ADDDATA: THM_UI_MANAGE_DATA <C:\GUI\THEMIS_GUI\themis\thm_ui_new\panels\thm_ui_manage_data.pro( 391) THM_UI_MANAGE_DATA_EVENT <C:\GUI\THEMIS_GUI\themis\thm_ui_new\panels\thm_ui_manage_data.pro( 213)> Traceback Report from THM_UI_MANAGE_DATA_EVENT: <C:\GUI\THEMIS_GUI\themis\thm_ui_new\panels\thm_ui_manage_data.pro( 391)> % Variable is undefined: SUCCESS. |  | Aaron | 2 | Pat | quick fix that pat has already taken care of.
2010 | Tplot enhanced crib - Davin should be involved and the cribs should not be too overwhelming. Possibly multiple cribs by functions |  | Pat | 3 | Pat | waiting for Davin for info about crib sent to him
964 | I noticed a bug with the x-grid thickness. For some reason if I use a style like dotted and increase the thickness, the thickness doesn't appear to increase properly for the portion of the grid near the axis itself. This is a pretty minor aesthetic thing, so I don't think it will be a big deal if we put it in the next phase. |  | Pat | 3 | Pat
2063 | Problem with edit3dbins is being caused by IDL's mouse system variable not being updated correctly on Macs. The ctime procedure, used to interactively select a time from a tplot window, relies on this variable to determine when a selection has been made in the tplot window. If the variable is never updated then ctime gets caught in an infinite loop. It's unclear whether this is specific to a particular OS version, but the routine should probably be modified at some point to maximize compatibility with Macs. In the meantime the alternate method of calling gettime that I copied you on yesterday should provide a temporary way around this bug. |  | Aaron | 3 | Pat
2106 | Add the ability to right-click on a variable in the widget-tree and display a popup with basic information about the quantity such as dimensions, range, or other meta data as well as the ability to rename variable |  | Pat | 3 | Pat | originally part of task 64, however, after further evaluation, it was determined this best belonged with the widget tree rather than the analysis window
1555 | A conversation here brought up what should probably be considered a feature. If only minor grids are on, gaps appear in the grid lines, because the grids are not drawn on major ticks. After talking about it, we were thinking a better rule would be to only maintain those gaps if major grids are turned on. |  | Pat | 3 | Pat
Misc
447 | Save THEMIS document: Attempting to save to a read only file in Windows outputs the correct error message, but IDL crashes immediately afterwards. |  |  | 1 |  | IDL Error report to ITT

## Future Tasks
Task # | Task Description | Reported By | Pri | Assigned To | Notes | Estimate (hrs)
To be Assigned or Discussed
2110 | Tplot User's Guide (David and Vassilis to talk further) |  | tbd | tbd
2111 | print, dprint, msg continue, verbose options for a standard |  | tbd | tbd
2112 | Tplot FAQ's (Amanda) Maybe replaced by #1 |  | tbd | tbd
Bugs
| She asked about generating ASI plots, like the ones done online, with the ASI data superimposed on a map. Ultimately, we may be able to implement this in a method similar to the method used for overview plots. Before we could do this, we would need a me | Xiaoyan | BL | Open | tbd
1298 | One item that I think we forgot about when discussing the spinner issues is that it returns strings in it's event structures but doubles when using get_value from widget_control. We should make it more consistent by returning doubles in the event structu | Aaron | BL | Open | tbd
1507 | The issue with 1467, is that users are able to create quantities that don't necessarily make sense as tplot variables with the 'calc' routine. I think I've got a workaround, but other variations on this problem will still exist. A long run solution would be to provide the user with better information on the dimensions of the variables. To that end, I'd like to put a feature request on the list. When a user right-clicks a variable on the widget-tree, it should display a popup with basis information about the quantity, ie dimensions, perhaps range. I don't think there barriers in IDL to implementing this, and making the change in the widget tree, would mean that pretty much every one of our panels would inherit this feature | Pat | BL | Open | tbd | Michael may have put some code in the original GUI that fixes this
Enhancements
1125 | Sometimes when the Annotate Last option is turned off (as it is by default) it will keep ticks relatively far away from the end of the axis from being annotated. If there are three or less ticks on an axis this may cause a large portion of it to be annotationless making it difficult to read. | Aaron | EL | Open | Aaron | 4 hrs (? Done)
1225 | Spinner for zoom control redraws every key stroke | Jim L | EL | Open | Aaron | 1 hr
1277 | Add note to user's guide re: printing | Pat/Jim M | EL | Open | Cindy | 1 hr (see pat/jim email)
267 | The Layout panel doesn't allow shift selection in the panel portion of the widget. | Vassilis | EL | Open | Aaron | 1 hr
63 | Up/Down Arrows to scroll draw area |  | EL | Open | Pat | 3 days
1155 | We should enable tabbing on some of the text boxes in part_getspec, particularly any sets of min/max values such as the angular limits, energy range, time range, etc. All that's required is to set a flag on the base containing the widgets. | Aaron | EL | Open | Bryan | 1 hr
537 | Message Bar bigger or bigger letters | David | EL | Open | Aaron | 1/2 day
492 | Work with Harald to be able to load a reasonable amount of ASI data and add tools into Analysis and DP to process this data. | Vassilis | EL | Open | Aaron | tbd
1311 | Add capability to go into landscape mode (page pull down menu) | Pat | EL | Open | tbd | 1 day
1497 | State Reduced: The save document dialog remembers your previous selection, but it doesn't do it quite right. It puts the expanded path of the file in the selection area. For example("/Users/pcruce/temp/state.tgd"). It should instead use the "path" keyword to dialog_pickfile so that the initial directory is the directory of your current selection ("/Users/pcruce/temp/") and the path keyword so that your initial selection is not the expanded path("state.tgd"). | Pat | EL | Open | tbd | 1 hr
1501 | Overview Plots: Applying any y-axis settings to the roi panel turns the data black making it somewhat hard to read. | Aaron | EL | Open | tbd | 4 hrs
1250 | If I select edit and a spectral is selected, the z-axis settings open, but the first spectral panel is always selected. The panel that the selected trace is on should be selected. | Pat | EL | Open | Aaron | 2 hrs (? Done)
1057 | Add version # to GUI (Help -> About…) | Bryan | EL | Open | Cindy | 2 hrs
810 | Replace the Set All Panel checkbox, with an 'Apply All' button at the bottom of the window. More intuitive. Need to check all panels for consistency |  | EL | Open | Aaron | 4 hrs
751 | Add tabs to each window |  | EL | Open | Cindy | 1 day
1498 | State Reduced: When Opening a Themis Document, it should list the directory of your previous selection. | Pat | EL | Open | tbd | 3 hrs
928 | Ticks/Margin Spinners When setting the Ticks and Margin spinners to decimal values, it appears the code truncates the value entered (i.e. 5.99 becomes 5). But the spinner should be updated upon Apply to update to the truncated value. Suggest low priorit | Bryan | EL | Open | Aaron | to discuss
1133 | When I am removing panels in the layout panel, it always resets the selection to the bottom panel in the list after I remove a panel. This can be annoying if there are several panels because I have to keep scrolling up and clicking. | Pat | EL | Open | Aaron | 1/2 day
1266 | Our numerical entry fields only accept exponential notation entries of the form (1.23e-3) but not the more traditional format( 1.23*10^-3). We may want to leverage the code base from the mini language so that we can interpret these entries as numbers. | Pat | EL | Open | Aaron | 3 days
| She asked about Importing data from Ascii. Jim L would probably have a better idea how long this will take. | Xiaoyan | EL | Open | tbd
959 | When removing a middle panel with locked axes on and you have more than 2 panels, the space the removed panel occupied is drawn blank, rather than moving the panels below it up. | Cindy | EL | Open | Aaron | 2 days
808 | IDL Format Code -currently have no way to insert a different font in the middle of a string (e.g. adding a symbol to a string in NewTimesRoman) |  | EL | Open | Pat | 1 week
| She asked about more extensive options to control the legend. Like being able to add units and move the legend around. I believe this is already listed, but not prioritized. I would estimate this task would take 1-1.5 weeks. | Xiaoyan | EL | Open | tbd | 1.5 weeks
1001 | Just a thought for the next phase; instead of over zealous error checking on spinners we could pass in limits at the spinner's creation that will be implemented only on the spinner's 'spin' function, keeping it from spinning to non-valid values but allowi | Aaron | EL | Open | Aaron | From Pat: That sounds like an interesting idea, although it'd be nice to implement one solution that would resolve spinner error checking for both the spinning operation and the text-entry operation.
960 | Add a change all pages option in the Page Options panel | Aaron | EL | Open | Aaron | 2 days
1063 | Axis Options: #1 When I turn off show-line and turn on mirror, the mirror doesn't show. This is not important, because it is not incorrect that it doesn't show, but we could maybe gray out the mirror check box + others when the show flag is not checked. | Pat | EL | Open | Aaron | 1 day
1149 | If you accidentally close an overview plot page, it would be nice to be able to recreate the plot without having to reload all the data. | Bryan | EL | Open | Bryan | tbd
1150 | If you open and close the overview panel, it doesn't store the current data. (or use the one that is available from the loaded data panel) It probably should. | Pat | EL | Open | Bryan | tbd
519 | We should extend our data model to support 3-dimensional distributions and 3-dimensional image data. This will entail modifications to load widgets, the loaded data object,the tree widget, the data processing widgets, and the addition of a means to draw |  | EL | Open | Bryan | 3 weeks - Bryan write 3-D distributions then extend to GUI
955 | Incorporate user profiles - Have a configuration panel that lets you set default values (e.g. a user always wants annotation time style to be of a certain format, size, or fon)t. This way they don't have to change everything everytime they start a new ses | Marissa | EL | Open | Cindy | 2.5 weeks
1241 | This is just a minor nuisance. If you delete button is hit with no entries in the GUI Data pane, the Delete GUI data confirmation dialog still pops up. Perhaps the delete and examine icons should be desensitized when there's no data loaded in the GUI. | Bryan | EL | Open | Cindy | 1 day
1125 | Var options - would be nice to have Panel droplist return to the Panel that was last modified. Right now it always opens with Panel 1. | Cindy | EL | Open | Cindy | 1/2 day
1266 | Revise test suites, make new suites with check lists. (check on manage/verify test suite and zoom test suite) | Pat | EL | Open | Cindy | 3 days
1301 | The draw object takes a long time to render spectrograms when they are very zoomed in. It should be possible to put a special case in that would make this work more quickly. | Pat | EL | Open | tbd
778 | Need capability to read in ASCII, CDF?, SPLASH files. IDL has a built in widget to specify ASCII formats. |  | EL | Open | Aaron | 3 weeks - Bryan write 3-D distributions then extend to GUI
362 | Implement Save with Data. |  | EL | Open | Aaron | 3 weeks
25 | Add checkbox to append data array.This is to allow a variable to be loaded and contain data for multiple days |  | EL | Open | Cindy
663 | ASK only has one data type, but it still makes you click in the window to select this. We could probably auto-select the '*' to resolve this. |  | EL | Open | Cindy | 1/2 day
692 | "support additional time formats for Save Data As ASCII"? |  | EL | Open | Cindy | 3 days
725 | Need a template or way to store certain global window values (time, spinner value, text boxes, etc…) so when window is reopened it will have same values. |  | EL | Open | Cindy
716 | When I swapped between traces on the line window there was a noticeable screen flicker and the line window was moved back to the center of the viewing area.(even though I had positioned the window off center. The flicker can be eliminated by turning upda |  | EL | Open | Pat
1000 | Panel Options: The panel name appearing to the right of the panel number in the Panels combobox is only updated when the window is started. I think we should either update the combobox as people enter title text or remove the titles from the combobox. | Aaron | EL | Open | Aaron | 1 day
949 | Page Options - Text tab: Step 6q (enter negative numbers for font sizes): Title and Footer font size spinners don't give a warning for size < 0. None of the font size spinners revert to the last valid value if a negative number is entered. Step 6r (enter | Jim L | EL | Open | Aaron | Title Footer - messages output are confusing, always says panel spacing changed. Need to buffer messages. Need to inform user negative value not accepted
998 | Nudge Traces: If a trace is nudged enough then the title will exceed the size of the combobox. When this happens a scroll bar is automatically added to the bottom of the combobox making it difficult to see the traces if the list is small (e.g. 3 or less | Aaron | EL | Open | Aaron | 1 day
1128 | Out of the four format styles we have currently two are only available when using the auto-format option. It would be nice to allow the user to specify exactly which one is desired by replacing the current buttons with a combobox. Instead of Auto, Numer | Aaron | EL | Open | Aaron | 1 week
1139 | We should turn on the hourglass and/or include a progress indicator when we generate angular spectra. | Pat | EL | Open | Bryan | get spec overhaul - 2 hr
1058 | Right now, if you make changes to lines via the line options and select 'Ok', then cancel out of the changes in the layout options, it will cancel the changes you made in the line options. I think we might want to consider a way to prevent this. Alterna |  | EL | Open | Cindy | 2 days
1177 | The above Axis Annotation tab buttons should probably get changed from "first/last" to "range min/max". They used to apply to tick positions, but now are really just the plot box (range) min/max. | Michael | EL | Open | Cindy | for discussion, 2 hrs
764 | Add widget to allow user to set space between labels in axis options label tab |  | EL | Open | Cindy | 1 day
312 | Keep Probe selected highlighted in Themis Load Data when selecting different instruments. | David | EL | Open | Cindy | 1/2 day
1178 | I accidentally tried to plot wavelets as lines and got a memory error. I do not know if there is any way of intercepting this, but it would be nice if there were. Traceback Report from THM_UI_LAYOUT_OPTIONS_EVENT: Unable to allocate memory: to make array | Michael | EL | Open | Pat | need to talk with michael
923 | Scrolling issue with rubberbanding | Jim M | EL | Open | Pat | discussion - 1 day to investigate, need original notes
943 | Getspec window is slightly larger than my 1024x768 screen. Minor issue, probably a Phase 2 task. The vertical size of the Loaded Data pane in the Data Processing window is not consistent across platforms. On my linux box, it's only about half the height | Bryan | EL | Open | Pat | 1 day
811 | Add capability for user to elect not to use all features, maybe an 'Advanced' check box. This would provide the power to the user when needed, but defaults to a simpler, faster way to plot. less |  | EL | Open | tbd
933 | Web forms allow users to go to the next text input box with a tab. Can we do that on our widgets? E.g., the GUI_TPLOT Verify Data would work well that way. | Michael | EL | Open | tbd | Phase III
539 | I noticed a way we might be able to simplify our error catch blocks in the future. The error_message() function that I'm calling to inform the user of an error will by default print the traceback info that our for loop prints now. We could get rid of t |  | EL | Open | Aaron | 1 day (done in some - need to resolve in all windows)
740 | If the user opens the running history with Word right in the middle of their session, then the history will not get saved at all after that point. Our fix to wait until the file is free will not allow us to save the file at any time. We should put an er |  | EL | Open | Aaron | 2 days
760 | It is somewhat confusing to the user about the zoom in and zoom out of the page. Another way to make this clearer, might be to draw a border around the draw area, so that the user is more aware of the difference between the two. We'll also have another wa |  | EL | Open | Aaron | 2 hrs
743 | GetProperty/SetProperty object methods - replace methods with code that is 'smarter'. This will help code maintenance so that new attributes can be added without having to change them in 4 or 5 places. |  | EL | Open | Aaron | 1 week
534 | Error handling - would be nice to have a panel for users to enter error information. Possibly ftp that panel info to our ftp site. Create a script to email to David. Basically replace error report form with widget |  | EL | Open | Aaron
552 | Pass in a calling (or main) widget status bar object into a child widget (see dproc), so that an appropriate message could be left behind after the child widget was closed or killed. I think this would be a good thing to do generally |  | EL | Open | Aaron
736 | Users Guide in HTML |  | EL | Open | Cindy
803 | Would be nice to have a way to move different panels from one window to another |  | EL | Open | Pat
1289 | It seems redundant to have row/column position and span options in both layout and panel options. I suggest we remove it from panel options | Aaron | EL | Open | Cindy | 2 hrs
799 | Add '*' shortcut for navigating the tree widget |  | EL | Open | Pat | tbd
50 | Color Widget on various panels only seems to display 256 colors. |  | EL | Open | Pat
745 | Windows: using arrow keys in spinners (spin it with up/down arrows) |  | EL | Open | Pat
361 | Using Vista the variable names inside plot position box are fuzzy. I believe this might have to do with computer screen size and not Vista. I ran the GUI on Vista and everything was ok. But, watching Marissa run it on her small laptop, I noticed the the a | David | EL | Open | tbd
1317 | I noticed that when X is not time and set to log10 scaling, the annotations are still in scientific notation instead of 10^X format. In natural log scaling, the format is e^X. Just wondering if this was supposed to be consistent. | Michael | EL | Open | tbd
1283 | Something we might want to put on the list is looking into making the overview plots load faster and use less memory. Right now they are much less efficient than they could be. | Pat | EL | Open | tbd | 2 days
1315 | Issues with Loaded Data - need routines built for configuration/save for ACE, WIND, IST. Currently, only have configuration routines for THEMIS and GOES. | Pat | EL | Open | tbd
1299 | The algorithm for determining on-screen clicks, particularly the difference between an x-axis click and a variable click could use improvement. Right now it does an approximation using the size of the margin, but a better solution would be for it to acco | Michael | EL | Open | Pat | 2 days
| I noticed that, currently, when a nudge is performed it splits the component out of its group to create the new nudged quantity. We might want to consider allowing users to nudge entire groups to prevent this problem | Pat | EL | Open | tbd
1387 | Line Options: The Edit X-Axis/Y-Axis Variable trees are a bit small making them difficult to use. Perhaps we should move them to their own tab to allow for more space. | Aaron | EL | Open | tbd | discuss
1419 | It is essentially impossible to get more aesthetic ticks on a log axis when ticks are spaced 1 order of magnitude apart. There is a fix that could fit more aesthetic ticks in | Pat | EL | Open | tbd
1420 | We should add an option that allows the user to determine if minor ticks should be log-spaced or not. On plots with very large ranges, logarithmically spaced minor ticks are not helpful. | Pat | EL | Open | tbd
1416 | This is probably partially an IDL/OS thing, but trying to highlight and copy out of the status bar has become quite tricky. It often will scroll over to a completely different message. Ideally, it should not change your message selection unless you sele | Pat | EL | Open | tbd
1447 | Look into file compressions methods - possibly apply to redraw | Pat | EL | Open | tbd
1445 | Load Themis Data: The status bar update showing what quantities have been selected to be loaded would be much easier to read if we added a space or two between the entries. This would be a very quick fix. | Aaron | EL | Open | tbd
1453 | Layout - when variables are added to a selected panel in the layout window, but the user switches to a different panel while in the variable options window. when the user is returned to the layout window, the variables will not be displayed since the sele | Cindy | EL | Open | tbd
1483 | When trying to open a non-THEMIS document,such as a text file or png file, I get the following system error dialog: "THM_UI_OPEN-->IDLFFXMLDOMDOCUMENT::LOAD: Error encountered during the parse operation." and here's the console output: Traceback Report | Jim L | EL | Open | tbd
1496 | State Reduced: The themis document doesn't keep track of the current page. Maybe it should. | Pat | EL | Open | tbd
805 | Implement Undo/Redo |  | EL | Open | tbd
1512 | Cancel load process |  | EL |  |  | How to implement within GUI? Command line? Tbd
2108 | Manage Data: The manage data fields should be made tabable. |  | Aaron | tbd | tbd
2109 | Calculate If the cursor is clicked onto the the last line in the program area, and if that line is blank, then inserted data names will appear either at the top of the field or at a recently clicked location. |  | Aaron | tbd | tbd
2107 | Add a new feature that allows the user to delete variables from the data processing window (avoids having to open the manage data window every time) |  | Aaron | tbd | tbd
1576 | I was thinking it would be nice if we enabled resize on the overview plot key window. That way on larger monitors, users could extend the window so that they can see the whole key at once. |  | Pat | 4 | Pat
1301 | The draw object takes a long time to render spectrograms when they are very zoomed in. It should be possible to put a special case in that would make this work more quickly. |  | Pat | 4 | Pat
2140 | A suggestion: The function used by tsub_average to return the median or average of the data can also be used to return the standard deviation. Since a single panel will probably be made for both the subtract average and subtract median options we could also add a third option to add/subtract the standard deviation. |  | Aaron | tbd | tbd | Subtracting the stand. dev. from a quantity may not make sense in the way that subtracting the average/median does. We may just want to direct people to the calculate panel, possibly adding a function to calc. stand dev. - Pat
802 | Would be nice to have a THEMIS color palette quickly available, maybe a dropdown menu with the 5 themis colors, or a check box to say use 5 default colors? |  |  | low | tbd |  | 4
447 | Save THEMIS document: Attempting to save to a read only file in Windows outputs the correct error message, but IDL crashes immediately afterwards. |  | 1 | Open | Jim L | IDL Error report to ITT

## Closed
Task # | Task Description | Date Opened | Reported By | Pri | Assigned To | Notes
64 | Analysis Panel - Need to provide a way for users to select a new variable name when data is manipulated. A default name will be provided, but need an editable text box for user to enter a different name. Loaded Data - add suffix to variable names |  |  |  | Cindy | This is not really closed. Initially it went to Aaron but after further evaluation it was decided to place the rename option within the widget tree. Is now task 2106 on Pats list
2044 | L0 to L1 processing: look ahead to the next packet before processing the current packet. BugzID=67 |  | Vassilis | 2 | Jim L
2079a | FGL issue. We have learned that FGL data from probes C, D and E has a 0.25 sec timing error, starting in summer 2007, and continuing to the present (Feb 2008) time. We would like to fix these timestamps in the L1 CDF files. Process should be generic so future corrections can be easily handled. Low Priority steps or tasks: a. create a flag for the affected L1 variables somehow, to prevent confusion about which corrections have or have not yet been applied. So each entry in the proposed correction file should have some sort of tag identifying what the correction is, which could be looked up in the CDF as a variable, variable attribute, or global attribute. |  | Vassilis | 3 | Jim L
2079b | Change L0-L1 code to take corrections into account. |  | Vassilis | 3 | Jim L
2127 | When the smooth() function is called for the y-data the width is applied to each dimension. This causes the function to fail when it's applied to the second dimension, usually containing 3 elements, since the width is almost always larger. We could solve the problem by either looping over each row in the array or by passing the smooth function a vector specifying the width of the extra dimension. It's possible the second solution could have undesirable effects on the data, but that should be straightforward and easy to test for. % SMOOTH: Width must be nonnegative and smaller than array dimensions: <DOUBLE ( 99.000000)> |  | Aaron | 1 | Aaron
2128 | The '-1' applied on the same line to the n_elements() call ends up being applied to the user specified width as well (e.g. in the error message for the first bug the number is 99, it should have been 100). This can be fixed simply by adding parentheses. |  | Aaron | 1 | Aaron
1404 | Making data active, then selecting clear active, then trying to make data active again(without reselecting), does nothing. It should add the data quantities that are still highlighted in the tree. This probably a result of the panel maintaining a list that duplicates the widget-state rather than querying the widget state as needed, and can probably be most reliably fixed by just replacing this list with queries to the widget tree. |  | Pat | 1 | Aaron
227b | Variable options - 2)After removing a variable the '-' delete button remains sensitive yet no variables are selected and clicking it does nothing. Either the button should be desensitized or another trace (first or adjacent maybe) should be selected after a delete. |  |  | 1 | Aaron
551 | Change a setting, then check "set all", then click Apply (as opposed to checking "set all", then changing a setting, then clicking Apply). The change should still propagate to all panels. This is probably a phase II bug. |  |  | 1 | Aaron
1296 | Analysis: Include keywords - analysis of needed changes |  | Vassilis | 1 | Aaron
1067 | Axis Options: 1) Insufficient precision for Unix times in bound autoscale min/max. 2) The first time I tried setting the autoscale min/max, I used 0 and 20. When I applied the change, I got a cryptic status bar message "Draw Object Error: Updating panels". I think this is because none of the data had an X axis value in that range. If so, that should be checked for, and result in a warning dialog rather than a status bar message. 3) Floating Center: Span not calculated correctly for logarithmic scales; for a time axis the calculated span is way too large. It looks like it might be using log(max-min) instead of log(max)-log(min). |  | Pat | 1 | Aaron | #1and#2 Aaron fixed #3 Michael fixed | 4
2002 | Sit-in on GEM PPT Slide Reviews |  | David | 1 | Bryan
2021 | It looks like there's a bug that limits specplot's ability to handle short timespans of data when setting the DATAGAP. Until we can get a fix out, you should be able to get the output you want by using the \options command to set the 'overlay' to 1 options, 'tha_ffp_??_*', 'overlay', 1. then you might have too reset the color bar with the zlim command: zlim, 'tha_ffp_??_*', 10e-14, 10e-5 |  |  |  | Bryan
1248 | D Power Spectrum doesn't seem to work on thg_pseudoAE. The dproc status bar returns "thg_pseudoAE Not processed." The seems to be some problem with loading the resulting tplot variable into the GUI as the console reports: STORE_DATA(177): Creating tplot variable: 243 thg_pseudoAE_dpwrspc STORE_DATA(76): "" not a valid handle name This also happens with tha_peif_density. |  | Bryan | 1 | Bryan
2025 | thm_part_moments2 so that it properly handles single-angle energy spectra when pitch/gyrophase constraints are requested by the user. |  | Vassilis | 1 | Bryan
2026 | Get Spec - 1) Step 11,b,i: Throws a CL error (after the popup): Traceback Report from THM_UI_PART_GETSPEC_OPTIONS_EVENT: Array subscript for PASPEC must have same size as source expression. Execution halted at: THM_PART_MOMENTS2 1070 |  | Vassilis | 1 | Bryan
2000 | Prep for GEM - sort out projector, PPT slides, make trip |  | David | 1 | Cindy
2022 | Train Jim L to give GUI Training at SSL |  | David | 1 | Cindy | sent training script to Jim L.
64 | Analysis Panel - Need to provide a way for users to select a new variable name when data is manipulated. A default name will be provided, but need an editable text box for user to enter a different name. Loaded Data - add suffix to variable names |  |  | 1 | Cindy | This is not really closed. Initially it went to Aaron but after further evaluation it was decided to place the rename option within the widget tree. See Pat's task number 2106 | 16
1510 | If you get an invalid marker error during marking, with either track one or track all turned on. (For example by starting/ending a marker outside of a panel), the vertical/horizontal bars don't get turned back on, after marking is complete. |  | Pat | 1 | Cindy |  | 4
1220 | The panel that the selected trace is on should be selected. |  | Bryan | 1 | Cindy |  | 2
1434 | Markers: If I get a warning because I ctrl-click without dragging.(ie "Could not create marker because marker had insufficient width") It will treat the CTRL as if it is off, even if I leave it pressed. We might want to fix this, although it doesn't appear to be doing anything too harmful. |  | Pat | 1 | Cindy |  | 4
1066 | Layout Options: I noticed that if the user has 'Show Data Components' checked but they forgot to or don't realized they must select both X and Y variables then no message is given to inform them. This may be confusing for the user as they'll have no way of knowing why the 'Add ->' button isn't working in such a case. |  | Aaron | 1 | Cindy |  | 1
1304 | This is not super important, but I noticed that the "draw between points" option in the line options window offers the same units regardless of whether the quantity being plotted is a time or not. For example, If I plot state_pos_x vs state_pos_y, I can go into the line options, and set "Do not draw between points if separated by more than 1 hour", and instead it will not draw between points if the separation is more than 3600 km. To fix, The convention we've adopted on the other panels, is to show the time related options(seconds,minutes,hours,days) when isTime is on, and to show the non time related options when it is off(<none>), rather than the full list (seconds,minutes,hours,days,<none>) |  | Pat | 1 | Cindy |  | 1
703 | Suggestions: The plot for a given panel disappears if logarithmic scaling is chosen for a fixed axis with negative limits. No error is thrown and the plot reappears when the values or scaling are changed. In the future we may want to send a notification to the user as to what happened. |  |  | 1 | Cindy |  | 2
1267 | We don't currently have any messages going to the status bar saying whether a rubber band operation succeeded or failed. It would probably be help to the user if we did. |  | Pat | 2 | Cindy | Cindy | 4
1550 | Calculate: When saving your calculations to a file the extension is not automatically included requiring the user to add it manually later. |  | Aaron | 2 | Cindy
2014a | Put together a simulation of ETC VHDL Design. |  | Peter | 1 | Hithesh | Working with Robert and may need MODELSIM software.
2014b | learn VHDL - . Look at the ETC VHTL programs and understand themis |  | Peter | 1 | Hithesh | in progress and almost complete
2023 | Install latest release on Stephen Mende's Mac |  | David | 1 | Jim L
2129 | GUI Script Training from Cindy |  | David | 1 | Jim L
2131 | Research Data Permissions with Tim |  | Jim L | 1 | Jim L
2123 | Reprocess L0->L1 BAU cdf's due to bug fix |  | Jim L | 1 | Jim L | BAU sun angle data missing/incorrect: fixed in QA, looks good, patch to automated L0->L1 processing deployed, copy fixed CDFs from QA->Production in progress
2034 | V03-L2 cdf STATE -attribute structure |  | Vassilis | 1 | Jim L | need code for missing variables -in progress. After some discussion with Hannes, we decided that the attribute structure for the new spin phase correction variable is incorrect.
2064 | In the process of using XDEGAP in THM_CAL_EFI to check for data gaps, I found that XDEGAP does not do any type checking. Integer inputs do not get recast, so NaNs cannot be assigned. Instead, those assignments become zeros. I propose to for the output to be at least float (no need to do anything, if the input is float or double), so that NaNs can always be assigned. |  | Michael | 1 | Michael | Warning msg only
2065 | A related enhancement to XDEGAP would be to add a FLAG kw to allow the user to choose different flags to fill the gaps (NaNs, by default). |  | Michael | 1 | Michael
2100a | Insert CL message for the begin/end times of the encountered gaps. Also, output to kw and recored # gaps in metadata. |  | John Bonnell | 1 | Michael
2100b | Implement nominal and minimum # of spins, and NaN data where intervals are shorter than min # of spins. |  | John Bonnell | 1 | Michael
2100c | Implement my suggestion to put the EDC offset output into a structure w/ one tag for ea. datatype. |  | John Bonnell | 1 | Michael
2100e | Reason for detecting frequent gaps? |  | John Bonnell | 1 | Michael | Closed -> Waveburst data is often shorter than estimation window.
2100f | Check burst mode behavior w/ on-the-fly offset |  | John Bonnell | 1 | Michael | Use LASP? JB may think it's close one more look
2100g | Updated metadata, CL, and keywords to work with on-the-fly offset method. |  | John Bonnell | 1 | Michael
2100i | Poor despinning bug fix |  | John Bonnell | 1 | Michael
2100j | Kepko and efi offsets |  | John Bonnell | 1 | Michael
2100l | Deconvolution -- LASP does this, but needs integration (see 2h). |  | John Bonnell | 1 | Michael
2100m | The EFI program headers should include what inputs are valid for each keyword. Documentation |  | John Bonnell | 1 | Michael
2100o | efs data deleted when thm_load_fit run twice, second time only fgs data requested |  | John Bonnell | 2 | Michael | Closed - don't know where task came from
2099b | Modify THM_SCPOT2DENS to work stand-alone and with THM_FITGMOM_OVERVIEWS. |  | Jim McFadden | 1 | Michael
2100q | Correlate to onboard spin fits using EFP data. Look at FGM. |  | John Bonnell | 1 | Michael | Closed - don't know where task came from
2101b | Needs to run faster |  | John Bonnell | 2 | Michael
2101c | John to get me example code from Chris Cully. |  | John Bonnell | 2 | Michael
2102a | Resolve conflict bet C. Cully and John B’s bin center values. Conflict resolved. John agrees with Chris |  | John Bonnell | 2 | Michael
2102b | Derive bin centers from CDFs (currently the bin centers are hard coded). |  | John Bonnell | 2 | Michael
2001 | Prep for GEM - sort out projector, PPT slides, make trip |  | David | 1 | Pat
2003 | SPLIT_VEC routine changes From Michael: SPLIT_VEC should also split the labels (as well as the traces), if there are the same number of labels as traces. Otherwise, you get the error: MPLOT: Incorrect number of labels and often also the wrong label displayed for the split trace. From Vassilis - Colors also, preserving the dlimits |  | Michael Vassilis | 1 | Pat
2004 | wavepol.pro and twavepol.pro - Put Olivier's into the distribution, test |  | Vassilis | 1 | Pat
608 | Variables: When axes are locked, draw object should recalculate space needed between panels to display variables. |  |  | 1 | Pat
2005 | str_element does not add to embedded structures (BugzID=69) |  | Vassilis | 1 | Pat
1456 | Page Options: When the font on the variables is set to monospace symbol, the following warning shows on the command line: % IDLGRSRCDEST::DRAW: Select Charmap failure (Encoding: 0x756e6963) (FreeType error info: (38) invalid charmap handle).Setting the annotations to "Scientific Notation" and the Font to "Monospace Symbol" or "Symbol", generates many copies of this error on the console: % IDLGRSRCDEST::DRAW: Select Charmap failure (Encoding: 0x756e6963) (FreeType error info: (38) invalid charmap handle). This probably has something to do with the IDL formatting commands that we've inserted into the annotation string. |  | Pat | 1 | Pat | related to 1422
2007 | Error msg for when timestamps of data do not match in tvector_rotate, tdotp, and tcrossp. |  | Pat | 1 | Pat
2008 | Tplot auto scaling. BugzID=41. |  | Pat | 1 | Pat
2143 | I noticed a small bug when I was running the ASI crib. When you use the command 'ctime,/cut' to generate the movies, it generates an error if you scroll out of bounds. Since everything continues to work functionally, I wouldn't think it is very high priority. |  | Pat | 1 | Pat
2142 | I just found a crash that occurs when trying to export more than one data quantity at once. It looks very simple to fix, but I'm pretty certain that it went out with 5.1 Compiled module: ERROR_MESSAGE. Traceback Report from THM_UI_MANAGE_DATA_EVENT: THM_GUI_NEW_EVENT </home/pcruce/IDLWorkspace/themis/thm_ui_new/thm_gui_new.pro( 260)> THM_UI_MANAGE_DATA </home/pcruce/IDLWorkspace/themis/thm_ui_new/panels/thm_ui_manage_data.pro( 391)> XMANAGER </usr/local/itt/idl70/lib/xmanager.pro( 704)> XMANAGER_EVLOOP_REAL_MODAL </usr/local/itt/idl70/lib/xmanager.pro( 506)> THM_UI_MANAGE_DATA_EVENT </home/pcruce/IDLWorkspace/themis/thm_ui_new/panels/thm_ui_manage_data.pro( 131)> Last IDL Error: % Expression must be a scalar or 1 element array in this context: <BYTE Array[2]>. % Execution halted at: THM_UI_MANAGE_DATA_EVENT 241 |  | Pat | 2 | Pat
2155 | The manage data window crashes when I try to load ASI data into the gui. Two pop-up messages are produced prior to the crash notifying the user that the data has the wrong dimensions to be loaded (this should happen), the first of the messages below was from one of those pop-ups. Traceback Report from THM_UI_LOADED_DATA::ADDDATA: THM_UI_MANAGE_DATA <C:\GUI\THEMIS_GUI\themis\thm_ui_new\panels\thm_ui_manage_data.pro( 391) THM_UI_MANAGE_DATA_EVENT <C:\GUI\THEMIS_GUI\themis\thm_ui_new\panels\thm_ui_manage_data.pro( 213)> Traceback Report from THM_UI_MANAGE_DATA_EVENT: <C:\GUI\THEMIS_GUI\themis\thm_ui_new\panels\thm_ui_manage_data.pro( 391)> % Variable is undefined: SUCCESS. |  | Aaron | 2 | Pat | quick fix that pat has already taken care of.
2011 | Christine's code to rotate the XY coord's along Earth direction was very effective. Also it was used by others. We need to streamline it, and it’s very similar to the others you've already written. |  | Pat | 3 | Pat
2012 | GMAG L2 attributes error - from Pat (very low priority - revisit) |  | Pat | 3 | Pat | could not figure out task
2066 | While generating an overview plot for probe c on 2009-6-3 I received a number of (~30-40) conversion errors (some where on line 400), get email from Aaaron or David |  | Pat | 3 | Pat
2016 | Review FSW Specifications document for v5 changes. Need to add documentation on external memory dump . |  | Peter | 1 | Hithesh | Finished and sent to Peter
2017 | ESA – investigate invalid configs from Survey to burst mode in IDPU scripts. |  | Vassilis | 1 | Hithesh | Task cancelled
2019 | Assisting Deron on EFI sensor diagnostics test |  |  | 1 | Hithesh
1549 | Get Spec - It would be nice if we organize some of the options in the top-right so that we can tell exactly when they are applied and how they interact. For example, we could desensitize the regrid option when it doesn't apply. Or perhaps organize the bases with a frame. Right now it almost looks like "normalize spectrum" is related to regrid, even though they are separate settings. |  | Pat | tbd | tbd
2133 | I found that VARNAMES was not working. It turns out that it is not an input as given in the doc'n, but an output from CDF_LOAD_VARS.PRO. That is also fixed b/c it needed CDF_DATA to be set (?). It is probably supposed to be paired w/ the CDF_DATA kw, so I will just put it that way in the doc'n for now, and we will just call everything closed. |  | Michael | tbd | tbd | non-gui
1549 | Get Spec - It would be nice if we organize some of the options in the top-right so that we can tell exactly when they are applied and how they interact. For example, we could desensitize the regrid option when it doesn't apply. Or perhaps organize the bases with a frame. Right now it almost looks like "normalize spectrum" is related to regrid, even though they are separate settings. |  | Pat | 2 | Cindy
2138 | I just noticed a bug in exporting. The default resolution when exporting spectral plots is set too high. In the example I was looking at which contained one line plot and one spectral plot, this meant that a file that should have been 1.0 MB ended up 1.5 MB. It is a trivial fix |  | Pat | 2 | Cindy
2150 | minor bug in both the clip and deflag routines. If the "flag" argument is set to zero the keyword_set() function does not recognize that the option was called and the routine continues as though the argument was never set. We've had this problem elsewhere whenever zero is a desired value for a keyword parameter. It should be a simple matter to fix it. |  | Aaron | 2 | Cindy
806b | Add marker titles |  |  | 3 | Cindy
1560 | Variable Options: The widget tree in variable options is not being updated with the state of the other trees. |  | Aaron | 2 | Cindy
2152 | Layout Options produced multiple errors then crashed upon startup after I imported a tplot variable composed of byte data. I could not open the window until the data was deleted. % TIME_STRUCT: Improper time input % TIME_STRING: Improper time input 1) Type conversion error: Unable to convert given STRING to Integer. 2) Detected at: THM_UI_WIDGET_TREE::ADDGROUP 585 3) Type conversion error: Unable to convert given STRING to Integer.Detected at: THM_UI_WIDGET_TREE::ADDGROUP 618 4) WIDGET_TREE: String expression required in this context: <INT ( 0)>. % Execution halted at: THM_UI_WIDGET_TREE::ADDGROUP 618 THM_UI_LAYOUT_OPTIONS 2130 |  | Aaron | 1 | Cindy
1267 | We don't currently have any messages going to the status bar saying whether a rubber band operation succeeded or failed. It would probably be help to the user if we did. |  | Pat | 4 | Cindy
481a | We need to add a meta data structure to spectra data objects so that they y-axis for these plots will be automatically set to linear or logarithmic depending on the type of spectra. |  | Bryan | 1 | Bryan | etc 6/26
946 | Print - Step 3) I can create eps files, and verify thet the .eps file is ok using ghostview or ps2pdf, but these do not print out. The 2 copies option does not seem to work. Step 4) The PCL4 file has only 35 bytes and does not print. The PCL5 fileis larger, but does not print. |  | Jim M | 1 | Pat | Documentation mod sent to Cindy and done by Cindy | 16
2096 | Inventory of Products, monitoring and building new alarms for Production Data Processing. Draft document produced. Next version with Harald's info as well |  | Vassilis | 2 | Tim
2097 | Create checksum files for gmag (completed), ASI then Probe files |  | Vassilis | 3 | Tim
2144 | When running tests on rotation crib-sheets, I found a problem with some field aligned coordinate variants. Specifically, the Rgeo and mRgeo transformation don't normalize the y-axis vector of the transformation matrix such that the output matrix generated will not be a proper rotation matrix, but will also scale some of the components by a factor.(I think the scaling factor should be the Sine of the angle between the radial position vector and the magnetic field vector).Requires changes in both fac_matrix_make and thm_fac_matrix_make, but they should be fairly quick. |  | Pat | 1 | Pat
1156 | Part_Getspec: The hourglass cursor does not seem to be appearing consistently while waiting for spectra to be created after clicking Apply. | Aaron | BL | Open | Bryan | related to 1139 - 2 hr
2027a | For STATE CDF files, the following variable attributes should be defined, consistent with they way they are defined in the L2 FGM file: units, coordinate_system (consult with Jim L.) |  | Vassilis | 2 | Bryan | already done Ken wherever you are
2027b | Once defined in the CDF, thm_load_state should take the values from the dlimits.cdf.vatt to set the metadata for the tplot variables: dlimits.data_att.units, dlimits.data_att.coord_sys |  | Vassilis | 2 | Bryan | already done Ken wherever you are
2027c | For thm_load_state, the suffix gets added to support data, but support data is not transformed: if you call thm_load_state, coord='gse', suffix='_gse', /get_support_data only the pos and vel get transformed, but all get the _gse suffix. |  | Vassilis | 2 | Bryan | already done Ken wherever you are
2027d | in thm_load_state, the code to delete support data that was loaded for coordinate transformation should be just del_data, '*_state_temp' e. THC braid photoelectrons |  | Vassilis | 2 | Bryan | already done Ken wherever you are
1318 | I noticed a bug in the GetVarData method on the loaded data object. If it's called with the dlimits option and then called later on the same quantity but w/ the dlimits option set the original pointer will be replaced with an null pointer. |  | Aaron | 1 | Aaron | no longer recreate
593 | Bug with writing flat-file, the code is being too restrictive with its types. Need a standing rule to always promote bytes to 4-byte integers. |  |  | 1 | Aaron
2153 | A crash occurred that shut down IDL when trying to open a THEMIS document. Some possible causes, a. R/W protection of the file? b. Incorrect file name/path? c. Second opening of the same file? |  | Pat/Cindy | 1 | Cindy | unable to reproduce any longer
2166 | On Unix-like platforms (Linux, Solaris, Mac), thm_init crashes if it can't connect to an X windows display. For example, if I ssh from my Windows machine to a Linux host, and I don't have an X server running on the PC, the first call to thm_init will crash my IDL session, even if I'm only doing command-line operations that don't require a graphical display. thm_init is trying to load a color table, and that operation requires either a working X display, or a command like set_plot,'ps' to set another graphics device. It should first check the environment, and skip loading the color table if that operation would fail. Crashing the IDL session is rather annoying! | 2009-07-07 | Jim L | 1 | Cindy
2132 | While working on documentation, I tested the kw: THEMIS> thm_load_efi, probe = 'c', datat = 'eff', cdf_data = cdf_data Level = ['l1'] probes = ['c'] Datatypes = ['eff'] Type = 'calibrated' Variable is undefined: NSNAMES. Execution halted at: THM_LOAD_EFI 93 C:\My Documents\THEMIS\software\THEMREPOS\themis\spacecraft\fields\thm_load_efi.pro |  | Michael | 2 | Cindy | non-gui
2154 | Bug with main image not being properly centered after a zoom. This is also a bug with IDL and thus not totally our problem, but also something we may want to try to work around. I had never seen it before except once previously with the Mac and the projector attached. Possible causes? a. It may be that having a projector attached somehow tricked IDL into improperly reporting the screen dimensions/resolution. b. I noticed that when Cindy typed in the text to zoom, she typed 5//100, then backspaced off the '//' so it will have read 5100% zoom for a second. There should be code to limit the maximum zoom, but it may have broken for some reason. |  | Pat/Cindy | 2 | Cindy
2156 | When writing the tplot export crib, I noticed that tplot_ascii doesn't export any of the y-axis scaling information for tplot spectral quantities(this is typically the d.v or d.v1 component of a tplot variable) Without this information, it is not possible to accurately reconstruct a spectral quantity. To keep things simple it should probably just dump the d.v-data into a separate file. |  | Pat | 2 | Cindy
2158 | I noticed an issue with the z-axis labels on the overview plots. The text from adjacent plots runs together and this makes them essentially unreadable. This should be very simple to fix. We just need to modify ui_overplot so that it sets the z-axis label margin to values which will stagger the z-axis labels. We should probably also remove the '!C' characters from the default labels, as '! C' is currently ignored by the gui. | 2009-07-02 | Pat | 2 | Cindy
1562a | The Margin spinner behavior is too strict, as it enforces the validity of input on every keystroke instead of on Apply. This produces odd behavior when backspacing, etc. This also applies to the Row, Column, Row Span, and Column Span spinners |  | Bryan | 3 | Cindy
2018 | Leftover 512 burst packets |  | Vassilis | 1 | Hithesh | Talked to ops. They found a workaround. Setting burst collection into "test" mode eliminated that effect.

## QA Suites and Scripts
Task # | Task Description | Reported By | Priority | Status | Assignment
Test Scripts
| CLWindows QA - General (cotrans, DP, Plot, Over Plot) |  | QA | Open
| CL Windows QA - FGM (load, cal, cotrans) |  | QA | Open
| CL Windows QA - Getspec and Fac |  | QA | Open
| CL Windows QA - Additional Plot Functions |  | QA | Open
| CL Windows QA - SpecPlot |  | QA | Open
| CL Windows QA - Mini Language (script or suite) |  | QA | Open
| CL Windows QA - SCM (load, cal, cotrans) |  | QA | Open
| CL Windows QA - FIT (load, cal, cotrans) |  | QA | Open
| CL Windows QA - ASI (load) |  | QA | Open
| CL Windows QA - GMAG (load) |  | QA | Open
| CL Windows QA - STATE (load) |  | QA | Open
| CL Windows QA - ESA (load, cal, cotrans) |  | QA | Open
| CL Windows QA - EFI (load, cal, cotrans) |  | QA | Open
| CL Windows QA - FGM (load) |  | QA | Open
| CL MAC QA - FGM (load, cal, cotrans) |  | QA | Open
| CL MAC QA - EFI (load, cal, cotrans) |  | QA | Open
| CL MAC QA - FBK (load, cal) |  | QA | Open
| CL MAC QA - SST (load, cal, cotrans) |  | QA | Open
| CL MAC QA - Tsyganenko, Trace, Trg, Getspec & Fac |  | QA | Open
| CL Unix QA - General (Plot, Over Plot) |  | QA | Open
| CL Unix QA - FGM (load, cal, cotrans) |  | QA | Open
| CL Linux QA - General (cotrans, DP, Plot, Over Plot) |  | QA | Open
| CL Linux QA - SCM (load, cal, cotrans) |  | QA | Open
| CL Linux QA - MOM (load) |  | QA | Open
| CL Linux QA - SST (load, cal, cotrans) |  | QA | Open
| CL Linux QA - ESA (load, cal, cotrans) |  | QA | Open
| CL Linux QA - Tsyganenko, Trace, Trg, MVA and Vector Rotate |  | QA | Open
Test Suites
| gui_tplot |  | QA | Open
| nudge |  | QA | Open
| Data Processing |  | QA | Open
| layout options |  | QA | Open
| line options |  | QA | Open
| Axis Options |  | QA | Open
| markers |  | QA | Open
| panel Options |  | QA | Open
| rubberband |  | QA | Open
| variable options |  | QA | Open
| Calculate |  | QA | Open
| part getspec |  | QA | Open
| save data as |  | QA | Open
| Export to Image |  | QA | Open
| Save Open |  | QA | Open
| page options |  | QA | Open
| z axis |  | QA | Open
| load themis data |  | QA | Open
| pulldown menus |  | QA | Open
| toolbar |  | QA | Open
| windows |  | QA | Open
| ESA Full Suite |  | QA | Open
| SST reduced Suite |  | QA | Open
| FGM Full Suite |  | QA | Open
| GMAG Full Suite |  | QA | Open
| ESA Full Suite |  | QA | Open
| ASK Reduced Suite |  | QA | Open
| SST Reduced Suite |  | QA | Open
| SCM Reduced Suite |  | QA | Open
| FIT Reduced Suite |  | QA | Open
| MOM Reduced Suite |  | QA | Open
| EFI Reduced Suite |  | QA | Open
| FFT Reduced Suite |  | QA | Open
| STATE Reduced Suite |  | QA | Open