## Open Tasks
Task # | Task Description | Date Opened | Reported By | Pri | Assigned To | Notes | Estimate | A&E; crib; script; suite; UG; DevG; Qref; AdmG
To be Assigned or Discussed
4706
4707
4708
General
Hannes
4153 | maintenance of gmag stations "Exclude List" | 2010-10-11 | David | 0 | Hannes | Exclude List up to date as of 9/20/2012
4018a | New Calibration FGM parameters and spin axis offsets | 2010-05-10 | Hannes | 1 | Hannes | 12/06/2012: Cal files updates, all probes from mid-August 2012 on.
4080 | Attitude Determination next few months | 2010-06-21 | Hannes | 1 | Hannes | 10-22-2012 Updated for 2012-04-01 – 2012-06-30
4472 | Inter-spacecraft FGM calibration for ARTEMIS. | 2012-01-04 | Vassilis | 1 | Hannes | 6/4/12 from Hannes: Artemis inter spacecraft differences show good results with current calibration
Aaron
4468 | Ongoing - Review all commits by Davin, Peter, etc for impact to TDAS. | 2012-03-27 | David | 0 | Aaron | Provide weekly report and spreadsheet
1301 | The draw object takes a long time to render spectrograms when they are very zoomed in. It should be possible to put a special case in that would make this work more quickly. |  | Pat | 1 |  | Workaround in place, working on another optimization that could save some memory and fix some other issues
4719 | ESA energy table updates – TDAS mods (ESA packet processing, calibration, summary plots, etc) | 2012-08-02 | Jim L | 1 | Aaron | Should have FLATSAT data soon to test with
4858 | One-count removal for velocity slices – make cutoff value a parameter | 2013-02-22 | Aaron | 1 | Aaron | Implement at lower level so can be used in more places
4700 | Trouble opening eps files exported from GUI | 2013-05-03 | Aaron |  | Aaron | Exports from slices gui OK, main gui not OK. Can be opened with OpenOffice on Linux, but not in Adobe Reader or Illustrator on Windows. IDL 7.0.6
4505 | Add a TDAS routine to do 1-d cuts - when ready to work send Aaron Bennenman an email for clarity of task and then review at the S/W meeting again with Vassilis. | 2012-02-06 | Aaron Breneman | 2 | Aaron | You could obtain a 1D cut of a slice by aligning the custom orientation vector (slice_orient keyword) such that the desired cut is along the x or y axis. The data could then be pulled directly from the array returned by thm_part_slice2d via the 'part_slice' keyword. This returns an R x R array containing the interpolated slice data (R=resolution). The x & y axis values for the array are returned in the 'xgrid' and 'ygrid' keywords. | 1 hr
4314d | combination of ESA and SST data could only be done in the Geometric mode. Would be great if it could be done in other modes as well. | 2011-08-11 | Xuzhi | 4 | Aaron | on hold | 1 hr
Cindy
4702 | Possible problem with neutral sheet model | 2013-05-03 | Cindy |  | Cindy | Fix tested and checked in
4703 | thm_map_add needs directory separator when building path to .sav file | 2013-05-03 | Harald |  | Cindy
4859 | Double check processing & mirroring of Greenland GMAG data | 2013-03-06 | Cindy |  | Cindy | Some data for site “upn” was missing at Berkeley but present at UCLA
4860 | Check inventory of Berkeley vs. UCLA GMAG CDFs and transfer any missing files | 2013-03-06 | Jim L |  | Cindy | On the Berkeley server, we have data for site "upn" for every day in 2010-06 *except* for 2010-06-06, the date used in the test. I'm looking in: /disks/themisdata/thg/greenland_gmag/l2/upn/2010 The CDFs for 2010-08-07 and 2010-08-08 are missing, too. It looks like there was a mass update of that directory in May 2012.
4842 | GUI API – Plugin access to GUI configuration settings dialog (remote, local data dirs, etc) | 2013-01-18 |  | 1 | Cindy | Another item for the master plugin config file (add a new mission to the dropdown in the configuration settings dialog) On hold until after TDAS 8.0
4611e | Add support to GUI configuration settings panel for editing/saving cdf_leap_second configuration. (See also: tasks 4516 and 1315 for ACE, WIND, ISTP). | 2012-04-17 |  | 1 | Cindy | May or may not make sense to combine with 4842, if too hard to integrate we can defer to a future release. On hold until after TDAS 8.0
Eric
4764 | Steps/Sawtooth pattern in FGS data near perigee | 2012-09-24 | Vassilis | 1 | Eric | Sudden changes at packet boundaries, probably a spin fit timing issue. On hold pending Jim L's analysis
4764a | Script to identify time intervals with FGL/FGH/FGE coverage in high B field | 2012-09-24 | Vassilis | 1 | Eric | Look at THD starting from early March 2013 (after full reset), see when glitches start happening. Anything to do with eclipse periods?
4764b | Look at FGS dB/dt and FGS header times to identify when glitches are occurring | 2012-09-24 | Vassilis | 1 | Eric
4764c | When glitches are present, compare FGS and waveform data looking for time offsets (off by 1 spin in FGS?) | 2012-09-24 | Vassilis | 1 | Eric | Seems to be happening intermittently, every other packet?
4688 | Add load routine for Kp index data. | 2013-04-08 | Xuzhi |  | Eric | ssl_general/key_param/load_kp.pro is obsolete, but Kp data is available from: ftp://ftp.ngdc.noaa.gov/STP/GEOMAGNETIC_DATA/INDICES/KP_AP/ Should check Tsyganenko cribs since some of them use Kp indices. There is also a IUGONET routine which is capable of loading some geomagnetic index data.
4689 | need to keep clicking “yes to all” when replaying document that overwrites data. Also need to track deletions of data. | 2013-03-27 | Pat |  | Eric | Looking into this one, I found that quite a few operations don't have overwrite queries tracked: Interpolate pwrspc calc nudge getspec Some seem to default to overwriting, some default to repeated queries to user. Original report: I loaded data for probes b and c and then went to plot the data and realised I should have loaded a and b for the tests. I returned to the load data panel and loaded the probe a data before deleting the probe c data. After saving as a themis document and reopening, the c data was loaded but not deleted. The data that was loaded and deleted using delete all data following the testscript does not appear when you reopen the document (as you'd expect).
4697 | Omni load, if no data available for selected interval, loads whatever is available for that month | 2013-04-26 | Eric |  | Eric | May be intentional to keep from producing empty tplot variables, but time_clip should at least produce a prominent warning.
4694 | Open legend options by clicking in legend box | 2013-04-18 | Eric |  | Eric | Similar to axis, panel, page options
1266 | Our numerical entry fields only accept exponential notation entries of the form (1.23e-3) but not the more traditional format( 1.23*10^-3). We may want to leverage the code base from the mini language so that we can interpret these entries as numbers. |  | Pat | 2 |  | Still happening? | 3 days
Jim L
4816 | Eclipse spin model processing: some eclipses not being processed with current code, but Ferdinand's code is giving results? | 2012-12-07 | Ferdinand |  | Jim L | Ferdinand has updated eclipse model parameters for inner probes
4709 | Manual eclipse processing resets "last processed" date for automated processing; some processing logs not preserved | 2012-07-24 | Jim L | 1 | Jim L | If the automated processing is up to date, and I manually reprocess a time range early in the mission, the "last processed" date will get reset to the earlier date, which could trigger an unintended reprocessing of the full mission. "last processed" date should only be updated if it moves forward in time.
4142 | issue with FGS processing - timestamps | 2010-09-30 | Vassilis | 1 | Jim L | not trivial. After 4764
2266 | Timing of Spin Fit data | 2009-10-16 | Jim McFadden | 1 | Jim L | See 4142 After 4764
Jim M
4690 | thm_mom_cotrans_cltestsuite is obsolete, either needs a complete rewrite to conform to current thm_load_mom usage, or merge any non-redundant tests into existing test scripts. | 2013-03-04 | Jim M |  | Jim M | This test script can be dropped. In fact, most of the “cotrans” CL test scripts should be folded into the instrument “load” CL tests, with the exception of tests like cotrans_all_combos.
4698 | time_clip/tclip | 2013-04-26 | Pat |  | Jim M | tclip is for clipping y-axis data, and doesn't do time clipping at all. Needs better documentation.
4784 | Add RBSP orbit data to THEMIS plots | 2012-10-16 | Vassilis |  | Jim M | 5/10/2013 Patched to hopefully fix a crash while trying to load a color table.
4820 | Need IDL-only FITS reader code suitable for inclusion in SPEDAS | 2012-12-11 | Mini-GEM |  | Jim M | Checked into SVN, needs to be documented in developers guide.
4152b | change the ESA tables such that the minimum magnetospheric electron energy becomes lower (about 3eV, or lower). McFadden can specify the lower energy | 2011-10-20 | Vassilis | 0 | Jim M | only ARTEMIS probes - Need to talk to Jim McFadden. Also need MOC Support. 5/03/2013: Need to update additional TOC checksums to prevent errors in instrument startup scripts.
4152c | change the ESA tables such that electrons and ions can be changed separately into magnetospheric and solar wind modes. | 2011-10-20 | Vassilis | 0 | Jim M
Nick
| Update FBK, FFT, ESA, SST configuration history HTML pages |  |  |  | Nick | Update monthly for now.
4691 | Use TLB_FRAME_ATTR in thm_ui_prompt_widget to avoid need for looping around overwrite/confirmation dialogs (by disabling [X] close button). | 2013-04-10 | Nick |  | Nick | Implement on one dialog first, test on all supported platforms, if it works everywhere, then convert the rest of the dialogs.
4834 | Add additional links to instrument configuration history pages | 2013-01-10 | Bob McGuire | 1 | Nick | 1) From ESA, SST, other instrument pages 2) L1/L2 master CDFs 3) Possibly from one of the “Data” dropdown menu items? Emmanuel working on web site updates
2078 | bau_sunpulse_met assumes x86 endiannes (BugzID=13) |  | Vassilis | 3 | Nick | Tmtools libdecom code. On first call, do runtime call to check whether floats are big-endian or little-endian, set a static flag in that routine, then do appropriate conversion. JWL to test.
4683 | Change L2 FIT master CDF to allow different sample counts for efs and efs_dot0 |  | Jim L |  |  | In progress.
4684 | thm_cal_fit: clean up NaNs in fgs and efs, reprocess L2 FIT |  | Jim L |  |  | After 4683. Will need to change code that writes variables to L2 CDF.
4704 | Web site code & files should be checked into SVN | 2013-05-09 | Jim L |  | Nick | Workflow to update web site might need to change to keep in sync with repository
Pat
4713 | Since the diode degradation will be modeled as shifting the minimum energy of the SST up, we'll need to interpolate the SST efficiency parameters to the new energy bins. | 2012-07-24 | Vassilis | 0 | Pat | This may not actually be done by someone on the software team, but I thought I'd report it anyway, so that it doesn't get lost in the shuffle once the other calibrations are completed.
4844 | Different SST look directions no longer line up in energy with original calibration factors | 2013-01-24 | Pat | 0 | Pat | What we came up with is to interpolate the esa to match SST(in time & look direction), then smooth the ESA data to account for poor count statistics, then interpolate between the SST and the ESA to shift the SST to a regular energy grid. This will be a decent amount of effort to code up, but it seems promising. Will probably not make it into TDAS 8.
4771 | Writeup for new SST calibration | 2012-09-28 |  | 0 | Pat/Drew | For senior review. After 4844. (But 4844 will likely not be ready for TDAS 8 release...ready when senior review is due?)
4861 | Code maintenance issue – GUI coordinate systems |  |  |  | Pat | But there may be a code maintenance issue since we maintain two lists of supported coordinate systems. (One in thm_ui_req_spin.pro & one in thm_ui_cotrans_new.pro I just used a comment to future programmers, but a single list would probably be more durable.
4696 | Reorganize crib sheets | 2013-04-03 | Pat |  | Pat | Maybe separate directories for “basic”, “advanced”, experimental” functions? (Will also need to update users guide and quick reference guide to reflect new crib locations)
4699 | improve time series handling in plotxyz | 2013-04-29 | Pat |  | Pat | Add x-is-time, y-is-time keywords
4701 | thm_part_moments2 very slow with certain options | 2013-05-03 | Pat |  | Pat | Possibly related to new SST calibrations?
4832 | Allow keywords in calc function calls | 2013-01-07 | Vassilis | 1 | Pat | e.g. calc,'a=total(b,/nan)'

## TDAS Enhancements
Task # | Task Description | Date Opened | Reported By | Pri | Assigned To | Notes | Estimate | Level of User Impact
Proposed Enhancements
4058 | This is getting a bit out of hand I think. How about a configuration file? The software just reads keywords from a configuration file. With such a configuration file it is possible to set keywords automatically (for the scientists) but additionally it would give us the possibility to keep track of what the software does automatically. When I do calibrations I can then save the configuration file together with the results and not worry about the things that the software might have done automatically. | 2010-05-10 | Hannes | 3 | Hannes | Hannes sent out new version for review.
519 | We should extend our data model to support 3-dimensional distributions and 3-dimensional image data. This will entail modifications to load widgets, the loaded data object,the tree widget, the data processing widgets, and the addition of a means to draw | 2011-10-17 | Vassilis | 3 | Aaron
519a | She asked about generating ASI plots, like the ones done online, with the ASI data superimposed on a map. Ultimately, we may be able to implement this in a method similar to the method used for overview plots. |  | Xiaoyan | BL
4299 | it looks like a way to better integrate the slices code with the THEMIS GUI without major modifications. In the current version, it doesn't generate the plots in the main themis window and it doesn't store the slices data in GUI memory. This means that you can't use analysis routines or change plot options the way that you can for other data types. But if we map the slices data into our current data model by storing the slices as if they're spectral data, we can include these data without any major changes. You wouldn't be able to automatically scroll through a series of slices, but they would be stored in the GUI memory so that you could plot them using the standard routines, perform analysis using the standard routines and export/save using the standard routines. | 2011-07-27 | Pat |  |  | Vassilis 7/27/11: These are good to haves but I think we are not cut for such a sophisticated system. We just need the basic cuts - they'd be already 10 times better anyone has ever done! 1-25-2013: Revisit the issue if/when we ever implement GUI plot types for 2-d (map-like) data. See 519,519a.
4313 | While on the telecon with Alberta, I was looking at the IDL documentation for their built in http download object. It actually makes it look like the http authentication, with username and password would not be too difficult. Since this keeps coming up, we might want to consider dedicating a few hours of programming time to see how hard it actually is to do authenticated downloads. If it turns out not to be too hard, it would probably give us the capability to extend our system to a lot more types of data. | 2011-08-11 | Pat | 3 | Lydia | when the need arises - on hold; Lydia 6/1/12: I think the idea of writing routine to download files using the IDL netURL objects to replace file_http_copy was discussed briefly at one of the software meetings. If this is done at some point then task 4313 to include the ability to authenticate/use passwords could be included in the new routine.
1149 | If you accidentally close an overview plot page, it would be nice to be able to recreate the plot without having to reload all the data. |  | Bryan | EL |  |  | tbd
1150 | If you open and close the overview panel, it doesn't store the current data. (or use the one that is available from the loaded data panel) It probably should. |  | Pat | EL |  |  | tbd
1283 | Something we might want to put on the list is looking into making the overview plots load faster and use less memory. Right now they are much less efficient than they could be. |  | Pat | EL |  |  | 2 days
808 | IDL Format Code -currently have no way to insert a different font in the middle of a string (e.g. adding a symbol to a string in NewTimesRoman). Possibly enable formatting like we did for the z axis labels |  | Oldie |  |  |  |  | 1 day
1512 | Cancel load process |  |  | EL |  | How to implement within GUI? Command line? Tbd
2030 | upgrade thm_load to work with probe assignments |  | Vassilis | 3 | Lydia
806a | Markers -1) Allow feature for user to control marker lines (style, color,size) marker text (font, format, color, size), and marker shaded region (color, opacity) 2) Add logic to check when tracking all is on so that selected markers will be selected for all panels. 3) If multi-panel tracking is on, subset all visible panels at the same time-range. |  |  | 3 |  | Vassillis reviewed on 7/20/09 | 1 week
4297 | One, the slices code should probably throw out the top four SST energy bins when it uses the default SST load and calibration. Those bins are not properly scaled in the default SST code and their energy boundaries are wrong. Vassilis 8/1/11: SST Calibration will fix. This task should be closed if the old SST calibrations are retired; if the old calibrations are still available as an option, reconsider keeping this task open. | 2011-07-27 | Pat | 2 |  | On hold till the SST calibrations have found wider use. Aaron 7/27/11: For the first suggestion (of throwing out the top 4 SST bins) that is something that I think we would want to implement at a lower level than the slices; perhaps as a keyword to the routines that load the data. We could do a specific implementation for the slices, however, the underlying issue should probably be addressed for any code using SST data. This is probably something we should discuss at the next meeting. If we decide to implement a slices-specific fix then it should be noted in the user's guide.
2140 | A suggestion: The function used by tsub_average to return the median or average of the data can also be used to return the standard deviation. Since a single panel will probably be made for both the subtract average and subtract median options we could also add a third option to add/subtract the standard deviation. |  | Aaron | tbd |  | Subtracting the stand. dev. from a quantity may not make sense in the way that subtracting the average/median does. We may just want to direct people to the calculate panel, possibly adding a function to calc. stand dev. - Pat
4695 | I noticed that, currently, when a nudge is performed it splits the component out of its group to create the new nudged quantity. We might want to consider allowing users to nudge entire groups to prevent this problem |  | Pat | EL
4135 | Now that the L1 ESA/SST/MOM reprocessing is underway, these CDFs will soon contain the full ESA and SST configuration words, in addition to the solar wind flags, sweep modes, and so forth. With the full configuration data available, if someone wants to use a property of these instrument configurations that's not already present as a L1 variable, we don't need to reprocess L1 to add it -- we just write a little more code for TDAS, to extract the new attribute from the configuration data that's already present. | 2010-09-10 | Jim L | 3 | Ben | On hold, after QA.
4135b | In the load and/or calibration routines for ESA, SST, MOM: rather than using the ESA solar wind flags and sweep mode from the L1 CDFs, use the ESA full configuration instead (which is present in all three L1 types, for convenience), and use the routines from 4135a to extract the solar wind flags, sweep mode, and any other useful attributes. I think SST does not have any configuration flags similar to the ESA quantities (there's the attenuator status, but that's separate from the instrument configuration word), but it needs them in the future, they should be handled the same way as ESA (extract from SST configuration word instead of adding L1 variables). I can do this, but if the routines from part (a) are well-documented, any of us could probably do this part. | 2010-09-10 | Jim L | 3 | Ben | On hold, after QA. | 2-4 hrs
1447 | Look into file compressions methods - possibly apply to redraw |  | Pat | EL
2055 | ESA L2 from L1 (not packets) - create L2 and test thoroughly, then reprocess ESA |  | Vassilis | 3 | Jim M | On Hold; awaiting Jim L to split L1 into master cdf
QA002 | IDL 8.1 font changes -- text no longer correctly formatted | 2012-01-18 | Pat
QA003 | IDL 8.1 changed window behavior (z-ordering): when options panels opened, main GUI window disappears behind main IDL window. Happens with modal and non-modal windows. | 2012-01-18 | Aaron
QA005 | IDL 8.1 GUI plots laid out differently; margins and fonts have changed, even with all default settings in place. | 2012-01-18 | Aaron
4685 | “Scale to Page” layout option | 2013-04-04 | Nick |  | tbd | The "problem": When we add panels they become smaller in order to fit into the page. An extreme case is the overview plot. The solution: We could add a menu selection under Graph, called "Scale to Page", and when it is checked (the default) everything will work as it does now. If the user unchecks it, then the panels will get longer and the page will get longer too (or we can split it into multiple pages). This will probably be helpful when the user wants to inspect the plots, or copy-paste into Word, or for posters etc. It may also help with the overlapping labels problem in the overview plots. This will need to be tested using multi-column as well as single-column layouts.
4686 | Refactor axis options code | 2013-04-05 | Eric |  | tbd | we may want to eventually spend some time refactoring the axis options code. It's over 4,600 lines, has inconsistent tabbing in several places and there seems to be lots of obsolete code commented out.
QA127 | Axis options -- “apply” affects multiple panels | 2013-04-16 | Pat |  | tbd | After QA. I'm attaching a gui document to help reproduce. Problem: when I set y-axis ticks to aesthetic=off, then I select "apply to all" the ticks on all panels change. If I then select "apply", the ticks on panel 3 change again.(even though I have panel one selected and did not "apply to all") #1 Load GUI document. #2 Open y-axis options, select ticks tab. #3 Uncheck "aesthetic ticks" #4 Select "apply to all" #5 Select "apply". (Error: panel 1 *AND* panel 3 change)

## SOC processing enhancements
Task # | Task Description | Date Opened | Reported By | Pri | Assigned To | Notes | Estimate | Level of User Impact
Proposed SOC processing Enhancements
4022 | Update L1 master cdfs to support SPDF hosting | 2010-03-25 | David | 3+ | Jim L | I think 4022 is a an end-of-mission task: basically clean up all the L1 CDFs, so they are fully ISTP compliant and as compatible as possible with SPDF's tools. But "ISTP compliant" is a moving target -- they keep adding new checks to the SKTEditor software -- so I think we made a task to do one final cleanup and reprocessing at the end of the mission, as opposed to reprocessing every time they introduce a new SKTEditor check that renders our L1 files non-ISTP-compliant. So 4022 = final end-of-mission adjustments to master CDFs, 4023=final reprocessing. Both should remain open, with no immediate action required as far as I know.
4040 | Spinfits - separate E&B timestamps? | 2010-04-15 | Jim L | 3 | Jim L | SPDF has issue creating plots on the L1 data with their software | 2 hrs
4046 | either thm_load_fit or the GUI code that calls thm_load_fit should split the data into separate tplot variables for E and B, before importing them into the GUI data model. I think thm_load_fft already does something like this. See task 4040 | 2010-04-23 | Pat | 3 | Jim L | Jim M 4/23: thm_load_fit also splits into efit and bfit variables, so unless you need to look at raw bytes, the 'fit' datatype is not needed. Pat: Agreed. Short term, excluding the data type from the GUI seems like an easy solution.
2047 | task 2047 in my name: "Seperate E and B timestamps for spin fits", which is also a change to the L1 FIT master CDF and associated TDAS code. But unlike the spacecraft potential enhancement (which only adds new CDF variables, and is more-or-less backward compatible), 2047 would require us to bump the L1 FIT CDF version number to V02, and produce both V01 and V02 for a while, so users of TDAS 5.20 and earlier will still be able to load L1 FIT data. So I'm not sure whether the spacecraft potential task should include 2047, or not. | 2010-03-02 | Jim L | 4+ | Jim L
2081 | Evaluate CDF compression algorithms BugZid=81 |  | Vassilis | 4 | Jim L
2038 | STATE Web Page (s) |  | Vassilis | 3 | Jim L | review web pages
2040 | L1 Data Processing History Info: SCM, EFI, STATE |  | Vassilis | 3 | Jim L | Ben???
2077 | Non Monotonic timestamps. BugzID=72 |  | Vassilis | 3 | Jim L
4075 | describe the FBK data type, time tag specified to correspond to the beginning of the time interval of the data that went into the FBK data, the middle, or the end, or is that unspecified, and what's happening here is that the time tagging is being changed in year 3+ of the mission - in the L1 file definition document, at least, does not define the time-tagging conventions to this level of detail. | 2010-06-11 | John Bonnell | 4 | Jim L
4023 | Before EOM reprocess L1 cdf's due to master cdf changes for SPDF | 2010-03-25 | David | 4 | Jim L
2080 | Phantom packets" cause non-monotonic distribution times. BugzID=25, low priority. |  | Vassilis | 4 | Jim L
2081 | Evaluate CDF compression algorithms BugZid=81 |  | Vassilis | 4 | Jim L
2083 | Add "last processed" time to L1 (and L2?) CDFs BugZid=115 |  | Vassilis | 4 | Jim L
4097 | cdf's with MD5 checksum | 2010-07-19 | Jim L | 4 | Jim L | Jim L to send email with subtasks and estimates
2046 | Create a more efficient & productive prototype QA Instrument Command Line Script - first template (s) functional blocks then scripts for FGM, ASK, SCM, FIT, MOM, ASI, EFI, FFT, FBK, Gmag, State, SST, ESA |  | Jim L | 2 | Ben | Save v7.0 templates and saved files.
4532 | Developer's guide update re: "touched" properties, standard way of tracking which settings were changed at user's request. | 2012-02-27 | Pat | 2 | Ben | with 4455
4214 | THEMIS Pipeline proof of concept regression tests |  |  |  |  | On hold, after QA.
4214e | GMAG | 2011-03-23 | Jim L | 2 | Ben
4214f | AE Index | 2011-03-23 | Jim L | 2 | Ben
4214g | ASI | 2011-03-23 | Jim L | 2 | Ben
4214h | mosaics | 2011-03-23 | Jim L | 2 | Ben
4214i | summary plots | 2011-03-23 | Jim L | 2 | Ben
2091 | Once Jim McFadden completes his mods for n_3d_new_3 reprocess L2 cdf's - entire mission |  | Vassilis | 3 | Jim M

## Unconfirmed bug reports
Task # | Task Description | Date Opened | Reported By | Pri | Assigned To | Notes | Estimate | Level of User Impact
Unconfirmed/hard to reproduce bugs
QA020 | Calculate, panels with modified variables sometimes blank | 2013-03-08 | Aaron |  |  | (cannot consistently reproduce) There were a few times where the panel containing a variable that was modified in calc was blank after exiting, even though auto range was on. The panel would be blank with a [0,1] y-axis range (the data was valid and worked fine on a new panel).
QA024 | Axis options – negative min on log axis | 2013-03-08 | Aaron |  |  | (cannot reproduce) The y-axis min/max was reset to [1,inf] after Applying a negative min on a log axis. When I attempted to set it to [1,20] a min>max error was given and the range set to [0,1].
QA031 | Performance issue, memory usage | 2013-03-08 | Aaron |  |  | Not clear if still happening? After running IDL for I while I end up needing to restart to free up memory. I seem to be noticing it the most after I have recently loaded large amounts of data, but it's hard to say exactly what might be causing it without more targeted testing. I attached a screen shot exampling the memory freed from a .full_reset_session and from exiting IDL (restarting IDL only added ~100mb back). I'm not sure when I last restarted so this could be a small issue that accumulated over time.
QA082 | Data processing, cotrans | 2013-03-26 | Aaron |  |  | Having trouble reproducing. I received an "unexpected error" when trying to transform a variable from DSL to SSE. SLP data was already loaded into to GUI from a previous cotrans operation and had not been modified. Console output below. STORE_DATA(221): Creating tplot variable: 11 newpos_sse DSL2GSE(210): done Traceback Report from THM_UI_COTRANS_NEW: $MAIN$ THM_UI_DPROC_PANEL_EVENT <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_dproc_panel.pro( 146)> THM_UI_COTRANS_NEW <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_cotrans_new.pro( 353)> ERROR_MESSAGE <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\utilities\error_message.pro( 256)> Last IDL Error: % GSE2SSE: ERROR: slp_sun_pos needs to be in GSE or GEI coordinates % Execution halted at: GSE2SSE 123 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\state\cotrans\gse2sse.pro
QA028 | Data processing – solar/lunar ephemeris load failed when replaying saved document | 2013-03-08 | Jim M |  | Pat | Having trouble reproducing. Loading Solar/Lunar ephemeris data... Object reference type required in this context: VAR.
QA006 | IDL 8.1 intermittent crashes in eclipse processing code | 2012-01-19 | Ben

## Closed Post v8.0
Task # | Task Description | Date Opened | Reported By | Pri | Assigned To | Notes | Estimate | A&E; crib; script; suite; UG; DevG; Qref; AdmG
4611d | Nightly thmsoc cron job to check/install updates to SPDF leap second table on SSL data server. Lower priority; probably won't be another update for at least a year. | 2012-04-17 |  | 4 |  | Complete by April 2013
4042 | Script to run every two weeks to runs IDL TDAS and checks if a file can be loaded from THEMIS SPDF file (s) | 2010-04-19 | Pat | 3 |  | see Pat
4706 | Missing data from McGrath magnetometer site | 2012-07-18 | Cindy | 1 | Cindy | 2/22/2013: RMD files received, but data not being processed for some reason.
1496 | State Reduced: The themis document doesn't keep track of the current page. Maybe it should. |  | Pat | EL
4862 | Reprocess L2 FIT data to fix efs_0, efs_dot0 (different counts of timestamps and data values)
4792 | 2013 MAP for Senior Review | 2012-11-01 |  |  | Jim L
4685 | Widget tree expansion, IDL 8.2 | 2012-06-26 | Pat | 1 | Aaron | IDL fixed a bug which we had worked around, need a version check to enable/disable the workaround so it will work on all IDL versions.
4857 | thm_convert_esa_units, conversion to energy flux and back not symmetric | 2013-02-22 | Aaron | 1 | Aaron
4760 | Add McMac magnetometer network (12 sites) to our data set. | 2012-09-17 | Vassilis | 1 | Cindy | 2/22/2013: Server problems at McMac data server, back data from 2007, 2008 being processed.
803 | Would be nice to have a way to move different panels from one page to another | 2011-11-22 | Oldie | 2 | Pat | sort how level of effort to accomplish. On hold, after QA
4855 | Discrepancy between spacecraft positions in summary plots. | 2013-02-08 | Mike Hartinger |  | Jim M | I noticed a discrepancy between the spacecraft position data shown at the bottom of the summary plots on the THEMIS website. The particular summary plots I compared were 2008-02-26 06:00-08:00, THEMIS-E - "Overview", "Space ESA moments", and "Ground ESA moments". The position data from "Overview" and "Ground ESA moments" differ from the position data from "Space ESA moments". 2-15-2013: Fixed, reprocessing plots.
4843 | Cron job to update configuration history database | 2013-01-24 |  | 1 | Nick | FBK done, FFTs next
4537 | Deletion of data not reflected in saved/reloaded THEMIS document. Formerly QA206. Also remember to overwrite prompt setting (yes to all, etc) | 2012-03-02 | Lydia |  | Pat | See 4689
4847 | Improve TDAS installation instructions for external libraries like IDL_GEOPACK | 2013-01-29 | John Bonnell |  | Cindy | May require sysadmin assistance if user doesn't have permission to update IDL installation directories. We should also mention the option of installing to an alternate location and using the DLM_PATH environment variable, rather than updating the IDL directory. README.txt with IDL_GEOPACK installation instructions already updated, copy into user guide and quick reference guide (if IDL_GEOPACK is mentioned at all there).
2100h | Try to track down frequency scaling problem in DPWRSPC (dlimit setting? Compare to old plots?). |  | John Bonnell | 4 | Eric | regenerate test plot and see if fixed after TDAS 8
4705 | Fix master CDF to correct bad long/lat for one McMap site, reprocess data CDFs | 2013-05-09 | Tami |  | Cindy
4693 | xtickinterval, ytickinterval for specplot.pro | 2013-04-15 | Andrew Poppe |  | Jim L | Suggest using plotxyz instead of specplot...JWL to mail AP and see if that meets his needs. I've been using specplot.pro directly to make plots and have noticed that it doesn't seem to accept the 'xtickinterval' or 'ytickinterval' keywords as part of the limits keyword structure. Can someone confirm this, and if so, would it be possible to add this functionality?

## TDAS 8.0 Release Notes
Task # | Task Description | Date Opened | Reported By | Pri | Assigned To | Notes
To be Assigned or Discussed
RN001 | Memory leak switching pages with IDL 7.1 and above (fixed now?)
RN002 | IDL 7.1 excessive RAM usage in interpolate (doesn't happen in 7.0.6)
RN003 | IDL 8.2.2, thm_cal_fgm extremely slow
RN004 | IDL 7.1: NaNs treated differently in interpolation, only affects IDL 7.1.

## TDAS 8.0 Open Bugs
Task # | Task Description | Date Opened | Reported By | Pri | Assigned To | Notes | Estimate | A&E; crib; script; suite; UG; DevG; Qref; AdmG
QA109 | Reorganize crib sheets | 2013-04-03 | Pat |  |  | Maybe separate directories for “basic”, “advanced”, experimental” functions? (Will also need to update users guide and quick reference guide to reflect new crib locations)
QA147 | Omni load, if no data available for selected interval, loads whatever is available for that month | 2013-04-26 | Eric |  |  | May be intentional to keep from producing empty tplot variables, but should at least produce a warning.
QA148
QA149
Aaron
Cindy
Eric
Jim L
Jim M
Nick
Pat

## QA v8.0 Bug List - Closed
Task # | Task Description | Date Opened | Reported By | Pri | Assigned To | Notes
To be Assigned or Discussed
QA001 | valid_names for thm_load_fft not working | 2013-02-28 | Cindy |  |  | Test suite fails in fresh session, works if retried
QA002 | valid_names for thm_load_fbk not working | 2013-02-28 | Cindy |  |  | Test suite fails in fresh session, works if retried
QA011 | crash in variable options | 2013-03-05 | Eric |  |  | % Type conversion error: Unable to convert given STRING to Long. % Detected at: ARRAY_CONCAT 29 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\ssl_general\misc\array_concat.pro % Type conversion error: Unable to convert given STRING to Long. % Detected at: ARRAY_CONCAT 29 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\ssl_general\misc\array_concat.pro % Type conversion error: Unable to convert given STRING to Long. % Detected at: ARRAY_CONCAT 29 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\ssl_general\misc\array_concat.pro % WIDGET_CONTROL: String expression required in this context: VARNAMES. % Execution halted at: THM_UI_VARIABLE_OPTIONS_INIT 819 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_variable_options.pro % THM_UI_VARIABLE_OPTIONS_EVENT 456 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_variable_options.pro
QA005 | Multiple failures in thm_fit_cal_cltestsuite, also same error in thm_fit_cotrans_cltestsuite | 2013-02-28 | Jim L |  |  | All tests failed with similar error: ;Test 0 Failed: thm_cal_fit,probe='a',datatype='efs' ;ERROR: -163 ;ERROR: % Subscript range values of the form low:high must be >= 0, < size, with low ;ERROR: <= high: <No name>. ;ERROR: % Execution halted at: THM_CAL_FIT 455 /home/jwl/tdas_8_00/idl/themis/spacecraft/fields/thm_cal_fit.pro ;ERROR: % $MAIN$ 42 /home/jwl/tdas_8_00/QA_testing/thm_fit_cal_cltestsuite.pro
QA006 | Failure in thm_fit_cal_template | 2013-02-28 | Jim L |  |  | THM_CAL_FIT(334): No good fit codes, assuming that E12 is used for EFS % Variable is undefined: NE34. % Execution halted at: THM_CAL_FIT 355 /home/jwl/tdas_8_00/idl/themis/spacecraft/fields/thm_cal_fit.pro % $MAIN$ 51 /home/jwl/tdas_8_00/QA_testing/thm_fit_cal_template.pro
QA008 | Failure in gmag_load_cltestsuite | 2013-03-04 | Jim M |  |  | Apparently the CDF for site UPN for 2010-06-06 is missing from the Berkeley server. ;Test 22 Failed: test dtu_sites ;ERROR: -5 ;ERROR: % $MAIN$: data load failed ;ERROR: % Execution halted at: $MAIN$ 699 /home/jimm/thmsoc_sw/QA_testing/thm_gmag_load_cltestsuite.pro
QA003 | Blank plots 1-10 in thm_slice2d_cltestsuite.pro | 2013-02-28 | Eric
QA004 | Test 11 failed in thm_slice2d_cltestsuite.pro | 2013-02-28 | Eric |  |  | ;Test 11 Failed: Multiple distributions ;ERROR: -224 ;ERROR: % Tag name VELOCITY is undefined for structure <Anonymous>. ;ERROR: % Execution halted at: THM_PART_SLICE2D_GETVEL 80 C:\Users\egrimes\Desktop\Space\tdas_8_00\idl\themis\spacecraft\particles\slices\thm_part_slice2d.pro ;ERROR: % THM_PART_SLICE2D 954 C:\Users\egrimes\Desktop\Space\tdas_8_00\idl\themis\spacecraft\particles\slices\thm_part_slice2d.pro ;ERROR: % $MAIN$ 371 C:\Users\egrimes\Desktop\Space\thmsoc\trunk\QA_testing\thm_slice2d_cltestsuite.pro
QA037 | GMAG labels | 2013-03-11 | Jim M |  |  | Note that the suite passes, except for step 5c) Labels for NAQ are (D, H, Z) instead of expected (dD, dH, dZ).
QA025 | Overview plots – crash in calendar widget | 2013-03-08 | Jim L |  | Eric | Traceback Report from THM_UI_TIME_WIDGET_EVENT: $MAIN$ THM_UI_TIME_WIDGET_EVENT </home/jwl/tdas_8_00/idl/themis/thm_ui_new/utilities/thm_ui_time_widget.pro( 50)> ERROR_MESSAGE </home/jwl/tdas_8_00/idl/themis/thm_ui_new/utilities/error_message.pro( 256)> Last IDL Error: % Keyword parameters not allowed in call. % Execution halted at: THM_UI_TIME_WIDGET_EVENT 126 /home/jwl/tdas_8_00/idl/themis/thm_ui_new/utilities/thm_ui_time_widget.p
QA040 | Interpolate calendar widget | 2013-03-11 | Cindy |  |  | Error message reported whenever I use the calendar icon. Once the error is reported anything done with time (text box widget, check box for single day) produces an error. If I don't use the calendar icon the time text box and check box work fine. The error message is below.Last IDL Error: % Expression must be a structure in this context: STATE. % Execution halted at: THM_UI_TIME_WIDGET_EVENT 171 C:\Users\clrussell\Desktop\tdas_8_00\idl\themis\thm_ui_new\utilities\thm_ui_time_widget.pro % XMANAGER: Caught unexpected error from client application. Message follows... % Tag name GUI_ID is undefined for structure <Anonymous>. % Execution halted at: THM_UI_INTERPOL_OPTIONS_EVENT 153 C:\Users\clrussell\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\dproc\thm_ui_interpol_options.pro % XMANAGER_EVLOOP_REAL_MODAL 506 C:\Program Files\ITT\IDL706\lib\xmanager.pro % XMANAGER 704 C:\Program Files\ITT\IDL706\lib\xmanager.pro % THM_UI_INTERPOL_OPTIONS 447 C:\Users\clrussell\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\dproc\thm_ui_interpol_options.pro
QA041 | dproc_power_spectra | 2013-03-12 | Nick |  |  | Error in calendar widget
QA034 | Suggestion, “save data as” | 2013-03-11 | Nick |  | Nick | For consistency the message in the status bar should say "Load Data" and not "Load THEMIS Data". Perhaps there are some other messages like that.
QA035 | Suggestion, closing pages | 2013-03-11 | Nick |  | Nick | When I produce a lot of pages I close them using Ctrl+Z, which is handy but it is very easy to also close the first page. Perhaps, if there is only one remaining page, TDAS should ask user permission (dialog message "Close last remaining page?", with OK-Cancel).
QA026 | Pages menu – checkbox incorrectly turned off | 2013-03-08 | Nick |  |  | With multiple pages, if you select the page you're already on, the checkbox in the menu is incorrectly turned off.
QA033 | Crash in thm_load_mom | 2013-03-08 | Aaron |  | Jim M | I received a crash from the load data window when loading all MOM data for all probes on 2013-03-05. Last IDL Error: % Array has too many elements. % Execution halted at: XDEGAP 231 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\ssl_general\misc\xdegap.pro % DYDT_SPIKE_TEST 97 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\ssl_general\misc\dydt_spike_test.pro % THM_ESA_DTC4MOM 479 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\spacecraft\particles\moments\thm_esa_dtc4mom.pro % THM_APPLY_ESA_MOM_DTC 98 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\spacecraft\particles\moments\thm_apply_esa_mom_dtc.pro % THM_LOAD_MOM_L2 142 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\spacecraft\particles\moments\thm_load_mom_l2.pro % THM_LOAD_MOM 587 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\spacecraft\particles\moments\thm_load_mom.pro
QA044 | Tooltips needed |  |  |  |  | The following options could use tooltips describing their function: -Bound autoscaling range (range tab) -Log minor tick type (ticks tab) -Save to Template -Apply to All Panels
QA012 | y axis options – set all panels | 2013-03-05 | Eric |  | Nick | test 51a is supposed to apply the title/subtitle font/format/size/color options to all other panels - does not seem to work. Title/subtitle/labels not applied (by design), but should allow “set all” font/format/size/color.
QA045 | Data processing – smooth data |  |  |  | Jim M | Block Average warns the user if the specified resolutions is shorter that the data's median cadence. It appears no similar check is done for Smooth Data.
QA050 | Slice2d – new SST calibrations | 2013-03-13 | Aaron |  |  | Attempting to create a slice using the new SST calibrations with psir data failed gracefully, as expected, however it gives the user an "unknown" error in the GUI. Neither that error nor the command line output it points to mention that the new calibrations are only valid for full and burst data (which should be what's causing the failure). (tha_psir, 2013-03-05/12:10 - 12:15, 90 sec window & step size, GSM)
QA052 | Slice2d – perturbed normal vector | 2013-03-13 | Aaron |  |  | (enhancement) Perturbing a cut's normal vector slightly off the x axis yields non-intuitive coordinates. This is because the choice of what vectors to use for the slice's x/y axes is usually determined by the projections of original coord's x axis. When the normal is set to x the slice's x/y are properly set to y/z; however, if the normal is off by a bit then then the (very small) projection will be used instead.
QA053 | Slice2d – line thickness | 2013-03-13 | Aaron |  |  | (quick enhancement) The axis and energy limit lines are drawn thicker than usual (I think the code was initially copied from thm_esa_slice2d). Drawing them with the default thickness would be consistent with the rest of the plot.
QA042 | “Omni” tab almost completely cut off in load data panel | 2013-03-11 | Jim L |  | Cindy | Platform dependent? (IDL 6.4, Linux)
QA014 | z axis options – 'Major Ticks' sensitized when no panels added yet | 2013-03-06 | Eric
QA045 | Data processing – smooth data |  |  |  | Jim M | Block Average warns the user if the specified resolutions is shorter that the data's median cadence. It appears no similar check is done for Smooth Data.
QA015 | xy axis options -- “equal X Y axis scaling” never sensitized? | 2013-03-07 | Nick |  |  | Is this feature used anywhere?
QA047 | Slice2d – multiple warnings | 2013-03-13 | Aaron |  |  | When producing a plot for the default time range using peif, peir, and peib for probe B I get three error messages stating that there is no peif data in that range. There should only be one message.
QA051 | Slice2d – FAC axis descriptions | 2013-03-13 | Aaron |  |  | (enhancement) The axis descriptions for slices along field aligned coordinates could be more descriptive. Right now they only denote the coordinates used (e.g. RGEO) and whether that axis is along x/y/z. The older rotations have somewhat more descriptive annotations.
QA017 | Calculate help window | 2013-03-08 | Aaron |  |  | The help window's Done button is drawn on the top left. It would be more consistent to draw it centered at the bottom of the window. Also, the help window's examples section could use examples of: -dimension option usage -proper use of logical and comparative operators (e.g. "&&" and "ge")
QA018 | Calculate error messages | 2013-03-08 | Aaron |  | Pat | The error message printed from a mis-match of dimensions (from a median operation) is ambiguous. Many other errors from calc may be hard for the user to interpret, but this one appears to have a specific issue. Also, It would be useful for the gui to print a line numbers with the error messages.
QA038 | MOM reduced – memory usage | 2013-03-11 | Eric |  |  | The MOM reduced suite failed twice on IDL 7.1/Linux. The first time was at test 6 (f) and only gave the following error before forcing IDL to close completely: 'Fatal error: IDL has encountered a fatal error and will now exit' I tried starting over from scratch and it failed again, this time at test 6 (k) with the error: 'Unable to allocate memory: to make array' -- followed immediately by the same 'Fatal error' as before. I then switched over to Windows 7 and tried again (from the beginning) and was able to complete the test error free, but not without eating most of the systems memory. I'm thinking there may be a memory leak somewhere - getting through the suite on Windows 7 took around 9GB of RAM, which didn't get released until I completely closed IDL (note that .full_reset_session did not release the memory).
QA023 | Legend options – crash changing font size | 2013-03-08 | Aaron |  |  | I get a crash when I apply a font size change with the Apply to All Panels option on a page with two panels and two separate variables plotted on the second panel. Error message below: Last IDL Error: % Attempt to subscript LISTOFTRACES with I is out of range. % Execution halted at: THM_UI_DRAW_OBJECT::ADDLEGEND 281 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\display\draw_object\thm_ui_draw_object__addlegend.pro % THM_UI_DRAW_OBJECT::UPDATEPANELS 883 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\display\draw_object\thm_ui_draw_object__updatepanels.pro % THM_UI_DRAW_OBJECT::UPDATE 156 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\display\draw_object\thm_ui_draw_object__update.pro % THM_UI_LEGEND_OPTIONS_EVENT 335 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_legend_options.pro
QA022 | Legend options – placement boxes | 2013-03-08 | Aaron |  |  | a) When the placement boxes are checked the units are reset to points but the units dropdown widgets are not updated. b) Clicking apply in such cases will not set the current placement values (in points) until the text widgets are selected. (e.g. If you open the window, check left & bottom, change units to cm, uncheck then re-check left & bottom, and then click apply nothing will happen. Once you click in the text boxes the their values will be interpreted as points.)
QA048 | Slice2d – smoothing | 2013-03-13 | Aaron |  |  | (bug/enhancement) a) The smoothing option will cause "smearing" in some cases with data gaps (in this case, thb_psif 2008-02-26/04:55 +5 min, BV cut, 3d interpolation, 3 point smoothing window). I don't think this is something we can fix without replacing the smoothing function (smooth). b) I think replacing Smooth is already in order. Smooth performs a simple boxcar average across each dimension with a specified width. For 2d data that is meant for a contour plot this leads to unrealistic square artifacts in the plots, especially at lower resolutions. IDL has a built in convolution routine (convol) which would certainly be preferable if it is able to accept a large number of points. I haven't checked the documentation in detail yet but it *may* be feasible to do this for v8.
QA029 | Overview plots – invalid date error re-occurred when replaying saved document | 2013-03-08 | Jim L |  | Pat | Accidentally selected date 2007-01-01 first time through, error reoccurred on playback.
QA054 | Calculate – adding variable twice in succession only adds it once | 2013-03-14 | Pat |  |  | If I have one variable loaded, select the variable to add it to my calc window, then click it again to add it a second time, the variable is only added the first time. The history window does note my additional selections, just somehow, they're being ignored.
QA027 | Layout options – overflowing labels | 2013-03-08 | Eric |  |  | in test 11 (q), y axis labels from from panel 3 do run into the trace labels for panel 2 (the test says to make sure the y axis labels from panel 3 don't run into panel 2)
QA016 | Markers – remove desensitized “use marker name as default” menu item | 2013-03-07 | Aaron
QA055 | Type mismatch loading TGD file (generated idl 8.2.2, loaded idl 7?) | 2013-03-15 | Pat |  |  | When I try to run this document, I get the following error:THM_UI_READWRITE::BUILDFROMDOMELEMENT: Type mismatch: class THM_UI_PAGE_SETTINGS, attribute LEFTPRINTMARGIN, expected double, got float
QA046 | Dynamic power spectra |  |  |  | Jim M | The dynamic power spectra produced from thb_peif_flux and thb_peif_t3 (with default settings) do not cover the entire time range of the data. Example plot attached.
QA013 | legend options | 2013-03-06 | Eric |  |  | Frame caption and variable names frames not shown, “Variables” label in bottom frame cut off on left, “Apply to All” and “Save to Template” text cut off (buttons too small). Linux specific?
QA030 | Performance issue, draw window | 2013-03-08 | Aaron |  |  | When I load an unusual amount of data (in this case all ESA, all probes, one day) the performance of the GUI is understandably slowed. Every time I move the cursor from the draw area to the rest of the GUI I get a short delay. If the cursor is quickly moved outside the GUI then the delay does not occur until the cursor re-enters the draw area. If I do this quickly enough that the tracking crosshairs remain on the current panel (quick enough that no other position events are generated) and then move the cursor back to that panel before the hourglass disappears it will create a marker from the cursor's original position to its new position.
QA039 | Interpolate, tests 6 and 7 | 2013-03-11 | Cindy |  |  | Interpolating to a shorter time frame seems to do nothing. The data is not shortened or changed although a new variable is created with the correct suffix. Longer time range also does not extend the data set. Here’s where I’m confused - the instructions claim the result will have the same time range. If my range doesn’t extend what then is the point of interpolating? I asked Aaron if this was the intended functionality for this panel and he did not think so.
QA056 | Memory leak when switching pages? (idl 8.2.2) | 2013-03-15 | Nick |  |  | Happens in IDL 7.1, not 7.0.6. Not obvious where the leak is. One test that I did is having just two pages, one with three panels and another one completely empty. When I change pages (Pages -> Page:1, Page:2) every time I go to the page with the panels the memory usage goes up about 50MB! If I go to the empty page, I also get an increase, but much Smaller.
QA019 | Calculate: adding variables vs. functions and operators | 2013-03-08 | Aaron |  |  | Variables are added to the current program with the add key, however functions and operators are still added upon selection. It would be useful and more consistent to have them behave the same as variables; either with a separate "add" button or with the current button if we can reliably determine which widget was last in focus. If using the current button a label could be added at the bottom to display the current selection.
QA032 | thm_load_fit, different # elements in X and Y components | 2013-03-08 | Aaron |  |  | While loading FIT data I received errors that the following quantities could not be imported for probes A, D, & E (2013-03-05) because their X & Y components contained different numbers of elements: th?_fgs_sigma, th?_efs_sigma, th?_efs_0_dsl, th?_efs_dot0_dsl
QA021 | Legend options – enable tabbing | 2013-03-08 | Aaron |  |  | It would be convenient to have tabbing enabled (should be single keyword to top level base). Also, add status bar and slightly enlarge panel.
QA036 | Legend options, units in dropdown menus | 2013-03-11 | Aaron |  |  | Do we need different units settings for each spinner, or should we just have one units setting that applies to all. Same issue with Panel Options.
QA061 | Legend options – trace dropdown | 2013-03-21 | Eric |  |  | When the user changes panels, the traces drop-down should be populated with the traces from the selected panel. This doesn't appear to be working on Windows/IDL 7.0.6 (or Linux/IDL 7.1).
QA062 | Panel options -- “Relative Vertical Size” not sensitized | 2013-03-22 | Eric |  |  | Remove control until functionality is implemented.
QA058 | ERG updates | 2013-03-19 | Jim L |  | Cindy | Do we need to re-apply modifications that we made to their last version of the plugin? What has changed since last time?
QA059 | IUGONET updates | 2013-03-19 | Jim L |  | Cindy | Do we need to re-apply modifications that we made to their last version of the plugin? What has changed since last time?
QA060 | rename terms_of_use.pro | 2013-03-21 | Jim L |  |  | should have “spedas” prefix and be in a separate directory. Can it be extended to handle the multiple acknowledgements that IUGONET needs?
QA069 | Axis options – apply all | 2013-03-25 | Cindy |  |  | Test 48. The 'Apply to all' panels button on the title tab did not function properly. I believe we do not apply the 'apply all' to text items (like titles/labels). The message in the status bar is confusing because it says it changed, but nothing happened. Maybe the 'apply all' button in the title tab could be grayed out?
QA071 | Z axis options “save to template” | 2013-03-25 | Jim M |  |  | Z-axis opitons failed for me. QA014 is fixed. But the 'save to template' button on the Z-axis options panel (step 25) does not work for me. It says that a template is saved, but does not prompt for a filename or save a file. If i save and relaod a template using the template opiton under the file pulldown button, then everything works. Linux, IDL 7.1
QA043 | ESA extended (axis options) |  |  |  |  | Y-axis range and scaling options are copied to other panels after selecting "Apply to all Panels" despite none of the Range tab options being touched. If the current page's panels have different range and scaling options this makes the "apply to all" option largely unusable.
QA073 | GUI Overview plots | 2013-03-25 | Nick |  |  | When panels are unlocked, all panels disappear and “no room for panels” error messages is displayed. Can anything be done?
QA079 | Timestamps on history and statusbar messages | 2013-03-26 | Nick |  |  | update methods should prepend a data/timestamp
QA087 | Data processing – interpolate window | 2013-03-25 | Eric |  |  | 'Quadradic' should be 'Quadratic'
QA076 | Markers unintentionally created in some situations | 2013-03-26 | Aaron |  |  | control/shift flags in info structure get “stuck” sometimes. Making data processing window modal might help. Aaron knows how to reproduce.
QA084 | calculate, add button tooltip and label not cleared | 2013-03-26 | Eric |  | Eric | if you click the function/operator/constants list and then click the 'insert variables' tree (but don't select a variable), the 'add' button tooltip and label aren't cleared. This creates a situation where the label and 'add' button tooltip both say 'Insert function: [function name]' but clicking the add button doesn't work
QA104 | thm_crib_calc | 2013-04-01 | Cindy |  |  | ** Structure <4781038>, 3 tags, length=36, data length=36, refs=1: TYPE STRING 'error' NAME STRING 'Globbing variable with no match' VALUE STRING '"?%3"' "?%3" % Stop encountered: $MAIN$ 116 C:\Users\clrussell\Desktop\tdas8-2\tdas_8_00\idl\themis\examples\thm_crib_calc.pro
QA105 | thm_crib_calc | 2013-04-01 | Cindy |  |  | STRING_GLOB_PREPROCESS(188): Warning: globbing used in operand variable when output variable is not a globbable STRING_GLOB_PREPROCESS(195): Error: globbing variable has no match: "?%3" % Stop encountered: $MAIN$ 123 C:\Users\clrussell\Desktop\tdas8-2\tdas_8_00\idl\themis\examples\thm_crib_calc.pro
QA035 | Suggestion, closing pages | 2013-03-11 | Nick |  |  | Prompt does not appear on Linux when using ctrl-Z to close last window, due to accelerator keys being handled in their own bit of code. Easy fix: duplicate code in other event handler. Possible to do a cleaner fix to avoid duplicating code?
QA094 | variable options format option | 2013-03-28 | Aaron |  |  | (minor/not OS specific) The "Format" option in the Variable Options window would be more correctly labeled "Precision".
QA066 | Axis options – align ticks | 2013-03-25 | Cindy |  |  | Error message for invalid entry disappears too quickly (overwritten by “changes applied” message) Remove “changes applied” message?
QA076 | Data processing menu | 2013-03-26 | Aaron |  |  | I noticed the right-click-menu item to bring up the data processing window reads "Data Analysis" while the GUI's main menu bar and the window itself read "Data Processing".
QA088 | Possible extrapolate issue | 2013-03-27 | Aaron |  |  | Extrapolate may not be working with the spline option 4/04/2013: Can't reproduce now.
QA096 | currently selected page | 2013-03-28 | Aaron |  |  | (enhancement) It could be useful to list the currently selected page somewhere in the main GUI window, perhaps in the window title bar.
QA092 | status bar reappears if main window resized | 2013-03-28 | Eric |  |  | Deselecting 'Status Bar' on the 'View' window gets rid of the status bar on the main window, as expected. However, if the user changes the size of the window (by clicking a corner and dragging), the status bar comes back...
QA030 | Control & click flags get stuck | 2013-03-08 | Aaron |  |  | I can now consistently reproduce QA30, which turned out not to be performance related. The "ctrl" and "click" flags in the info structure end up getting stuck at 1 in some circumstances. This causes the GUI to interpret mouse movements within a panel as a marker being drawn. Usually those flags are properly reset when the cursor leaves the GUI but for some reason they are not in this case, causing the bug to persist until an actual marker is drawn. a) The "ctrl" flag gets stuck if the first clicks in the data processing window are ctrl-clicks. This could be cleanly fixed by making the window modal. b) (No Repro, win 7/idl 7.0.6) The "click" flag gets stuck if you open the right click menu in the draw area then click and the drag the cursor from within the draw area to outside of it.
QA093 | load data window layout | 2013-03-28 | Aaron |  | Jim L | (minor) The load data window has a lot of empty space at the bottom between the "Done" button and the rest of the widgets. Jim L to verify on Mac 4/04/2013: By design, closing.
QA091 | copy/paste into Word | 2013-03-28 | Eric |  |  | When the user copy+pastes the current window into Word, the legend for each panel is copied with the trace names but without any values. It seems to me that we would want this to just copy the page with no legends.
QA074 | Axis options – grid tab | 2013-03-25 | Pat |  |  | On the grid tab, the "panel outline thickness" setting has appeared. It is a little odd for two reasons. #1 Why isn't it on panel options? #2 It changes the thickness of major ticks, minor ticks, & grids, in addition to panel frame thickness.(Affecting both x axis & y-axis & panel, All at the same time)
QA078 | Overview plots – enable “track one panel” | 2013-03-26 | Pat |  |  | Legends are overlapping and illegible. We used to enable “track one panel” for overview plot pages, but not happening now...needs to be restored.
QA106 | Obsolete error handling in cdf_load_vars.pro | 2013-04-02 | Aaron |  |  | I did notice that the "message" call I was dropped to at the bottom of cdf_load_vars references an obsolete system variable "!err_string". The IDL documentation claims that code using this variable will still work, but they advise against using it. I was unable to run the line in question, although I did first enter several other commands into IDL before attempting to move past it - something I did may have broken the supposed backward compatibility.
QA100 | Blank plots, sst contamination | 2013-04-01 | Aaron |  |  | 1. (not platform dependent) Plots 9 and 10 come out blank. It appears the data exists but the y-axis range does not cover the data's range. Plots 11 and 12 show some data but also appear to have misaligned y-axis ranges. This may actually be an issue with the test suite itself.
QA110 | thm_load_gmag dlimits | 2013-04-03 | Pat |  |  | Should set dlim.data_att.units to 'nT' where applicable
QA097 | enhancement: status bar, history window | 2013-03-28 | Aaron |  |  | A wrapper routine with keywords for updated the status bar or history window or both would cut down on some of the repetition in the error reporting code.
QA067 | Axis options – align ticks | 2013-03-25 | Cindy |  |  | Test 20.c.d If I use an invalid value into the Align Ticks at text box (for ex: 2007/0"ewrt5hd"3/23-00:00:00) The invalid status message is displayed and then before a user could note the error a changes applied message is displayed. This is like the one I reported at standup - the date is changed back to 2007/03/23-00:00:00, however this does more and changes the Major Ticks by Number radio button from 'Major Ticks by Number' to '2007/03/23-00:00:00'. That radio button stays at that until the panel is closed. This situation occurs only when there was an invalid entry in align ticks. This is easily repeatable.
QA103 | thm_crib_eclean_subsolar, thm_crib_cleanefp | 2013-04-01 | Eric, Cindy |  |  | Removing spikes in Ez... % Loop limit expression too large for loop variable type. <LONG ( 55272)>. % Execution halted at: THM_QFIT 229 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\spacecraft\fields\LASP\thm_qfit.pro % THM_LSP_REMOVE_SPINTONE 98 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\spacecraft\fields\LASP\thm_lsp_remove_spintone.pro % THM_EFI_CLEAN_EFP 516 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\spacecraft\fields\LASP\thm_efi_clean_efp.pro
QA107 | thm_crib_esa_slice2d assumes Windows filenames | 2013-04-02 | Jim M |  |  | thm_crib_esa_slice2d also worked, but generates a bunch of png files with names like this: C:THEMIS20080226_045400thbpeib.png It seems to be optimized for Windows, so we might want to change that.
QA102 | thm_crib_gmag.pro | 2013-04-01 | Nick |  |  | Problem when selecting a time interval: % Attempt to subscript RES with <INT ( 1)> is out of range.
QA077 | Save to template confusing | 2013-03-26 | Jim M |  |  | Rename button or provide tooltip to explain what it does?
QA083 | Calculate, spurious newline added | 2013-03-26 | Eric |  | Pat | if you add something and close and then reopen calculate it adds a newline to the beginning of the program. Only happens once (so if you do it multiple times, there aren't multiple newlines added)
QA085 | calculate enhancements | 2013-03-26 | Eric |  | Pat | Add 'Clear' button for program -- Add constant 'Re' for earth radius
QA086 | calculate event handler | 2013-03-26 | Eric |  | Pat | Edit event handler so that double click on insert function or operator listbox adds the selection to the program
QA089 | Page options layout tab | 2013-03-27 | Pat |  | Pat | For some reason the default left margin is displaying as: 1.649999976158 Not a huge deal, but it should probably default to 1.65 (platform specific?)
QA115 | possible click events bug | 2013-04-03 | Aaron |  |  | I noticed some odd behavior in the GUI over the last day or two. Every now and then I seem to be getting "stuck" in a state where tracking is off and clicks within the draw area are not registered. I don't know how to consistently reproduce it yet, but I haven't seen this particular behavior before so I'm guessing it's related to a recent change.
QA113 | Use statusbar/history wrapper in axis options code | 2013-04-03 | Aaron |  |  | Replace simple usages that are likely to be exercised in regression testing, save more complex or hard-to-reach cases for later.
QA112 | layout panel “row span” field not updated properly | 2013-04-03 | Pat |  |  | If I create an overview plot, then open the layout panel, select panel 14(the last panel) then select delete until only panel 1 remains, I notice a few things. #1 Each time that I delete, it says that the row span=row of the panel. (This is wrong) #2 When I reach the last remaining panel(panel 1) it says the row is 1 and the row span 1. If I try to reduce the rows per page, it will only let me reduce the rows per page to 4. (Because the row span is actually 4 not 1) #3 If I close & reopen the layout panel, it correctly lists the row span as 4
QA068 | Axis options – overlapping labels | 2013-03-25 | Cindy |  |  | Test 47(abc) In the title tab when going from bottom to top in the second panel the labels overlap. This always happen with the lower panels however initially it does happen not the top panel. You can play around long enough you can get titles to overlap. This issue only occurs when the horizontal button is selected.
QA078 | Data processing, cotrans | 2013-03-26 | Aaron |  |  | When the window automatically loads state data for a coordinate transformation it leaves behind the spin_ras and spin_dec variables but no others. I don't think this is necessarily an issue rather thought it was strange as I would expect either all or no variables to be left behind.
QA063 | “Last change to all panels” | 2013-03-22 | Aaron |  |  | On hold until we figure out a minimal fix for this release Replace “Apply to all panels” in Axis Options
QA065 | omni load routine | 2013-03-25 | Eric |  |  | Needs time clipping – if you select a single day, the entire month gets loaded.
QA101 | thm_crib_dproc.pro, wavelet error | 2013-04-01 | Eric |  |  | There seems to be a problem with plotting the spectrograms of the wavelet transforms in thm_crib_dproc.pro. I get the following error at line 139: "TPLOT(222): No valid variable names found to tplot! (use TPLOT_NAMES to display)" and then it crashes on the next step when I try to continue: % Variable is undefined: INPUTUNITS. % Execution halted at: TDPWRSPC 133 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\ssl_general\misc\tdpwrspc.pro % THM_UI_PWRSPC 47 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\thm_ui\thm_ui_pwrspc.pro % $MAIN$ 145 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\examples\thm_crib_dproc.pro
QA080 | Manage data, renaming variable into different branch of data tree | 2013-03-26 | Aaron |  |  | (Manage Data) If I edit a variable (two in this case) that is in one branch of the data tree such that it falls into another already existing branch then only the changed variables will be shown in that node. The original variables show up again when the window is restarted.
QA075 | Y axis options, IDL formatting codes | 2013-03-25 | Pat |  |  | We support IDL formatting codes in our labels now. But there is no way for users to know that. We should probably have a help or examples button that briefly shows how to use it. #3 IDL formatting codes largely make the "symbol" and "monospace symbol" fonts useless. (Well more useless, they were already pretty useless....) We should probably take them out.
QA098 | sst_contamination_test failed on solaris | 2013-03-29 | Jim M |  |  | Test 8 Failed: electron burst mask/sun ERROR: -225 ERROR: % Expression must be a structure in this context: DAT. ERROR: % Execution halted at: EDIT3DBINS 33 /home/jimm/thmsoc_sw/idl/ss l_general/science/edit3dbins.pro ERROR: % THM_SST_CONTAMINATION_TEST 223 /home/jimm/thmsoc _sw/QA_testing/thm_sst_contamination_test.pro ERROR: % $MAIN$
QA049 | Slice2d – displaced cuts, geometric mode | 2013-03-13 | Aaron |  |  | Doesn't appear to be a bug. Displaced cuts using geometric mode often have bin boundaries that do not look possible. The plots generally match the those done with 3D interpolation so my guess is that there's a small mathematical error in the algorithm used to determine bin extent that only shows up when the slice plane does not intersect the origin.
QA077 | Smoothing with no time interpolation | 2013-03-26 | Aaron |  |  | The No Time Interpolation option for the smoothing function is very slow and will sometimes cause IDL to become non-responsive (e.g. a 28,000 sample vector takes ~2-3 minutes; for a 175,000 sample vector IDL will still be non-responsive after 30 minutes). If this is a useful feature to have the GUI we may want to add a more specific warning, perhaps even a pop-up.
QA079 | Data processing, block average | 2013-03-26 | Aaron |  |  | The Limit Time Range option in the Block Average options does not appear to do anything. Also, once implemented we should add a tooltip to the checkbox to specify whether it clips the variable or only applies an average over the specified interval (I'm guessing the latter is the intended behavior).
QA046 | Dynamic power spectra |  |  |  | Jim M | The dynamic power spectra produced from thb_peif_flux and thb_peif_t3 (with default settings) do not cover the entire time range of the data. Example plot attached. Still some problems: Double checking QA046 and I think there might be something that isn't working right. If I use tha_peif_flux data from 2007-03-23. There aren't enough data points with the default window/shift options, so I just get one point for the day. If I reduce to a window of 32 points and a shift of 32 points, I get the first attached plot which is strange, but maybe not wrong? if I use a window of 256 points and a shift of 32 points, I get a result that is definitely wrong. The second attached plot. (Dates in 1970 should not be happening. When the widget tree lists the start and stop times for the data in layout options it lists "2007-03-23/08:08:22 to 1970-01-01/00:00:00")
QA095 | loaded data tree in data processing | 2013-03-28 | Aaron |  | Jim L | Verified on Mac and Linux. The loaded data tree in the Data Processing window is very small (each side is maybe 60% the size of the corresponding side of the Active Data list).
QA057 | file_http_copy suggestions | 2013-03-19 | Jim L |  |  | Issues with RBSP data server – they have suggested modifications to file_http_copy, should we implement?
QA099 | weird colors, thm_crib_tplot_layout | 2013-04-01 | Eric |  |  | No repro on Windows from fresh IDL session? I made it through 'thm_crib_tplot_layout' with only one minor issue: the procedure to set the color scheme (init_crib_colors) doesn't seem to be working correctly on my machine (IDL 7.0.6/Win 7). All of the figures created by the tplot layout crib have a red background with line colors that appear to be different shades of black/grey.
QA108 | draw_color_scale zrange annotations for log scaling | 2013-04-02 | Christine G |  |  | Closing, would be hard to fix and a good workaround already exists. For small ranges only 1 annotation is shown – should display min and max values for this case.
QA117 | GUI cotrans infinite loop | 2013-04-10 | Pat |  |  | Trying to overwrite a variable using a cotrans produced an infinite loop of "warning would you link to overwrite errors" I'm guessing it was caused by modal settings on the warning being changed. The warning popup needs to be modal. The basic process was tha_state_pos->tha_state_pos_sse->tha_state_pos_sm->tha_state_pos_sse, I think. But I was just clicking stuff, trying to reproduce. QA081/QA02
QA081 | Data processing, cotrans | 2013-03-26 | Aaron |  |  | I received an "unexpected error" when trying to transform a variable with modified state data from GEI or DSL to SPG (did not test other starting coords). The console output is below. I'm not sure if it was related but it also appears that one of the underlying cotrans routines may be expecting to get the probe designation from the variable's name; which is probably a bad idea. SPG2SSL(54): spacecraft has to be a, b, c, d or e (third letter of the input name) SPG2SSL(70): SSL-->SPG SPG2SSL(112): number of DATA records: 1440 Traceback Report from THM_UI_COTRANS_NEW: $MAIN$ THM_UI_DPROC_PANEL_EVENT <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_dproc_panel.pro( 146)> THM_UI_COTRANS_NEW <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_cotrans_new.pro( 353)> ERROR_MESSAGE <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\utilities\error_message.pro( 256)> Last IDL Error: % TRANSPOSE: Expression must be an array in this context: RM. % Execution halted at: SPG2SSL 119 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\ssl_general\cotrans\spg2ssl.pro STORE_DATA(106): Deleted 3 variables
QA121 | Users Guide – Eric | 2013-04-10 |  |  | Eric | Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA122 | Users Guide – Jim L | 2013-04-10 |  |  | Jim L | Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA116 | “Open Help” brings up web interface guide, should be user's guide | 2013-04-09 | Eric
QA111 | thm_map_add | 2013-04-03 | Pat |  |  | thm_map_add.sav file not found for non-SSL users, doesn't use file_retrieve to copy it into local_data_dir Add sav file to some TDAS directory, modify thm_map_add to restore from there rather than the data directory.
QA118 | file_mkdir2 error handling, if a file already exists at the specified path | 2013-04-10 | Pat |  |  | Execution halts, rather than passing the error status back to the caller. Should be handled similarly to write permission error, which is already handled correctly.
QA124 | Users Guide – Nick | 2013-04-10 |  |  | Nick | Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA114 | Move thm_fgm_fit_correlate_tplot.pro and other non-crib/utiilty code out of examples directory | 2013-04-03 | Pat |  |  | Also whatindices.pro & whatindex.pro are support routines that are used by recover_Vxz_mom_early_2007_crib.pro. They should be moved(maybe into the crib?)
QA120 | Users Guide – Cindy | 2013-04-10 |  |  | Cindy | Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA126 | Error handling, obsolete fonts | 2013-04-12 | Aaron |  | Nick | When I load the attached .tgd file I receive an expected error (expected because the files uses a font we no longer support). The error is caught and the rest of the window not drawn. However, as soon as an options window (e.g. load data) is opened and closed I get dropped into the font object code. In addition to ensuring that such errors are caught correctly we may want to put a check into the font code to keep the error from happening in the first place. The now-unsupported fonts are symbol and monospace symbol so I'm not sure if many users would actually run into this, but it would be a simple way to maintain backwards compatibility just in case. Lastly, the error message that popped up when I loaded the file was not very user friendly ("THM_UI_OPEN--> Attempt to subscript FONTS with INEDEX"). This might be fixed once better error handling is in place, but if not we should see if something more useful could be output.
QA070 | Y axis options – poor default tick locations | 2013-03-25 | Pat |  |  | I think we've got some regression going on with the automatic tick selection in the y-axis. It is selecting pretty bad default tick locations.(for log axes) For example, when I plot tha_peif_en_eflux, I get sticks at 10^1.3, 10^1.95,10^2.60, 10^3.25,10^3.90
QA123 | Users Guide – Jim M | 2013-04-10 |  |  | Jim M | Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA072 | GUI Overview plots | 2013-03-25 | Nick |  |  | Can anything be done about the overlapping labels and legends? Shorten labels to make them more like the online summary plots.
QA128 | Axis options control labels | 2013-04-16 | Pat |  |  | The "format help" button should probably appear on the title tab. Right now it is only on the labels tab. Also, in the UI the section controlling style & placement is labeled "Placement:" on the titles tab and "Style:" on the labels tab. Both sections have basically the same set of options. I would recommend the same name for both. Since there is plenty of space in the layout, "Style & Placement:" seems a good choice. Or just "Placement:"
QA129 | Remove “Disable status bar” control | 2013-04-16 | Pat |  |  | There is an option to disable the status bar. I'm not really sure why it is there at all. I could imagine that you might want to disable it to save a little space on screen. Unfortunately, when you disable it, there is just a blank space where the bar used to be.(At least on linux) And if you resize, the blank space stays. So it doesn't save you screen space.
QA130 | Error with mission selection dropdown in GUI configuration options | 2013-04-17 | Aaron |  | Jim L | state structure is not initialized?
QA064 | CL test for file_http_copy | 2013-03-22 | Pat |  |  | Should exercise globbing, conflicts with preexisting files or directories, missing permissions, “Load Highest Version” functionality using THEMIS, SPDF, RBSPICE, mirror sites, plus tests of more basic functionality
QA132 | Axis Options min/max fields | 2013-04-17 | Aaron |  |  | In axis options if Fixed Min/Max is not selected then the fixed min & max fields are updated to reflect the automatically chosen range when the window is opened. However, they are not updated when range options that affect the automatic range are applied(e.g. log scaling, margin). I'm not sure if they ever were updated on apply, but we should double check in case this is a regression.
QA131 | Axis Options/Apply to All tooltip | 2013-04-17 | Aaron |  |  | The Apply to All button in axis options needs its tooltip updated to reflect the current behavior.
QA133 | file_http_copy, th[ade] style wildcards don't work | 2013-04-18 | Aaron |  |  | RBSPICE fix caused a regression
QA134 | Combine 2 popups when loading themis document |  |  |  |  | I think we should consider replacing the two pop-ups used when loading TGD files with a single pop-up. Right now the first question asks if the currently loaded data should be kept or deleted and the second reminds the user that all pages will be replaced and gives them an option to cancel. The functionality of both could be contained in a single Yes/No/Cancel pop-up containing the same warning and choice (e.g. "yes" to delete data, "no" to retain it, and "cancel" to not load a document). I'm guessing this is simple enough to implement for this release.
QA119 | Users Guide – Aaron | 2013-04-10 |  |  | Aaron | Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA125 | Users Guide – Pat | 2013-04-10 |  |  | Pat | Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA136 | Error importing tplot variables | 2013-04-19 | Aaron |  |  | I get a error when importing multiple tplot variables whose names match existing GUI variables. After clicking "Yes to All" on the prompt to overwrite the current data I get an error message that reads "THM_UI_VERIFY_DATA--> Error retrieving data for". After selecting OK the Verify Data window comes up as usual only with a blank entry at the top. When I select OK again the window crashes and brings up the help request form.
QA007 | Failures in thm_spdf_cltestsuite | 2013-03-01 | Eric |  |  | Waiting on SPDF to fix spin_cal files ;Test 3 Failed: SPDF/SPDF L1/L2 comparsion ;ERROR: -5 ;ERROR: % $MAIN$: SPDF L1/SPDF L2 Fail ;ERROR: % Execution halted at: $MAIN$ 103 C:\Users\egrimes\Desktop\Space\thmsoc\trunk\QA_testing\thm_spdf_cltestsuite.pro ;Test 4 Failed: THEMIS/THEMIS L1/L2 comparsion ;ERROR: -5 ;ERROR: % $MAIN$: THEMIS L1/THEMIS L2 Fail ;ERROR: % Execution halted at: $MAIN$ 122 C:\Users\egrimes\Desktop\Space\thmsoc\trunk\QA_testing\thm_spdf_cltestsuite.pro
QA138 | Missing routines, ssw/fits | 2013-04-23 |  |  | Jim M | Missing get_pipe_filesize, hprint, repchr routines
QA140 | Missing routine, SCM | 2013-04-23 |  |  | Jim M | temp_scw_degap, used in thm_cal_scm.pro
QA144 | Misplaced definition, thm_scm_modpha | 2013-04-23 |  |  | Jim M
QA143 | Missing routine, EFI | 2013-04-23 |  |  | Jim M | notch_filter, used in thm_efi_despin.pro
QA139 | Missing routine, dprint | 2013-04-23 |  |  | Jim L | dprinttool, used in dprint.pro
QA141 | Missing routine, SST | 2013-04-23 |  |  | Pat | sst_calib_params_com, used in thm_sst_energy_cal.pro
QA146 | Slight difference in FGM L1 calibrated vs. L2 data | 2013-04-23 | Nick |  | Jim M | Maybe a time_clip issue, some other difference between TDAS L1 calibration and thmsoc L1->L2 processing?
QA135 | Create virtual machine .sav file from tdas zip file | 2013-04-19 |  |  |  | Use current zip file for dry run, will repeat with final zip file.
QA142 | Misplaced definition, function_list | 2013-04-23 |  |  | Eric | Compile before building VM .sav file Defined in mini_routines.pro, used in mini-predicates.pro, calc,pro. Also, function_list is used as a keyword argument.
QA145 | Misplaced definition, aacgm_load_coef | 2013-04-23 |  |  |  | ERG plugin, defined in aacgmloadcoef.pro (no underscores). DLL/DLM needed, or is IDL definition sufficient?
Compat001 | Name conflict: thm_ui_new/utilities/color_bar__define.pro |  | Lydia/Dan Weimer |  |  | Object with same name exists in IDL 8.0+
Compat002 | Name conflict: ssl_general/misc/getcolor.pro |  | Lydia/Dan Weimer |  |  | Two IDL demo programs define their own getcolor routine.
QA004 | IDL 8.1 dprint formatting different, routine name and line number no longer on same output line as message. | 2012-01-18 | Aaron |  |  | Fixed by Davin's update to dprint?

## QA v8.0 Suites and Scripts
Task # | Task Description | Initial Status | Retest#1 | Retest#2 | Retest#3 | IDL version | Operating System | Assignment | Notes
Command-Line Test Scripts
| fac_testscript.pro | Pass |  |  |  | 7.0.6 | Windows XP | Aaron
| kyoto_load_testsuite.pro | Pass |  |  |  | 7.0.6 | Windows XP | Aaron
| mva_testscript.pro | Pass |  |  |  | 7.0.6 | Windows XP | Aaron
| rot_testscript.pro | Pass |  |  |  | 7.0.6 | Windows XP | Aaron
| slp_test.pro | Not for TDAS | [5 empty] | Aaron
| test_cotrans.pro | Pass |  |  |  | 7.0.6 | Windows 7 | Aaron
| thm_ascii_cltestsuite.pro | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy
| thm_asi_load_cltestsuite.pro | Pass |  |  |  | 7.0.6 | Windows XP | Aaron | 3 tests ran out of memory, retest on different machine? Passes on different machine with 16 Gb RAM (Win 7, IDL 7.1)
| thm_ask_load_cltestsuite.pro | Pass |  |  |  | 7.0.6 | Windows XP | Aaron
| thm_calc_testsuite.pro | Pass |  |  |  | 7.0.6 | Windows XP | Aaron
| thm_cotrans_all_combos.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick | Very slow. Retest with different environment?
| thm_cotrans_cltestsuite.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_cotrans_test.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_dproc_cltestsuite.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_dproc_fbk_testsuite.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_efi_cal_cltestsuite.pro | Pass |  |  | Pass | 8.22 | Windows 7 | Aaron
| thm_efi_cotrans_template.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick | Very slow on 8.2.2, OK under 8.1 and 7.1.0
| thm_efi_load_cltestsuite.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_esa_cal_cltestsuite.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_esa_cotrans_cltestsuite.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_esa_load_cltestsuite.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_fac_testscript.pro | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy
| thm_fbk_cal_cltestsuite.pro | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy
| thm_fbk_load_cltestsuite.pro | Failed | Pass |  |  | 7.0.6 | Windows 7 | Cindy | Test 19, valid names (error in fresh session, no error if test repeated?) see qa002
| thm_fft_cal_testsuite.pro | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy
| thm_fft_load_cltestsuite.pro | Failed | Pass |  |  | 7.0.6 | Windows 7 | Cindy | Test 17, valid names (error in fresh session, no error if test repeated?) see qa001
| thm_fgm_cal_cltestsuite.pro | Pass |  |  | Pass | 7.0.6 | Windows 7 | Aaron
| thm_fgm_cotrans_template.pro | Open | [5 empty] | Jim L | Obsolete, removed from SVN
| thm_fgm_cotrans_testsuite.pro | Pass |  |  |  | 6.4 | Linux | Jim L | No SVN reference plots
| thm_fgm_load_cltestsuite.pro | Pass |  |  |  | 6.4 | Linux | Jim L | No SVN reference plots
| thm_fit_cal_cltestsuite.pro | Failed | Pass |  |  | 6.4 | Linux | Jim L | See qa006 All tests failed with similar error: ;Test 0 Failed: thm_cal_fit,probe='a',datatype='efs' ;ERROR: -163 ;ERROR: % Subscript range values of the form low:high must be >= 0, < size, with low ;ERROR: <= high: <No name>. ;ERROR: % Execution halted at: THM_CAL_FIT 455 /home/jwl/tdas_8_00/idl/themis/spacecraft/fields/thm_cal_fit.pro ;ERROR: % $MAIN$ 42 /home/jwl/tdas_8_00/QA_testing/thm_fit_cal_cltestsuite.pro
| thm_fit_cal_template.pro | Failed | Pass |  |  | 6.4 | Linux | Jim L | Obsolete. See qa005 THM_CAL_FIT(334): No good fit codes, assuming that E12 is used for EFS % Variable is undefined: NE34. % Execution halted at: THM_CAL_FIT 355 /home/jwl/tdas_8_00/idl/themis/spacecraft/fields/thm_cal_fit.pro % $MAIN$ 51 /home/jwl/tdas_8_00/QA_testing/thm_fit_cal_template.pro
| thm_fit_cotrans_cltestsuite.pro | Failed | Pass |  |  | 6.4 | Linux | Jim L | See qa005 THM_CAL_FIT(334): No good fit codes, assuming that E12 is used for EFS % Variable is undefined: NE34. % Execution halted at: THM_CAL_FIT 355 /home/jwl/tdas_8_00/idl/themis/spacecraft/fields/thm_cal_fit.pro % $MAIN$ 51 /home/jwl/tdas_8_00/QA_testing/thm_fit_cal_template.pro
| thm_fit_load_cltestsuite.pro | Pass |  |  |  | 6.4 | Linux | Jim L
| thm_gmag_load_cltestsuite.pro | Failed | Pass | Pass |  | 8.1 | Linux | Jim L | Test 22 failed (test DTU sites)
| thm_lasp_cltestsuite.pro | Pass |  |  |  | 8.1 | Linux | Jim M
| thm_mirror_cltestsuite.pro | Failed |  | Pass | Pass | 8.1 | Linux | Nick | SPDF test failed (URL changes?)
| thm_mom_cal_template.pro | Not for TDAS | [5 empty] | Jim M
| thm_mom_cotrans_cltestsuite.pro | Failed |  |  |  | 8.1 | Linux | Jim M | Script is obsolete, needs total rewrite. (QA010)
| thm_mom_load_cltestsuite.pro | Pass |  |  |  | 8.1 | Linux | Jim M
| thm_mouse_testsuite.pro | Pass |  |  |  | 7.0.6 | Windows XP | Aaron
| thm_neutral_sheet_cltestscript.pro | Pass |  |  |  | 7.0.6 | Windows XP | Aaron | Passes after script editing. No comparison plots?
| thm_overplot_testsuite.pro | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy
| thm_part_getspec_testscript.pro | Pass |  |  |  | 6.4 | Linux | Jim L | Switching to another virtual desktop results in corrupted PNGs (plot windows are iconified), retest worked when staying on same desktop.
| thm_part_moments_cltestsuite.pro | Pass |  |  |  | 8.1 | Linux | Jim M
| thm_plot_options_testsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric | No SVN reference plots
| thm_plotxy_testsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric | No SVN reference plots
| thm_plotxyz_testsuite.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_scm_cal_cltestsuite.pro | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_scm_cotrans_cltestsuite.pro | Pass |  |  |  | 7.0.6 | Windows XP | Aaron
| thm_scm_dproc_cltestsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric
| thm_scm_load_cltestsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric
| thm_slice2d_cltestsuite.pro | Failed | Pass |  |  | 7.1 | Windows 7 | Eric | See qa003, qa004 Blank plots for tests 1-10, test 11 failed (multiple distributions) ESA worked, SST failed
Obsolete | thm_spdf_cltestsuite.pro | Failed |  |  |  | 7.1 | Windows 7 | Eric | See qa007 Tests 3 (SPDF L1/SPDF L2) and 4 (THEMIS L1/THEMIS L2) failed
| thm_specplot_cltestsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric
| thm_sst_contamination_test.pro | Pass |  | Pass |  | 7.1 | Windows 7 | Jim L | plots differed, but look reasonable, SVN reference plots out of date?
| thm_sst_load_cltestsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric
| thm_state_load_cltestsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric | Test 14 commented out?
| thm_tplotxy_testsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric
| thm_trg_load_cltestsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric
| thm_tsy_cltestsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric
| thm_ttrace_cltestsuite.pro | Pass |  |  |  | 7.1 | Windows 7 | Eric
GUI Test Suites
| gui_tplot | Pass |  |  |  | 7.0.6 | Windows XP | Aaron | Rename script or update spreadsheet?
| nudge | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy
| Data Processing | Failed | Some issues | Pass |  | 8.22,7.06 | Linux, Win XP | Aaron | QA028 (load sun/moon data failed when replaying themis document)
| layout options | Minor issue | [5 empty] | Eric | QA027 (overflowing labels)
| line options | Pass |  |  |  | 6.4 | Linux | Jim L
| Axis Options (X axis only) | Pass | Some issues | Pass |  | 7.1 | Linux | Nick | QA015 (equal X Y axis scaling never sensitized)
| Axis Options (Y axis only) | Pass | Some issues | Issues | Pass | 7.1 | Windows 7 | Nick | QA127 - “apply” affects multiple panels
| markers | Pass |  |  |  | 7.0.6 | Windows XP | Aaron | QA016 – unreachable menu item for markers, QA024
| panel Options | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy
| rubberband | Pass |  |  |  | 8.22 | Windows 7 | Nick
| variable options | Pass |  |  |  | 7.1 | Linux | Eric
| legend options | Failed | Pass |  |  | 7.1,6.4 | Linux,Linux | Jim L | QA013: there seems to be some issues with the frames on the right hand side of the window. (platform dependent?) Also QA021, QA022, QA023
| Calculate | Some issues | Pass | Pass | Pass |  |  | Eric (VM version) | QA017, QA018, QA019, QA020
| part getspec | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy
| save data as | Pass |  |  |  | 8.22 | Windows 7 | Nick
| Export to Image | Pass |  |  |  | 7.1 | Linux | Eric
| Save Open | Pass |  |  |  | 6.4 | Linux | Jim L
| page options | Pass |  |  |  | 8.22 | Windows 7 | Nick
| z axis | Pass |  |  |  | 7.1 | Linux | Jim M | QA014 – 'Major ticks' sensitized when no panels added yet
| load themis data | Failed | Pass |  |  | 7.0.6,8.22 | Windows XP, Win 7 | Nick | Issues loading fit (QA032) and mom (QA033)
| pulldown menus | Pass |  | Minor issue | Pass | 6.4 | Linux | Jim L | QA129 “Disable status bar” useless
| toolbar | Pass |  |  |  | 8.22 | Windows 7 | Nick
| pages | Pass |  |  |  | 7.1 | Linux | Eric
| ESA Full Suite | Failed | Some issues | Pass | Pass | 7.0.6 | Windows XP | Aaron (VM) | QA043, QA044, QA045, QA046
| FGM Full Suite | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy
| GMAG Full Suite | Pass |  | Pass |  | 8.22 | Linux | Cindy | Minor issue with labels (QA037)
| ASK Reduced Suite | Pass |  |  |  | 8.22 | Windows 7 | Nick
| SST Reduced Suite | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy
| SCM Reduced Suite | Pass | [5 empty] | Nick
| FIT Reduced Suite | Pass |  |  |  | 7.1 | Linux | Eric
| MOM Reduced Suite | Failed | Pass |  |  | 7.1 | Linux | Eric | Excessive memory usage (QA038)
| EFI Reduced Suite | Pass |  |  |  | 7.1 | Linux | Eric
| FFT Reduced Suite | Pass | [5 empty] | Nick
| STATE Reduced Suite | Pass |  |  |  | 7.1 | Linux | Eric
| Slices Suite | Minor issues | [5 empty] | Aaron | QA047-QA053
| thm_ui_journal_history_help | Pass |  |  |  | 7.0.6 | Windows 7 | Cindy | No error message for invalid filename characters, but it was clear that the file was not created. Update instructions? Confirmed platform dependent, works on Linux.
| thm_ui_interpolate | Failed | extrapolate splines | Pass |  |  |  | Nick (IDL 8.2.2) | QA039, QA040
| thm_ui_dproc_power_spectra | Failed | Pass |  |  | 8.22,7.1 | Windows 7, Win 7 | Eric | QA041
| thm_ui_overview_plots | Failed | Pass |  |  | 8.22 | Windows 7 | Nick | QA025 – crash in calendar widget, QA029 – error reoccurred replaying themis document
| thm_ui_graphic_rendering | Pass |  |  |  | 8.22 | Windows 7 | Nick
| thm_ui_horizontal_bar | Pass |  |  |  | 7.1 | Linux | Eric
| thm_ui_error_message.txt | Pass | [5 empty] | Jim L
| thm_ui_fileconfig.txt | Pass | [5 empty] | Jim L
| thm_ui_load_cdf_ascii.txt | Pass | [5 empty] | Cindy
| thm_ui_tplot_manage_data.txt | Failed | Pass |  | Pass |  |  | Nick | QA136, problem importing multiple variables if they already exist in GUI
Platform Compatibility Tests
| GUI rubberband (Mac) | Pass | [5 empty] | Aaron
| GUI rubberband (Solaris) | Pass | [5 empty] | Jim M
| GUI thm_ui_interpolate (IDL 7.1) | Memory usage > 5 GB, fails | [5 empty] | Eric
| GUI thm_ui_interpolate (IDL 7.0.6) | Pass | [5 empty] | Eric
| GUI Pulldown menus (Windows) | A few minor issues | [5 empty] | Pat
| GUI Pulldown menus (Mac) | Pass | [5 empty] | Cindy
| GUI Pulldown menus (Solaris) | Pass | [5 empty] | Jim M
| thm_cotrans_all_combos (IDL 8.1 or below) | Pass | [5 empty] | Pat
| thm_cotrans_all_combos (IDL 8.2.2) | Pass (time?) | [5 empty] | Pat
| thm_fgm cal_cltestsuite (IDL 8.1) | 8 mins | 8 min |  |  |  |  | Nick
| thm_fgm cal_cltestsuite (IDL 8.2.2) | 5+hours | 1 hour |  |  |  |  | Nick
| thm_efi cal_cltestsuite (IDL 8.1) | 16 mins | 22 min |  |  |  |  | Nick
| thm_efi cal_cltestsuite (IDL 8.2.2) | 6 hours | 90 min |  |  |  |  | Nick
| thm_sst_contamination_test (Solaris) | Failed | [5 empty] | Jim L | QA098
| thm_sst_contamination_test (Mac) | Blank plots | [5 empty] | Aaron
| thm_asi_load_cltestsuite (Mac) | Pass (no memory error!) | [5 empty] | Aaron
| thm_asi_load_cltestsuite (Solaris) | Out of memory | [5 empty] | Jim M
Crib sheets/examples
ssl_general/examples:
| thm_crib_tplot_annotation.pro | color map issue | [5 empty] | Jim L
| thm_crib_tplot_export_print.pro | Pass | [5 empty] | Cindy
| thm_crib_tplot_layout.pro | color map issue | [5 empty] | Eric | QA099
| thm_crib_tplot.pro (Windows) |  |  | Pass |  |  |  | Nick
| thm_crib_tplot.pro (Linux) | color map issue |  | Pass |  |  |  | Jim L
| thm_crib_tplot_range.pro | color map issue | [5 empty] | Eric
| time_correlate_crib.pro | Pass | [5 empty] | Nick
themis/examples:
| crib_lshell.pro | Pass | [5 empty] | Aaron
| fac_crib.pro | Pass | [5 empty] | Aaron | after L2 data specified in fgm load calls
| mva_crib.pro | Pass | [5 empty] | Aaron | after L2 data specified in fgm load calls
| recover_Vxz_mom_early2007_crib.pro | Pass | [5 empty] | Aaron
| rxy_crib.pro | Pass | [5 empty] | Aaron | after L2 data specified in fgm load calls
| sse_crib.pro | Pass | [5 empty] | Cindy
| thm_crib_asi.pro | Pass | [5 empty] | Cindy
| thm_crib_calc.pro | Pass | [5 empty] | Cindy
| thm_crib_cleanefp.pro | Failed | [5 empty] | Cindy | QA103
| thm_crib_cleanefw.pro | Pass | [5 empty] | Cindy
| thm_crib_cotrans_lmn.pro | Pass | [5 empty] | Eric
| thm_crib_cotrans.pro | Pass | [5 empty] | Eric
| thm_crib_dproc.pro | wavelet issue |  | Pass |  |  |  | Eric | QA101
| thm_crib_eclean_subsolar.pro | Failed |  | Pass |  |  |  | Aaron | QA103
| thm_crib_efi_cal.pro | Pass | [5 empty] | Eric
| thm_crib_efi.pro | Pass | [5 empty] | Jim L
| thm_crib_esa_bgnd_remove.pro | Pass | [5 empty] | Jim L
| thm_crib_esa_da.pro | Pass | [5 empty] | Jim L
| thm_crib_esa_extrapolation.pro | Pass | [5 empty] | Jim L
| thm_crib_esa_moments.pro | Pass | [5 empty] | Jim L
| thm_crib_esa_read_gmoms.pro | Pass | [5 empty] | Aaron | obsolete error reporting code in cdf_load_vars
| thm_crib_esa_slice2d.pro | Pass | [5 empty] | Eric
| thm_crib_export.pro | Pass | [5 empty] | Nick
| thm_crib_fac.pro | Pass | [5 empty] | Pat
| thm_crib_fbk.pro | Pass | [5 empty] | Eric
| thm_crib_fft.pro | Pass | [5 empty] | Nick
| thm_crib_fgm.pro | Pass (slow on 8.2.2) | [5 empty] | Nick
| thm_crib_fit.pro | Pass | [5 empty] | Nick
| thm_crib_gmag.pro | Failed |  | Pass |  |  |  | Aaron | QA0102
| thm_crib_greenland_gmag.pro | Pass | [5 empty] | Nick
| thm_crib_maccs_gmag.pro | Pass | [5 empty] | Pat
| thm_crib_make_ae.pro | Pass | [5 empty] | Pat
| thm_crib_mom_dead_time_correct.pro | Pass | [5 empty] | Pat
| thm_crib_mom.pro | Pass | [5 empty] | Pat
| thm_crib_mva.pro | Pass | [5 empty] | Pat
| thm_crib_neutral_sheet.pro | Pass | [5 empty] | Eric | neutral sheet models need explicit compilation
| thm_crib_overplot.pro | Pass | [5 empty] | Eric
| thm_crib_part_getspec.pro | Pass | [5 empty] | Eric
| thm_crib_part_slice2d.pro | Pass | [5 empty] | Nick
| thm_crib_plotxy.pro | Pass | [5 empty] | Nick
| thm_crib_plotxyvec.pro | Pass | [5 empty] | Nick
| thm_crib_plotxyz.pro | Pass | [5 empty] | Jim L
| thm_crib_poynting_flux.pro | Pass | [5 empty] | Jim L
| thm_crib_read_write_ascii_cmdline.pro | Pass | [5 empty] | Jim L
| thm_crib_scm.pro | Possible issue? |  | Pass |  |  |  | Jim M | The plot for the diagnostic parameter 'thd_scp_iano' is empty on the second figure produced, not sure if there's supposed to be something there.
| thm_crib_scpot2dens.pro | Pass | [5 empty] | Eric
| thm_crib_slp_sse.pro | Pass | [5 empty] | Eric
| thm_crib_spinfit.pro | Pass | [5 empty] | Nick
| thm_crib_sst_calibration.pro | Pass | [5 empty] | Nick
| thm_crib_sst_contamination.pro | Pass | [5 empty] | Nick
| thm_crib_sst_extrapolation.pro | Pass | [5 empty] | Pat
| thm_crib_sst.pro | Pass | [5 empty] | Nick
| thm_crib_sst_set_calibrations.pro | Pass | [5 empty] | Pat
| thm_crib_state.pro | Pass | [5 empty] | Cindy
| thm_crib_superpo_interpol_histo.pro | Pass | [5 empty] | Cindy
| thm_crib_tplot_overlay.pro | Pass | [5 empty] | Cindy
| thm_crib_tplotxy.pro | Pass | [5 empty] | Eric
| thm_crib_trace.pro | Pass | [5 empty] | Eric
| thm_crib_twavpol.pro | Pass | [5 empty] | Eric
| thm_crib_validate_high_freq_using_phase.pro | Pass | [5 empty] | Pat
| thm_fgm_fit_correlate_tplot.pro | not a crib | [5 empty] | Pat
| thm_map_examples.pro | Obsolete | [5 empty] | Pat | can't find .sav files
| thm_script_fgm.pro | Pass | [5 empty] | Jim L
| twavpol_scm_crib.pro | Pass | [5 empty] | Jim L
Tests for external/contributed code
erg_gmag_mm2120_load_cltestsuite, erg_gmag_nipr_load_cltestsuite

## QA Suites and Scripts Template
Task # | Task Description | Initial Status | IDL version | Operating System | Notes | A | N | C | JL | JM | P | E | Assignment
Platform Availability
Mac Leopard: Jim L, Cindy
Mac Snow Leopard:
Mac Lion: ?(UCLA)
Windows XP: Aaron
Windows 7: Jim M, Nick, Jim L, Eric?
Linux: Pat, Nick, Jim L, Eric?
Unix: Jim M
Command-Line Test Scripts
| fac_testscript.pro | Open |  |  |  | 1
| kyoto_load_testsuite.pro | Open |  |  |  | 1
| mva_testscript.pro | Open |  |  |  | 1
| rot_testscript.pro | Open |  |  |  | 1
| slp_test.pro | Not for TDAS |  |  |  | 1
| test_cotrans.pro | Open |  |  |  | 1
| thm_ascii_cltestsuite.pro | Open |  |  |  | 1
| thm_asi_load_cltestsuite.pro | Open |  |  |  | 1
| thm_ask_load_cltestsuite.pro | Open |  |  |  | 1
| thm_calc_testsuite.pro | Open |  |  |  | 1
| thm_cotrans_all_combos.pro | Open |  |  |  |  | 1
| thm_cotrans_cltestsuite.pro | Open |  |  |  |  | 1
| thm_cotrans_test.pro | Open |  |  |  |  | 1
| thm_dproc_cltestsuite.pro | Open |  |  |  |  | 1
| thm_dproc_fbk_testsuite.pro | Open |  |  |  |  | 1
| thm_efi_cal_cltestsuite.pro | Open |  |  |  |  | 1
| thm_efi_cotrans_template.pro | Open |  |  |  |  | 1
| thm_efi_load_cltestsuite.pro | Open |  |  |  |  | 1
| thm_esa_cal_cltestsuite.pro | Open |  |  |  |  | 1
| thm_esa_cotrans_cltestsuite.pro | Open |  |  |  |  | 1
| thm_esa_load_cltestsuite.pro | Open |  |  |  |  | 1
| thm_fac_testscript.pro | Open | [5 empty] | 1
| thm_fbk_cal_cltestsuite.pro | Open | [5 empty] | 1
| thm_fbk_load_cltestsuite.pro | Open | [5 empty] | 1
| thm_fft_cal_testsuite.pro | Open | [5 empty] | 1
| thm_fft_load_cltestsuite.pro | Open | [5 empty] | 1
| thm_fgm_cal_cltestsuite.pro | Open | [5 empty] | 1
| thm_fgm_cotrans_testsuite.pro | Open | [6 empty] | 1
| thm_fgm_load_cltestsuite.pro | Open | [6 empty] | 1
| thm_fit_cal_cltestsuite.pro | Open | [6 empty] | 1
| thm_fit_cal_template.pro | Obsolete | [6 empty] | 1
| thm_fit_cotrans_cltestsuite.pro | Open | [6 empty] | 1
| thm_fit_load_cltestsuite.pro | Open | [6 empty] | 1
| thm_gmag_load_cltestsuite.pro | Open | [7 empty] | 1
| thm_lasp_cltestsuite.pro | Open | [7 empty] | 1
| thm_mirror_cltestsuite.pro | Open | [7 empty] | 1
| thm_mom_cal_template.pro | Not for TDAS | [7 empty] | 1
| thm_mom_cotrans_cltestsuite.pro | Obsolete | [7 empty] | 1
| thm_mom_load_cltestsuite.pro | Open | [7 empty] | 1
| thm_mouse_testsuite.pro | Open | [8 empty] | 1
| thm_neutral_sheet_cltestscript.pro | Open | [8 empty] | 1
| thm_overplot_testsuite.pro | Open | [8 empty] | 1
| thm_part_getspec_testscript.pro | Open | [8 empty] | 1
| thm_part_moments_cltestsuite.pro | Open | [8 empty] | 1
| thm_plot_options_testsuite.pro | Open | [8 empty] | 1
| thm_plotxy_testsuite.pro | Open | [8 empty] | 1
| thm_plotxyz_testsuite.pro | Open | [8 empty] | 1
| thm_scm_cal_cltestsuite.pro | Open | [8 empty] | 1
| thm_scm_cotrans_cltestsuite.pro | Open | [8 empty] | 1
| thm_scm_dproc_cltestsuite.pro | Open | [9 empty] | 1
| thm_scm_load_cltestsuite.pro | Open | [9 empty] | 1
| thm_slice2d_cltestsuite.pro | Open | [9 empty] | 1
| thm_spdf_cltestsuite.pro | Open | [9 empty] | 1
| thm_specplot_cltestsuite.pro | Open | [9 empty] | 1
| thm_sst_contamination_test.pro | Open | [9 empty] | 1
| thm_sst_load_cltestsuite.pro | Open | [9 empty] | 1
| thm_state_load_cltestsuite.pro | Open | [9 empty] | 1
| thm_tplotxy_testsuite.pro | Open | [9 empty] | 1
| thm_trg_load_cltestsuite.pro | Open | [9 empty] | 1
| thm_tsy_cltestsuite.pro | Open | [9 empty] | 1
| thm_ttrace_cltestsuite.pro | Open | [9 empty] | 1
[6 empty] | 10 | 11 | 6 | 6 | 6 | 10 | 12
[6 empty] | A | N | C | JL | JM | P | E
| GUI Test Suites |  |  |  |  | 8 | 6 | 3 | 4 | 5 | 4 | 2
| gui_tplot | Open |  |  |  | 1
| nudge | Open | [7 empty] | 1
| Data Processing | Open | [5 empty] | 1
| layout options | Open |  |  |  | 1
| line options | Open | [8 empty] | 1
| Axis Options (X axis only) | Open
| Axis Options (Y axis only) | Open | [5 empty] | 1
| markers | Open | [6 empty] | 1
| panel Options | Open | [5 empty] | 1
| rubberband | Open | [6 empty] | 1
| variable options | Open |  |  |  | 1
| legend options | Open
| Calculate | Open | [9 empty] | 1
| part getspec | Open |  |  |  | 1
| save data as | Open |  |  |  |  | 1
| Export to Image | Open | [6 empty] | 1
| Save Open | Open |  |  |  |  | 1
| page options | Open |  |  |  |  | 1
| z axis | Open | [8 empty] | 1
| load themis data | Open |  |  |  |  | 1
| pulldown menus | Open |  |  |  | 1
| toolbar | Open |  |  |  |  | 1
| pages | Open |  |  |  |  | 1
| ESA Full Suite | Open | [6 empty] | 1
| FGM Full Suite | Open | [8 empty] | 1
| GMAG Full Suite | Open |  |  |  | 1
| ASK Reduced Suite | Open | [7 empty] | 1
| SST Reduced Suite | Open | [7 empty] | 1
| SCM Reduced Suite | Open | [7 empty] | 1
| FIT Reduced Suite | Open |  |  |  | 1
| MOM Reduced Suite | Open | [7 empty] | 1
| EFI Reduced Suite | Open | [9 empty] | 1
| FFT Reduced Suite | Open | [8 empty] | 1
| STATE Reduced Suite | Open
| Slices Suite | Open |  |  |  | 1
| thm_ui_journal_history_help | Open
| thm_ui_interpolate | Open
| thm_ui_dproc_power_spectra | Open
| thm_ui_overview_plots | Open
| thm_ui_graphic_rendering | Open
| thm_ui_horizontal_bar | Open
Tests for external/contributed code
erg_gmag_mm2120_load_cltestsuite, erg_gmag_nipr_load_cltestsuite