## Open Tasks
Task #	Task Description	Date Opened	Reported By	Pri	Assigned To	Notes	Estimate	A&E; crib; script; suite; UG; DevG; Qref; AdmG
	To be Assigned or Discussed
4754	GOES overview plots				TBD	On hold until Eric's routine to load GOES data from NOAA is ready to use. Should include e-, i+, B field, s/c position, X rays, AE index, B wave survey (like FGM wave survey)
4756	Apply spacecraft potential to energy spectrograms		Aaron		Jim M?	Do not apply. Rather, show S/C potential as black line in ESA e- summary plots (within TDAS and also on web). Enable with new keyword to thm_part_getspec?
4758	Clean up s/c potential (onboard and ground), FBK and EFS data for time intervals when SDTs are running				Jim M?	Cleanup to be done in L1->L2 processing, using time intervals when SDTs were being run. Eliminate this contaminated data from summary plots and L2 data files.
4760
4761
4762

	Hannes
4018a	New Calibration FGM parameters and spin axis offsets	5/10/2010	Hannes	1	Hannes	12/06/2012: Cal files updates, all probes from mid-August 2012 on.
4080	Attitude Determination next few months	6/21/2010	Hannes	1	Hannes	5-24-2013 Updated for 2012-12-01 – 2013-02-21, tha, thd, the
4472	Inter-spacecraft FGM calibration for ARTEMIS.	1/4/2012	Vassilis	1	Hannes	6/4/12 from Hannes: Artemis inter spacecraft differences show good results with current calibration
	Aaron
4711a	Getspec rewrite, sanitize ESA	05/23/13			Aaron	Convert to physical units, standard internal representation, strip extraneous fields to save memory
4711c	Getspec rewrite, Apply theta,energy,phi limits	05/23/13			Aaron	disables bins based on user specified limits
4711g	Getspec rewrite, Make PA/Theta spec	05/23/13			Aaron	Tracking down last few discrepancies (e.g. fringing)
4711h	Getspec rewrite, Make Gyro/Phi spec	05/23/13			Aaron
4711i	Getspec rewrite, Make En spec	05/23/13			Aaron
4740	Getspec rewrite, bells, whistles, keywords etc.	07/08/13			Aaron	~1 week work remaining
4741	Getspec rewrite, GUI modifications to support new code	07/08/13			Aaron
4757	Implement wrapper routine for new moment calculations		Aaron		Aaron	Similar to spectrogram wrapper
4314d	combination of ESA and SST data could only be done in the Geometric mode. Would be great if it could be done in other modes as well.	8/11/2011	Xuzhi	4	Aaron		1 hr
	Cindy
4153	maintenance of gmag stations "Exclude List"	10/11/2010	David	0	Cindy	Exclude List up to date as of 9/20/2012, updates in progress (will take a while because we're so far behind)
4358	Every 6 months check that the UCLA Mag Cal have not changed.	9/6/2011	David	0	Cindy	Next September 2013
4751	Locate Photoshop files and update plot keys for overview plots and GUI plots	08/05/13			Cindy	“Deep plasma sphere” bit repurposed to “Very low magnetic field (> 30 Re)” for ARTEMIS probes. Photoshop file now checked into repository.
4753	Edit CARISMA master CDFs for PI info & reprocess data CDFs	08/08/13			Cindy
4842	GUI API – Plugin access to GUI configuration settings dialog (remote, local data dirs, etc)	1/18/2013		1	Cindy	Convert to tabbed interface, like “load data” panel.
4759	Clean up temp(?) files on UCLA mirror site that are causing error messages in cron output				Cindy	Cron output has been going to wrong C Russell until today, but you should be seeing the messages from now on...
4743	Clean up GMAG processing scripts		Cindy	2	Cindy	many variations of wget wrappers, will be much cleaner when code is consolidated.
	Eric
4731	Add support for loading netcdf files	06/25/13	GEM-SPEDAS	1	Eric	Implement netcdf2tplot as first step, then work with Janet Green to develop load routine for GOES netcdfs. Load routine now working for particle & mag data, working on some bug fixes.
4750	Add support for a standalone GSM->aGSM cotrans routine	08/02/13	Eric		Eric	Should accept either solar wind velocity data, or a user-provided rotation angle. Should live with other analytic transforms.
4749	OMNI solar wind velocity missing coordinate system attribute	08/02/13	Eric		Eric
4736	Add support for aGSM coordinates to neutral sheet model	06/27/13	Eric	2	Eric
4724	Calendar widget should indicate valid date range	06/25/13	GEM-TDAS tutorial	2	Eric	Maybe a tooltip?
4737	NaN vs “missing” in legend box	07/01/13	Pat	2	Eric	If cursor is outside the range of loaded data, should show “Missing” or “Out of range” instead of NaN in legend box.
	Jim L
4748	Jumps in FGS and FGL around times of FGM range changes	07/29/13			Jim L	May be a dropped sample at the time of the range change? Problem goes away with the start of the next L0 packet.
4142	issue with FGS processing - timestamps	9/30/2010	Vassilis	0	Jim L	not trivial. After 4764
2266	Timing of Spin Fit data	10/16/2009	Jim McFadden	0	Jim L	See 4142 After 4764
	Jim M
4732	Rename TDAS to SPEDAS for next release	06/25/13	GEM-SPEDAS		Jim M	Issues with thm prefixes -> spedas or spd, repository organization. First step may be to rename things in the release build scripts without disturbing the repository, if practical. Make separate nightly zip file with SPEDAS rather than TDAS “branding”.
4152b	change the ESA tables such that the minimum magnetospheric electron energy becomes lower (about 3eV, or lower). McFadden can specify the lower energy	10/20/2011	Vassilis	0	Jim M	Scripts appear to be running but we're still seeing the old configs. Need to work with John McD, seems like a flatsat setup issue.
	Nick
4755	Heidi Fuqua help request				Jim /Nick	She can access the THEMIS website via web browser, but can't download data in TDAS (MacOS, IDL 8.2.3, TDAS 8). Might be related to firewall or VPN configuration?
4728	Use SPDF web services to write a generic SPEDAS plugin to import arbitrary data sets	06/25/13	GEM-SPEDAS		Nick	Try using this method to access RBSP data
4734	trange keyword doesn't clip for thm_load_state	06/25/13	GEM-TDAS tutorial		Jim L	By design (to avoid clipping spin model). Leave spin model alone, but clip other tplot variables?
4704	Web site code & files should be checked into SVN	5/9/2013	Jim L		Nick	THEMIS done & deployed, ARTEMIS site next
4745	tplot_ascii formatting bug	07/25/13	Andre Runov		Nick	He was trying to print spectral tplot variables with values a few values that are very small negative numbers. (e.g. -1.23456789e-14, caused by round-off error in operations that would ideally be producing a result that is zero.) What he found is that the spaces between the columns can disappear which breaks parsing when he tries to read the values back in. / #1 This should be fixed. It should detect if it needs additional space to write a number and use wider columns. / #2 There is no keyword in tplot_ascii to manually control formats. There should be.(The workaround I gave him was to edit tplot_ascii.pro, obviously no ideal)
4752	Add GUI configuration option to specify command to use to spawn a web browser				Nick	No standard environment variable on Linux/Mac to reliably get user's preferred browser. (Hold until work on new configuration panel is completed?)
4729	Investigate bug tracking/wiki support for SPEDAS developers	06/25/13	GEM-SPEDAS		Nick?	Work with Clarina to do test install of issue tracking, wiki, blog tools
4738	User-friendly indication of availability of various THEMIS products over time (e.g. no L2 MOM until boom deployment)	06/25/13	GEM-TDAS tutorial		Nick?	THEMIS done, GOES, WIND, RBSP in progress

	Pat
4771	Writeup for new SST calibration	9/28/2012		1	Pat/Drew	For senior review. After 4844. Waiting for results of Drew's analysis, may implement a few more slight improvements.
4711b	Getspec rewrite, sanitize SST	05/23/13			Pat	Convert to physical units, standard internal representation, strip extraneous fields to save memory
4711d	Getspec rewrite, FAC transform	05/23/13			Pat	In progress. Needed to test some of Aaron's code updates.
4711e	Getspec rewrite, Regrid	05/23/13			Pat
4711f	Getspec rewrite, Apply PA and gyro limits	05/23/13			Pat
4740	Getspec rewrite, bells, whistles, keywords etc.	07/08/13			Pat	Adding support for new SST calibrations, about 1 week effort remaining
4744	Add combined ESA/SST moments capability to new particle routine	07/24/13	Pat		Pat	I was talking to Drew about particle stuff yesterday and we got to talking about how our goal for THEMIS particles should be combined ESA/SST particle products. (Spectra and moments) Doing this for spectra should be pretty easy with the new routine. (Just pass in a concatenated structure and it should work.) Doing this for moments would be pretty tricky in the current configuration because it makes a lot of assumptions about the particular instrument that it is working with. But Aaron and I were thinking that we could probably add moments capability to the the new particle routine pretty easily and this could be done in a way that was sufficiently generic that it would not choke on a combined particle distribution struct. I don't think it would be more than a week for one of us to do this.
4718	Add new variables to SST L2 master CDF	06/06/13	SPDF		Pat	New SST calibrations working well enough to start making new L2 CDFs.

## TDAS Enhancements
Task #	Task Description	Date Opened	Reported By	Pri	Assigned To	Notes	Estimate	Level of User Impact
	Proposed Enhancements
4058	This is getting a bit out of hand I think. How about a configuration file? The software just reads keywords from a configuration file. With such a configuration file it is possible to set keywords automatically (for the scientists) but additionally it would give us the possibility to keep track of what the software does automatically. When I do calibrations I can then save the configuration file together with the results and not worry about the things that the software might have done automatically.	5/10/2010	Hannes	3	Hannes	Hannes sent out new version for review.
519	We should extend our data model to support 3-dimensional distributions and 3-dimensional image data. This will entail modifications to load widgets, the loaded data object,the tree widget, the data processing widgets, and the addition of a means to draw	10/17/2011	Vassilis	3	Aaron
519a	She asked about generating ASI plots, like the ones done online, with the ASI data superimposed on a map. Ultimately, we may be able to implement this in a method similar to the method used for overview / plots.		Xiaoyan	BL
4299	it looks like a way to better integrate the slices code with the THEMIS GUI without major modifications. In the current version, it doesn't generate the plots in the main themis window and it doesn't store the slices data in / GUI memory. This means that you can't use analysis routines or change plot options the way that you can for other data types. But if we map the slices data into our current data model by storing the slices as if they're spectral data, we can include these data without any major changes. You wouldn't be able to automatically scroll through a series of slices, but they would be stored in the GUI memory so that you could plot them using the standard routines, perform analysis using the standard routines and export/save using the standard routines.	7/27/2011	Pat			Vassilis 7/27/11: These are good to haves but I think we are not cut for such a sophisticated system. We just need the basic cuts - they'd be already 10 times better anyone has ever done! 1-25-2013: Revisit the issue if/when we ever implement GUI plot types for 2-d (map-like) data. See 519,519a.
1149	If you accidentally close an overview plot page, it would be nice to be able to recreate the plot without having to reload all the data.		Bryan	EL			tbd
1150	If you open and close the overview panel, it doesn't store the current data. (or use the one that is available from the loaded data panel) It probably should.		Pat	EL			tbd
1283	Something we might want to put on the list is looking into making the / overview plots load faster and use less memory. Right now they are much less efficient than they could be.		Pat	EL			2 days
2030	upgrade thm_load to work with probe assignments		Vassilis	3	Lydia
806a	Markers -1) Allow feature for user to control marker lines (style, color,size) marker text (font, format, color, size), and marker shaded region (color, opacity) 2) Add logic to check when tracking all is on so that selected markers will be selected for all panels. 3) If multi-panel tracking is on, subset all visible panels at the same time-range.			3		Vassillis reviewed on 7/20/09	1 week
4297	One, the slices code should probably throw out the top four SST energy bins when it uses the default SST load and calibration. Those bins are not properly scaled in the default SST code and their energy boundaries are wrong. Vassilis 8/1/11: SST Calibration will fix. This task should be closed if the old SST calibrations are retired; if the old calibrations are still available as an option, reconsider keeping this task open.	7/27/2011	Pat	2		On hold till the SST calibrations have found wider use. Aaron 7/27/11: For the first suggestion (of throwing out the top 4 SST bins) that is something that I think we would want to implement at a lower level than the slices; perhaps as a keyword to the routines that load the data. We could do a specific implementation for the slices, however, the underlying issue should probably be addressed for any code using SST data. This is probably something we should discuss at the next meeting. If we decide to implement a slices-specific fix then it should be noted in the user's guide.
2140	A suggestion: The function used by tsub_average to return the median or average of the data can also be used to return the standard deviation. Since a single panel will probably be made for both the subtract average and subtract median options we could also add a third option to add/subtract the standard deviation.		Aaron	tbd		Subtracting the stand. dev. from a quantity may not make sense in the way that subtracting the average/median does. We may just want to direct people to the calculate panel, possibly adding a function to calc. stand dev. - Pat
4695	I noticed that, currently, when a nudge is performed it splits the component out of its group to create the new nudged quantity. We might want to consider allowing users to nudge entire groups to prevent this problem		Pat	EL
4135	Now that the L1 ESA/SST/MOM reprocessing is underway, these CDFs will soon contain the full ESA and SST configuration words, in addition to the solar wind flags, sweep modes, and so forth. With the full configuration data available, if someone wants to use a property of these instrument configurations that's not already present as a L1 variable, we don't need to reprocess L1 to add it -- we just write a little more code for TDAS, to extract the new attribute from the configuration data that's already present.	9/10/2010	Jim L	3	Ben	On hold, after QA.
4135b	In the load and/or calibration routines for ESA, SST, MOM: rather than using the ESA solar wind flags and sweep mode from the L1 CDFs, use the ESA full configuration instead (which is present in all three L1 types, for convenience), and use the routines from 4135a to extract the solar wind flags, sweep mode, and any other useful attributes. I think SST does not have any configuration flags similar to the ESA quantities (there's the attenuator status, but that's separate from the instrument configuration word), but it needs them in the future, they should be handled the same way as ESA (extract from SST configuration word instead of adding L1 variables). I can do this, but if the routines from part (a) are well-documented, any of us could probably do this part.	9/10/2010	Jim L	3	Ben	On hold, after QA.	2-4 hrs
1447	Look into file compressions methods - possibly apply to redraw		Pat	EL
2055	ESA L2 from L1 (not packets) - create L2 and test thoroughly, then reprocess ESA		Vassilis	3	Jim M	On Hold; awaiting Jim L to split L1 into master cdf
QA002	IDL 8.1 font changes -- text no longer correctly formatted	1/18/2012	Pat
QA003	IDL 8.1 changed window behavior (z-ordering): when options panels opened, main GUI window disappears behind main IDL window. Happens with modal and non-modal windows.	1/18/2012	Aaron
QA005	IDL 8.1 GUI plots laid out differently; margins and fonts have changed, even with all default settings in place.	1/18/2012	Aaron
4685	“Scale to Page” layout option	4/4/2013	Nick		tbd	The "problem": When we add panels they become smaller in order to fit into / the page. An extreme case is the overview plot. / The solution: We could add a menu selection under Graph, called "Scale to / Page", and when it is checked (the default) everything will work as it / does now. If the user unchecks it, then the panels will get longer and the / page will get longer too (or we can split it into multiple pages). This / will probably be helpful when the user wants to inspect the plots, or / copy-paste into Word, or for posters etc. It may also help with the / overlapping labels problem in the overview plots. This will need to be tested using multi-column as well as single-column layouts.
4686	Refactor axis options code	4/5/2013	Eric		tbd	we may want to eventually spend some time refactoring the axis options code. It's over 4,600 lines, has inconsistent tabbing in several places and there seems to be lots of obsolete code commented out.
QA127	Axis options -- “apply” affects multiple panels	04/16/13	Pat		tbd	After QA. I'm attaching a gui document to help reproduce. Problem: when I set y-axis ticks to aesthetic=off, then I select "apply to all" the ticks on all panels change. If I then select "apply", the ticks on panel 3 change again.(even though I have panel one selected and did not "apply to all") / #1 Load GUI document. / #2 Open y-axis options, select ticks tab. / #3 Uncheck "aesthetic ticks" / #4 Select "apply to all" / #5 Select "apply". (Error: panel 1 *AND* panel 3 change)
4806	CLUSTER load routine?	11/27/2012	Johnathan Eastwood			There may be a way of importing this data into tplot already, but maybe under a non-obvious name? Ask Jim McFadden, Tai Phan, French team?
4725	Generate combined ESA/SST moments in GUI	06/25/13	GEM-TDAS tutorial			Very preliminary at the moment, add to GUI in 6-12 months (so probably sometime in 2014)
4726	Show data analysis commands & options in GUI history window	06/25/13	GEM-TDAS tutorial			Would have to be done separately for each analysis routine, not really trivial, but still doable.
4730	Integrate idlneturl into file_http_copy?	06/25/13	GEM-SPEDAS	2	TBD	Would have to sacrifice IDL 6.3 compatibility, but most users should have upgraded by now. OK to proceed.
4735	tsyganenko support in GUI	06/25/13	GEM-TDAS tutorial	2	TBD	Does this mean we'd have to distribute the DLM/DLL/so files with TDAS instead of providing a separate download? How would this work for the VM?

## SOC processing enhancements
Task #	Task Description	Date Opened	Reported By	Pri	Assigned To	Notes	Estimate	Level of User Impact
	Proposed SOC processing Enhancements
4022	Update L1 master cdfs to support SPDF hosting	3/25/2010	David	3+	Jim L	I think 4022 is a an end-of-mission task: basically clean up all the L1 CDFs, so they are fully ISTP compliant and as compatible as possible with SPDF's tools. But "ISTP compliant" is a moving target -- they keep adding new checks to the SKTEditor software -- so I think we made a task to do one final cleanup and reprocessing at the end of the mission, as opposed to reprocessing every time they introduce a new SKTEditor check that / renders our L1 files non-ISTP-compliant. / So 4022 = final end-of-mission adjustments to master CDFs, / 4023=final reprocessing. Both should remain open, with no / immediate action required as far as I know.
4040	Spinfits - separate E&B timestamps?	4/15/2010	Jim L	3	Jim L	SPDF has issue creating plots on the L1 data with their software	2 hrs
4046	either thm_load_fit or the GUI code that calls thm_load_fit should split the data into separate tplot variables for E and B, before importing them into the GUI data model. I think thm_load_fft already does something like this. See task 4040	4/23/2010	Pat	3	Jim L	Jim M 4/23: thm_load_fit also splits into efit and bfit variables, so unless you need to look at raw bytes, the 'fit' datatype is not needed. Pat: Agreed. Short term, excluding the data type from the GUI seems like an easy solution.
2047	task 2047 in my name: "Seperate E and B timestamps for spin fits", which is also a change to the L1 FIT master CDF and associated TDAS code. But unlike the spacecraft potential enhancement (which only adds new CDF variables, and is more-or-less backward compatible), 2047 would require us to bump the L1 FIT CDF version number to V02, and produce both V01 and V02 for a while, so users of TDAS 5.20 and earlier will still be able to load L1 FIT data. So I'm not sure whether the spacecraft potential task should include 2047, or not.	3/2/2010	Jim L	4+	Jim L
2081	Evaluate CDF compression algorithms BugZid=81		Vassilis	4	Jim L
2038	STATE Web Page (s)		Vassilis	3	Jim L	review web pages
2040	L1 Data Processing History Info: SCM, EFI, STATE		Vassilis	3	Jim L	Ben???
2077	Non Monotonic timestamps. BugzID=72		Vassilis	3	Jim L
4075	describe the FBK data type, time tag specified to correspond to the beginning of the time interval of the data that went into the FBK data, the middle, or the end, or is that unspecified, and what's happening here is that the time tagging is being changed in year 3+ of the mission - in the L1 file definition document, at least, does not define the time-tagging conventions to this level of detail.	6/11/2010	John Bonnell	4	Jim L
4023	Before EOM reprocess L1 cdf's due to master cdf changes for SPDF	3/25/2010	David	4	Jim L
2080	Phantom packets" cause non-monotonic distribution times. BugzID=25, low priority.		Vassilis	4	Jim L
2081	Evaluate CDF compression algorithms BugZid=81		Vassilis	4	Jim L
2083	Add "last processed" time to L1 (and L2?) CDFs BugZid=115		Vassilis	4	Jim L
4097	cdf's with MD5 checksum	7/19/2010	Jim L	4	Jim L	Jim L to send email with subtasks and estimates
2046	Create a more efficient & productive prototype QA Instrument Command Line Script - first template (s) functional blocks then scripts for FGM, ASK, SCM, FIT, MOM, ASI, EFI, FFT, FBK, Gmag, State, SST, ESA		Jim L	2	Ben	Save v7.0 templates and saved files.
4532	Developer's guide update re: "touched" properties, standard way of tracking which settings were changed at user's request.	2/27/2012	Pat	2	Ben	with 4455
4214	THEMIS Pipeline proof of concept regression tests					On hold, after QA.
4214e	GMAG	3/23/2011	Jim L	2	Ben
4214f	AE Index	3/23/2011	Jim L	2	Ben
4214g	ASI	3/23/2011	Jim L	2	Ben
4214h	mosaics	3/23/2011	Jim L	2	Ben
4214i	summary plots	3/23/2011	Jim L	2	Ben
2091	Once Jim McFadden completes his mods for n_3d_new_3 reprocess L2 cdf's - entire mission		Vassilis	3	Jim M
	Automated GUI testing	5/14/2013	Eric			There are Python libraries that can be used to automate clicking on GUI elements, reading values from text boxes, etc. We could use these to script a lot of our GUI testing.

## Unconfirmed bug reports
Task #	Task Description	Date Opened	Reported By	Pri	Assigned To	Notes	Estimate	Level of User Impact
	Unconfirmed/hard to reproduce bugs
QA020	Calculate, panels with modified variables sometimes blank	03/08/13	Aaron			(cannot consistently reproduce) There were a few times where the panel containing a variable that was modified in calc was blank after exiting, even though auto range was on. The panel would be blank with a [0,1] y-axis range (the data was valid and worked fine on a new panel).
QA024	Axis options – negative min on log axis	03/08/13	Aaron			(cannot reproduce) The y-axis min/max was reset to [1,inf] after Applying a negative min on a log axis. When I attempted to set it to [1,20] a min>max error was given and the range set to [0,1].
QA031	Performance issue, memory usage	03/08/13	Aaron			Not clear if still happening? After running IDL for I while I end up needing to restart to free up memory. I seem to be noticing it the most after I have recently loaded large amounts of data, but it's hard to say exactly what might be causing it without more targeted testing. I attached a screen shot exampling the memory freed from a .full_reset_session and from exiting IDL (restarting IDL only added ~100mb back). I'm not sure when I last restarted so this could be a small issue that accumulated over time.
QA082	Data processing, cotrans	03/26/13	Aaron			Having trouble reproducing. I received an "unexpected error" when trying to transform a variable from DSL to SSE. SLP data was already loaded into to GUI from a previous cotrans operation and had not been modified. Console output below. / STORE_DATA(221): Creating tplot variable: 11 newpos_sse / DSL2GSE(210): done / Traceback Report from THM_UI_COTRANS_NEW: / $MAIN$ / THM_UI_DPROC_PANEL_EVENT <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_dproc_panel.pro( 146)> / THM_UI_COTRANS_NEW <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_cotrans_new.pro( 353)> / ERROR_MESSAGE <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\utilities\error_message.pro( 256)> / Last IDL Error: / % GSE2SSE: ERROR: slp_sun_pos needs to be in GSE or GEI coordinates / % Execution halted at: GSE2SSE 123 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\state\cotrans\gse2sse.pro
QA028	Data processing – solar/lunar ephemeris load failed when replaying saved document	03/08/13	Jim M		Pat	Having trouble reproducing. Loading Solar/Lunar ephemeris data... / Object reference type required in this context: VAR.
QA006	IDL 8.1 intermittent crashes in eclipse processing code	1/19/2012	Ben
4700	Trouble opening eps files exported from GUI	5/3/2013	Aaron		Aaron	Exports from slices gui OK, main gui not OK. Can be opened with OpenOffice on Linux, but not in Adobe Reader or Illustrator on Windows. IDL 7.0.6. Unable to reproduce
4710	Diagnose severity 1 GMAG processing errors, stuck job on auxo	05/20/13	Jim L		Cindy	Trouble diagnosing, can't reproduce. Cindy is adding additional logging.

## Closed Post v8.0
Task #	Task Description	Date Opened	Reported By	Pri	Assigned To	Notes	Estimate	A&E; crib; script; suite; UG; DevG; Qref; AdmG
4611d	Nightly thmsoc cron job to check/install updates to SPDF leap second table on SSL data server. Lower priority; probably won't be another update for at least a year.	4/17/2012		4		Complete by April 2013
4042	Script to run every two weeks to runs IDL TDAS and checks if a file can be loaded from THEMIS SPDF file (s)	4/19/2010	Pat	3		see Pat
4706	Missing data from McGrath magnetometer site	7/18/2012	Cindy	1	Cindy	2/22/2013: RMD files received, but data not being processed for some reason.
1496	State Reduced: The themis document doesn't keep track of the current page. Maybe it should.		Pat	EL
4862	Reprocess L2 FIT data to fix efs_0, efs_dot0 (different counts of timestamps and data values)
4792	2013 MAP for Senior Review	11/1/2012			Jim L
4685	Widget tree expansion, IDL 8.2	6/26/2012	Pat	1	Aaron	IDL fixed a bug which we had worked around, need a version check to enable/disable the workaround so it will work on all IDL versions.
4857	thm_convert_esa_units, conversion to energy flux and back not symmetric	2/22/2013	Aaron	1	Aaron
4760	Add McMac magnetometer network (12 sites) to our data set.	9/17/2012	Vassilis	1	Cindy	2/22/2013: Server problems at McMac data server, back data from 2007, 2008 being processed.
803	Would be nice to have a way to move different panels from one page to another	11/22/2011	Oldie	2	Pat	sort how level of effort to accomplish. On hold, after QA
4855	Discrepancy between spacecraft positions in summary plots.	2/8/2013	Mike Hartinger		Jim M	I noticed a discrepancy between the spacecraft position data shown at the bottom of the summary plots on the THEMIS website. The particular summary plots I compared were 2008-02-26 06:00-08:00, THEMIS-E - "Overview", "Space ESA moments", and "Ground ESA moments". The position data from "Overview" and "Ground ESA moments" differ from the position data from "Space ESA moments". 2-15-2013: Fixed, reprocessing plots.
4843	Cron job to update configuration history database	1/24/2013		1	Nick	FBK done, FFTs next
4537	Deletion of data not reflected in saved/reloaded THEMIS document. Formerly QA206. Also remember to overwrite prompt setting (yes to all, etc)	3/2/2012	Lydia		Pat	See 4689
4847	Improve TDAS installation instructions for external libraries like IDL_GEOPACK	1/29/2013	John Bonnell		Cindy	May require sysadmin assistance if user doesn't have permission to update IDL installation directories. We should also mention the option of installing to an alternate location and using the DLM_PATH environment variable, rather than updating the IDL directory. README.txt with IDL_GEOPACK installation instructions already updated, copy into user guide and quick reference guide (if IDL_GEOPACK is mentioned at all there).
2100h	Try to track down frequency scaling problem in DPWRSPC (dlimit setting? Compare to old plots?).		John Bonnell	4	Eric	regenerate test plot and see if fixed after TDAS 8
4705	Fix master CDF to correct bad long/lat for one McMap site, reprocess data CDFs	5/9/2013	Tami		Cindy
4693	xtickinterval, ytickinterval for specplot.pro	4/15/2013	Andrew Poppe		Jim L	Suggest using plotxyz instead of specplot...JWL to mail AP and see if that meets his needs. I've been using specplot.pro directly to make plots and have noticed that it doesn't seem to accept the 'xtickinterval' or 'ytickinterval' keywords as part of the limits keyword structure. Can someone confirm this, and if so, would it be possible to add this functionality?
4702	Possible problem with neutral sheet model	5/3/2013	Cindy		Cindy	Fix tested and checked in
4703	thm_map_add needs directory separator when building path to .sav file	5/3/2013	Harald		Cindy
1266	Our numerical entry fields only accept exponential notation entries of the form (1.23e-3) but not the more traditional format( 1.23*10^-3). We may want to leverage the code base from the mini language so that we can interpret these entries as numbers.		Pat	2		Still happening?	3 days
4698	time_clip/tclip	4/26/2013	Pat		Jim M	tclip is for clipping y-axis data, and doesn't do time clipping at all. Needs better documentation.
4691	Use TLB_FRAME_ATTR in thm_ui_prompt_widget to avoid need for looping around overwrite/confirmation dialogs (by disabling [X] close button).	4/10/2013	Nick		Nick	Implement on one dialog first, test on all supported platforms, if it works everywhere, then convert the rest of the dialogs.
4713	Since the diode degradation will be modeled as shifting the minimum energy of the SST up, we'll need to interpolate the SST efficiency parameters to the new energy bins.	7/24/2012	Vassilis	1	Pat	This may not actually be done by someone on the software team, but I thought I'd report it anyway, so that it doesn't get lost in the shuffle once the other calibrations are completed.
4844	Different SST look directions no longer line up in energy with original calibration factors	1/24/2013	Pat	1	Pat	What we came up with is to interpolate the esa to match SST(in time & look direction), then smooth the ESA data to account for poor count statistics, then interpolate between the SST and the ESA to shift the SST to a regular energy grid. This will be a decent amount of effort to code up, but it seems promising. Will probably not make it into TDAS 8.
4460	Add New Routines from Lynn Wilson	3/22/2012	Vassilis	1	Pat
4460-1	Include: safe, minimal effort, obvious benefit. (21)		Vassilis	1	Pat		3-4 days
4460-2	Documentation only: LW3 has documented a routine that didn't have documentation previously, but incorporating routine body is not worthwhile.(possible bugs or too much effort) (12)		Vassilis	1	Pat		1 day
4460-4	Not sure: Need a scientist's opinion on the benefits of the routine. (26)		Vassilis	?	Pat	Vassilis will talk to Lynn Wilson and ask the benefits of these routines
4460-5	Not sure: Need more programmer time to make confident recommendation. (14)		Vassilis	?	Pat	Vassilis will talk to Lynn Wilson and ask the benefits of these routines
4460-6	Helper, only include if required by an included routine. (9)		Vassilis	1	Pat
4686	There were several reports that the dproc window was too small in IDL 8+. It looks like this is a side effect of the font change.	6/27/2012	Pat	2	Pat	For whatever reason, many widget sizes are specified in characters, instead of more standard units. This means that if the base font size of a character changes, so does the size of a viewable area. Just an FYI, I'm going to be rolling this one into the font size one. I'll list it as a reason why the font size change is such a pain in the rear.
2035	Split L1 ESA (using Thomas’s routine) in master ESA data cdf		Vassilis	2	Jim M	On Hold - awaiting Jim McFadden release: Then send David Sub Task List; Calibration variables removed from L1 data master CDF. (Side note: found and reported a bug in SKTEditor, which the Goddard team has agreed to fix...) Waiting for feedback from Jim McFadden about how calibration data should be handled (TH-A ASCII calibration file (used for all probes) doesn't match anything I removed from the data CDF).
808	IDL Format Code -currently have no way to insert a different font in the middle of a string (e.g. adding a symbol to a string in NewTimesRoman). Possibly enable formatting like we did for the z axis labels		Oldie					1 day
1512	Cancel load process			EL		How to implement within GUI? Command line? Tbd
4832	Allow keywords in calc function calls	1/7/2013	Vassilis	1	Pat	e.g. calc,'a=total(b,/nan)'
1301	The draw object takes a long time to render spectrograms when they are very zoomed in. It should be possible to put a special case in that would make this work more quickly.		Pat	1		Workaround in place, working on another optimization that could save some memory and fix some other issues
4697	Omni load, if no data available for selected interval, loads whatever is available for that month	04/26/13	Eric		Eric	May be intentional to keep from producing empty tplot variables, but time_clip should at least produce a prominent warning.
4694	Open legend options by clicking in legend box	4/18/2013	Eric		Eric	Similar to axis, panel, page options
4683	Change L2 FIT master CDF to allow different sample counts for efs and efs_dot0		Jim L			In progress.
4701	thm_part_moments2 very slow with certain options	5/3/2013	Pat	1	Pat	Possibly related to new SST calibrations?
4519	getspec/thm_part_moments2 (CL) rewrite for maintainability	2/21/2012	Pat, Aaron, Jim M	2	Pat/Vassilis	Code has become prone to bugs, very difficult to understand and maintain, would benefit greatly from rewriting from scratch with "lessons learned" up to this point. Level of effort? Pat and Vassilis to go over code, improve documentation, and identify areas that could be improved.
4519a	Aaron has identified some “cut points” for sections that can be pulled out as separate procedures.			2	Pat	Extract procedures, figure out which variables are used/required in each section.
4712	Undefined proc/func 'TRG' in get_ylimits	05/23/13	Naiguo Lin		Eric	Here is part of the program that I try to run: / get_data,'thc_peif_N',data=tmp / store_data,'dens_f',data={x:tmp.x,y:tmp.y} / get_data,'thc_peim_density',data=tmp / store_data,'dens_m',data={x:tmp.x,y:tmp.y} / store_data,'NmNr',data=['dens_r','dens_m'] / I can plot 'dens_f' and 'dens_m' with tplot separately (for example, tplot,'dens_f' or tplot,'dens_m') / but when I plot 'NmNr' with / tplot,'NmNr' / I got the following error message: / % Attempt to call undefined procedure/function: 'TRG'. / % Execution halted at: GET_YLIMITS 29 /disks/socware/idl/ssl_general/tplot/get_ylimits. / pro / % TPLOT 491 /disks/socware/idl/ssl_general/tplot/tplot.pro
4709	Move is_numeric function to ssl_general and add keyword to preserve backward compatibility	05/20/13	Eric		Eric
4688	Add load routine for Kp index data.	4/8/2013	Xuzhi		Eric	ssl_general/key_param/load_kp.pro is obsolete, but Kp data is available from: ftp://ftp.ngdc.noaa.gov/STP/GEOMAGNETIC_DATA/INDICES/KP_AP/ Should check Tsyganenko cribs since some of them use Kp indices. There is also a IUGONET routine which is capable of loading some geomagnetic index data.
4707	Problem with GUI overview plots for default date	5/22/2013	Aaron		Nick	Works in IDL 8.2.2, fails in IDL 7.1. Related somehow to NaN cleanup in thm_cal_fit.
4816	Eclipse spin model processing: some eclipses not being processed with current code, but Ferdinand's code is giving results?	12/7/2012	Ferdinand		Jim L	Ferdinand has updated eclipse model parameters for inner probes
4860	Check inventory of Berkeley vs. UCLA GMAG CDFs and transfer any missing files	3/6/2013	Jim L		Cindy	On the Berkeley server, we have data for site "upn" for every day in 2010-06 / *except* for 2010-06-06, the date used in the test. I'm looking in: / /disks/themisdata/thg/greenland_gmag/l2/upn/2010 / The CDFs for 2010-08-07 and 2010-08-08 are missing, too. / It looks like there was a mass update of that directory in May 2012.
4699	improve time series handling in plotxyz	4/29/2013	Pat	1	Pat	Add x-is-time, y-is-time keywords
4711	Getspec rewrite, top level	05/23/13			Pat	Loops over data, validates input arguments
4715	Right click on data tree not showing metadata for non-THEMIS variables	05/24/13	Eric		Eric
4716	thm_part_moments gives different results than it used to	05/28/13	Don Fairfield		Jim M	Two years ago Dr Miho Saito (who was in our lab at that time) visited UCLA and with the advice of Vassilis and others developed a program to calculate total pressure from esa and sst data. I ran this program successfully until recently. Now the program fails due to a problem with the routine reading esa data: thm_part_moments. I see no error messages but the results are clearly wrong because the day was run sucessfully in the past and I know what the results should be. It looks to me like all the energy channels are not being used resulting in incomplete energy spectra and too-low density. When this day is run with all 5 spacecraft the error is the same in all spacecraft.
4713	Add GUI load panel for geomagnetic indices	05/24/13	Eric		Eric	6/7/2013: In progress. OK to create dependency on iugonet code?
4722	Finish implementation of OMNI load routine datatype keyword	06/14/13	Eric		Eric	For geomagnetic index panel.
4723	Add hexadecimal format option to legend options & annotation options	06/14/13	Jim L		Nick
4706	Replace difficult-to-modify Javascript menus on themis web site, clean up navigation inconsistencies	5/17/2013	Nick		Nick	2013-06-07: THEMIS done, working on ARTEMIS
4721	Use IDL file picker dialog for “export as image” function	06/07/13			Nick	Need a submenu to select the image format, then use standard file picker to specify directory/filename, then format-specific dialog for image conversion parameters (e.g. jpg compression, eps resolution)
	Update FBK, FFT, ESA, SST configuration history HTML pages				Nick	Update monthly for now.
4733	Bug report: pxxm_pot doesn't always load in GUI (e.g. default day)	06/25/13	GEM-TDAS tutorial			No L2 moments CDFs for times before EFI boom deployment
4858	One-count removal for velocity slices – make cutoff value a parameter	2/22/2013	Aaron	1	Aaron	06/06/2013: Checked in some code, but duplicates some functionality in Pat's background subtraction code. Should they be merged?
4717	Verify TDAS versus ssllib neutral sheet models	06/03/13		2	Eric	6/7/2013: In progress, combining wrapper and processing routines, then will get help validating results are as expected. 6/14/2013: Some results have changed with updated code, need to figure out why.
4719	file_http_copy requests getting blocked on some web servers	06/06/13	Marc Pulupa		Jim L/Clarina	Multiple requests in rapid succession (e.g. lots of small files) triggering DOS protection measures.
4506	GUI Getspec: Some regrid values yield all while plots (noticed in GUI getspec test suite for TDAS 7). If a re-write of thm_part_getspec this would be done as part of it.	2/8/2012	Aaron	2		In this case phi/theta values of 40x20, 45x20, and 64x20 yield plots but 50x20 and 49x20 do not. All energy fluxes appear normal. This is certainly something strange happening in thm_part_moments2, so we probably want to wait until after QA to fix it. After 4711
4859	Double check processing & mirroring of Greenland GMAG data	3/6/2013	Cindy		Cindy	Some data for site “upn” was missing at Berkeley but present at UCLA. 6/7/2013: Identified missing files at UCLA, need Bill and/or Todd to fix 7/12/2013: Mirror files should be owned by a 'thmsoc' user so we don't have to go through the sysadmins to make corrections.
4784	Add RBSP orbit data to THEMIS plots	10/16/2012	Vassilis		Jim M	Plots are on beta site now, also Nick's test area. Reprocess all plots so they'll be the same size?
4521	GUI getspec: issues when setting phi limits and starting phi at same time -	2/8/2012	Aaron	2		I produced two phi plots with the phi limits set to 45 - 180; the second plot also had the start angle set to 90 degrees. That plot begins at 90 degrees and appears as it should until just past 160 degrees at which point the remainder appears to be 'smeared' and ends at a maximum of ~440. Because of this it is also hard to tell if it looped back to the data between 45-90 correctly. Should be fixed now, will close when passes all tests
4507	GUI getspec: no way to return just an energy spectrogram	2/8/2012	Aaron			Formerly QA099 Should be fixed now, will close when passes all tests
4505	Add a TDAS routine to do 1-d cuts - when ready to work send Aaron Bennenman an email for clarity of task and then review at the S/W meeting again with Vassilis.	2/6/2012	Aaron Breneman	2	Aaron	You could obtain a 1D cut of a slice by aligning the custom orientation vector (slice_orient keyword) such that the desired cut is along the x or y axis. The data could then be pulled directly from the array returned by thm_part_slice2d via the 'part_slice' keyword. This returns an R x R array containing the interpolated slice data (R=resolution). The x & y axis values for the array are returned in the 'xgrid' and 'ygrid' keywords. 7/08/2013: Good feedback from Stefan, seems to be working well, one or two minor issues to confirm with Aaron B.	1 hr
4719	ESA energy table updates – TDAS mods (ESA packet processing, calibration, summary plots, etc)	8/2/2012	Jim L	1	Aaron
4742	Limit time range of data loaded by cdf2tplot	07/09/13	Peter Schroeder			We have been using cdf2tplot to load RBSP/EFW data into IDL, but we have run into an issue that I'm hoping someone else has solved before I try to reinvent the fix. / The problem is that the amount of data in one of our daily burst files can be huge: way too much for many machines to handle. We are trying to figure out how to load only a portion of a cdf file (for example, extracting 10 minutes from a daily file using a defined timespan). I don't see an obvious way to do this in cdf2tplot. I do see that cdf_load_vars allows you to load by record index, which is what I think you would have to do. JWL to email Peter with suggestions from group discussion.
4611e	Add support to GUI configuration settings panel for editing/saving cdf_leap_second configuration. (See also: tasks 4516 and 1315 for ACE, WIND, ISTP).	4/17/2012		1	Nick	What to do about differences between structure fields in the various system variables (!themis, !cdf_leap_sec, !goes)? Working, but doesn't support CDF_LEAP_SEC preserve_tt2000 setting yet.
4747	wavpol compile error	07/29/13			Nick	Changed gamma(x,y) to gammy[x,y] to avoid conflict with IDL's gamma() function. Lots of other array references using () syntax are there and should be changed too.
4684	thm_cal_fit: clean up NaNs in fgs and efs, reprocess L2 FIT		Jim L			After 4683. Will need to change code that writes variables to L2 CDF. Jim L to test sample reprocessed L2 file.
4708	Add nan_cleanup keyword to thm_load_fit and thm_cal_fit. Default should be “no cleanup” for backward compatibility.	5/22/2013	Jim L		Nick	On hold until we see whether this is needed or not
4720	Update GMAG master CDFs with correct GIMA PI credited	06/05/13	Dieter B		Cindy	Master CDFs first, data CDFs when convenient to reprocess
4746	Crash in moments_3d	07/26/13	Pat		Jim M	I was accidentally using values in the energy extrapolation that went too high and the extrapolations in my sst code generated values that were quite a bit too large. / When passed into thm_part_moments I got a crash: / % TRIQL: Too many iterations in tqli. / % Execution halted at: MOMENTS_3D 330 /home/pcruce/IDLWorkspace82/TDAS/idl/ssl_general/science/wind/moments_3d.pro / % THM_PART_MOMENTS 297 /home/pcruce/IDLWorkspace82/TDAS/idl/themis/spacecraft/particles/moments/thm_part_moments.pro / % $MAIN$ / The issue occurs because particle routines use floats and the numbers grew big enough during the calculation that they rolled into +-inf, which broke the routine that finds the eigenvalues/vectors for the moment matrix. The Particle routines intentionally use floats for storage because it saves memory. I say that this is not a big issue because the inputs were probably large enough that they wouldn't ever come up(correctly) for earth physics, but they weren't *that* far outside realistic ranges either. It would be preferable if the routine outputs a value(like infinity) or terminates with a clearer error message. Possible solutions would be to put a catch block in for the error, check the moment matrix for invalid values before triql, or cast to double before the operation and cast back to original data type afterward.
4825	Implement error estimates (/get_error) for angular spectrograms	12/10/2012	Vassilis

## TDAS 8.0 Release Notes
Task #	Task Description	Date Opened	Reported By	Pri	Assigned To	Notes
	To be Assigned or Discussed

RN001	Memory leak switching pages with IDL 7.1 and above (fixed now?)
RN002	IDL 7.1 excessive RAM usage in interpolate (doesn't happen in 7.0.6)
RN003	IDL 8.2.2, thm_cal_fgm extremely slow
RN004	IDL 7.1: NaNs treated differently in interpolation, only affects IDL 7.1.

## TDAS 8.0 Open Bugs
Task #	Task Description	Date Opened	Reported By	Pri	Assigned To	Notes	Estimate	A&E; crib; script; suite; UG; DevG; Qref; AdmG
QA109	Reorganize crib sheets	04/03/13	Pat			Maybe separate directories for “basic”, “advanced”, experimental” functions? (Will also need to update users guide and quick reference guide to reflect new crib locations)
QA147	Omni load, if no data available for selected interval, loads whatever is available for that month	04/26/13	Eric			May be intentional to keep from producing empty tplot variables, but should at least produce a warning.
QA148
QA149

	Aaron
	Cindy
	Eric
	Jim L
	Jim M
	Nick
	Pat

## QA v8.0 Bug List - Closed
Task #	Task Description	Date Opened	Reported By	Pri	Assigned To	Notes
	To be Assigned or Discussed
QA001	valid_names for thm_load_fft not working	2/28/2013	Cindy			Test suite fails in fresh session, works if retried
QA002	valid_names for thm_load_fbk not working	2/28/2013	Cindy			Test suite fails in fresh session, works if retried
QA011	crash in variable options	03/05/13	Eric			% Type conversion error: Unable to convert given STRING to Long. / % Detected at: ARRAY_CONCAT 29 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\ssl_general\misc\array_concat.pro / % Type conversion error: Unable to convert given STRING to Long. / % Detected at: ARRAY_CONCAT 29 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\ssl_general\misc\array_concat.pro / % Type conversion error: Unable to convert given STRING to Long. / % Detected at: ARRAY_CONCAT 29 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\ssl_general\misc\array_concat.pro / % WIDGET_CONTROL: String expression required in this context: VARNAMES. / % Execution halted at: THM_UI_VARIABLE_OPTIONS_INIT 819 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_variable_options.pro / % THM_UI_VARIABLE_OPTIONS_EVENT 456 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_variable_options.pro
QA005	Multiple failures in thm_fit_cal_cltestsuite, also same error in thm_fit_cotrans_cltestsuite	2/28/2013	Jim L			All tests failed with similar error: ;Test 0 Failed: thm_cal_fit,probe='a',datatype='efs' / ;ERROR: -163 / ;ERROR: % Subscript range values of the form low:high must be >= 0, < size, with low / ;ERROR: <= high: <No name>. / ;ERROR: % Execution halted at: THM_CAL_FIT 455 /home/jwl/tdas_8_00/idl/themis/spacecraft/fields/thm_cal_fit.pro / ;ERROR: % $MAIN$ 42 /home/jwl/tdas_8_00/QA_testing/thm_fit_cal_cltestsuite.pro
QA006	Failure in thm_fit_cal_template	02/28/13	Jim L			THM_CAL_FIT(334): No good fit codes, assuming that E12 is used for EFS / % Variable is undefined: NE34. / % Execution halted at: THM_CAL_FIT 355 / /home/jwl/tdas_8_00/idl/themis/spacecraft/fields/thm_cal_fit.pro / % $MAIN$ 51 / /home/jwl/tdas_8_00/QA_testing/thm_fit_cal_template.pro
QA008	Failure in gmag_load_cltestsuite	03/04/13	Jim M			Apparently the CDF for site UPN for 2010-06-06 is missing from the Berkeley server. ;Test 22 Failed: test dtu_sites / ;ERROR: -5 / ;ERROR: % $MAIN$: data load failed / ;ERROR: % Execution halted at: $MAIN$ 699 / /home/jimm/thmsoc_sw/QA_testing/thm_gmag_load_cltestsuite.pro
QA003	Blank plots 1-10 in thm_slice2d_cltestsuite.pro	2/28/2013	Eric
QA004	Test 11 failed in thm_slice2d_cltestsuite.pro	2/28/2013	Eric			;Test 11 Failed: Multiple distributions / ;ERROR: -224 / ;ERROR: % Tag name VELOCITY is undefined for structure <Anonymous>. / ;ERROR: % Execution halted at: THM_PART_SLICE2D_GETVEL 80 C:\Users\egrimes\Desktop\Space\tdas_8_00\idl\themis\spacecraft\particles\slices\thm_part_slice2d.pro / ;ERROR: % THM_PART_SLICE2D 954 C:\Users\egrimes\Desktop\Space\tdas_8_00\idl\themis\spacecraft\particles\slices\thm_part_slice2d.pro / ;ERROR: % $MAIN$ 371 C:\Users\egrimes\Desktop\Space\thmsoc\trunk\QA_testing\thm_slice2d_cltestsuite.pro
QA037	GMAG labels	03/11/13	Jim M			Note that the suite passes, except for step 5c) Labels for NAQ are (D, H, / Z) instead of expected (dD, dH, dZ).
QA025	Overview plots – crash in calendar widget	03/08/13	Jim L		Eric	Traceback Report from THM_UI_TIME_WIDGET_EVENT: / $MAIN$ / THM_UI_TIME_WIDGET_EVENT </home/jwl/tdas_8_00/idl/themis/thm_ui_new/utilities/thm_ui_time_widget.pro( 50)> / ERROR_MESSAGE </home/jwl/tdas_8_00/idl/themis/thm_ui_new/utilities/error_message.pro( 256)> / Last IDL Error: / % Keyword parameters not allowed in call. / % Execution halted at: THM_UI_TIME_WIDGET_EVENT 126 /home/jwl/tdas_8_00/idl/themis/thm_ui_new/utilities/thm_ui_time_widget.p
QA040	Interpolate calendar widget	03/11/13	Cindy			Error message reported whenever I use the calendar icon. Once the error is reported anything done with time (text box widget, check box for single day) produces an error. If I don't use the calendar icon the time text box and check box work fine. The error message is below.Last IDL Error: / % Expression must be a structure in this context: STATE. / % Execution halted at: THM_UI_TIME_WIDGET_EVENT 171 C:\Users\clrussell\Desktop\tdas_8_00\idl\themis\thm_ui_new\utilities\thm_ui_time_widget.pro / % XMANAGER: Caught unexpected error from client application. Message follows... / % Tag name GUI_ID is undefined for structure <Anonymous>. / % Execution halted at: THM_UI_INTERPOL_OPTIONS_EVENT 153 C:\Users\clrussell\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\dproc\thm_ui_interpol_options.pro / % XMANAGER_EVLOOP_REAL_MODAL 506 C:\Program Files\ITT\IDL706\lib\xmanager.pro / % XMANAGER 704 C:\Program Files\ITT\IDL706\lib\xmanager.pro / % THM_UI_INTERPOL_OPTIONS 447 C:\Users\clrussell\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\dproc\thm_ui_interpol_options.pro
QA041	dproc_power_spectra	03/12/13	Nick			Error in calendar widget
QA034	Suggestion, “save data as”	03/11/13	Nick		Nick	For consistency the message in the status bar should say / "Load Data" and not "Load THEMIS Data". Perhaps there are some other / messages like that.
QA035	Suggestion, closing pages	03/11/13	Nick		Nick	When I produce a lot of pages I close them using Ctrl+Z, which is handy / but it is very easy to also close the first page. Perhaps, if there is / only one remaining page, TDAS should ask user permission (dialog message / "Close last remaining page?", with OK-Cancel).
QA026	Pages menu – checkbox incorrectly turned off	03/08/13	Nick			With multiple pages, if you select the page you're already on, the checkbox in the menu is incorrectly turned off.
QA033	Crash in thm_load_mom	03/08/13	Aaron		Jim M	I received a crash from the load data window when loading all MOM data for all probes on 2013-03-05. / Last IDL Error: / % Array has too many elements. / % Execution halted at: XDEGAP 231 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\ssl_general\misc\xdegap.pro / % DYDT_SPIKE_TEST 97 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\ssl_general\misc\dydt_spike_test.pro / % THM_ESA_DTC4MOM 479 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\spacecraft\particles\moments\thm_esa_dtc4mom.pro / % THM_APPLY_ESA_MOM_DTC 98 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\spacecraft\particles\moments\thm_apply_esa_mom_dtc.pro / % THM_LOAD_MOM_L2 142 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\spacecraft\particles\moments\thm_load_mom_l2.pro / % THM_LOAD_MOM 587 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\spacecraft\particles\moments\thm_load_mom.pro
QA044	Tooltips needed					The following options could use tooltips describing their function: / -Bound autoscaling range (range tab) / -Log minor tick type (ticks tab) / -Save to Template / -Apply to All Panels
QA012	y axis options – set all panels	03/05/13	Eric		Nick	test 51a is supposed to apply the title/subtitle font/format/size/color options to all other panels - does not seem to work. Title/subtitle/labels not applied (by design), but should allow “set all” font/format/size/color.
QA045	Data processing – smooth data				Jim M	Block Average warns the user if the specified resolutions is shorter that the data's median cadence. It appears no similar check is done for Smooth Data.
QA050	Slice2d – new SST calibrations	03/13/13	Aaron			Attempting to create a slice using the new SST calibrations with psir data failed gracefully, as expected, however it gives the user an "unknown" error in the GUI. Neither that error nor the command line output it points to mention that the new calibrations are only valid for full and burst data (which should be what's causing the failure). (tha_psir, 2013-03-05/12:10 - 12:15, 90 sec window & step size, GSM)
QA052	Slice2d – perturbed normal vector	03/13/13	Aaron			(enhancement) Perturbing a cut's normal vector slightly off the x axis yields non-intuitive coordinates. This is because the choice of what vectors to use for the slice's x/y axes is usually determined by the projections of original coord's x axis. When the normal is set to x the slice's x/y are properly set to y/z; however, if the normal is off by a bit then then the (very small) projection will be used instead.
QA053	Slice2d – line thickness	03/13/13	Aaron			(quick enhancement) The axis and energy limit lines are drawn thicker than usual (I think the code was initially copied from thm_esa_slice2d). Drawing them with the default thickness would be consistent with the rest of the plot.
QA042	“Omni” tab almost completely cut off in load data panel	03/11/13	Jim L		Cindy	Platform dependent? (IDL 6.4, Linux)
QA014	z axis options – 'Major Ticks' sensitized when no panels added yet	03/06/13	Eric
QA045	Data processing – smooth data				Jim M	Block Average warns the user if the specified resolutions is shorter that the data's median cadence. It appears no similar check is done for Smooth Data.
QA015	xy axis options -- “equal X Y axis scaling” never sensitized?	03/07/13	Nick			Is this feature used anywhere?
QA047	Slice2d – multiple warnings	03/13/13	Aaron			When producing a plot for the default time range using peif, peir, and peib for probe B I get three error messages stating that there is no peif data in that range. There should only be one message.
QA051	Slice2d – FAC axis descriptions	03/13/13	Aaron			(enhancement) The axis descriptions for slices along field aligned coordinates could be more descriptive. Right now they only denote the coordinates used (e.g. RGEO) and whether that axis is along x/y/z. The older rotations have somewhat more descriptive annotations.
QA017	Calculate help window	03/08/13	Aaron			The help window's Done button is drawn on the top left. It would be more consistent to draw it centered at the bottom of the window. Also, the help window's examples section could use examples of: / -dimension option usage / -proper use of logical and comparative operators (e.g. "&&" and "ge")
QA018	Calculate error messages	03/08/13	Aaron		Pat	The error message printed from a mis-match of dimensions (from a median operation) is ambiguous. Many other errors from calc may be hard for the user to interpret, but this one appears to have a specific issue. Also, It would be useful for the gui to print a line numbers with the error messages.
QA038	MOM reduced – memory usage	03/11/13	Eric			The MOM reduced suite failed twice on IDL 7.1/Linux. The first time was at test 6 (f) and only gave the following error before forcing IDL to close completely: / 'Fatal error: IDL has encountered a fatal error and will now exit' / I tried starting over from scratch and it failed again, this time at test 6 (k) with the error: / 'Unable to allocate memory: to make array' -- followed immediately by the same 'Fatal error' as before. / I then switched over to Windows 7 and tried again (from the beginning) and was able to complete the test error free, but not without eating most of the systems memory. I'm thinking there may be a memory leak somewhere - getting through the suite on Windows 7 took around 9GB of RAM, which didn't get released until I completely closed IDL (note that .full_reset_session did not release the memory).
QA023	Legend options – crash changing font size	03/08/13	Aaron			I get a crash when I apply a font size change with the Apply to All Panels option on a page with two panels and two separate variables plotted on the second panel. Error message below: / Last IDL Error: / % Attempt to subscript LISTOFTRACES with I is out of range. / % Execution halted at: THM_UI_DRAW_OBJECT::ADDLEGEND 281 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\display\draw_object\thm_ui_draw_object__addlegend.pro / % THM_UI_DRAW_OBJECT::UPDATEPANELS 883 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\display\draw_object\thm_ui_draw_object__updatepanels.pro / % THM_UI_DRAW_OBJECT::UPDATE 156 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\display\draw_object\thm_ui_draw_object__update.pro / % THM_UI_LEGEND_OPTIONS_EVENT 335 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_legend_options.pro
QA022	Legend options – placement boxes	03/08/13	Aaron			a) When the placement boxes are checked the units are reset to points but the units dropdown widgets are not updated. b) Clicking apply in such cases will not set the current placement values (in points) until the text widgets are selected. (e.g. If you open the window, check left & bottom, change units to cm, uncheck then re-check left & bottom, and then click apply nothing will happen. Once you click in the text boxes the their values will be interpreted as points.)
QA048	Slice2d – smoothing	03/13/13	Aaron			(bug/enhancement) a) The smoothing option will cause "smearing" in some cases with data gaps (in this case, thb_psif 2008-02-26/04:55 +5 min, BV cut, 3d interpolation, 3 point smoothing window). I don't think this is something we can fix without replacing the smoothing function (smooth). b) I think replacing Smooth is already in order. Smooth performs a simple boxcar average across each dimension with a specified width. For 2d data that is meant for a contour plot this leads to unrealistic square artifacts in the plots, especially at lower resolutions. IDL has a built in convolution routine (convol) which would certainly be preferable if it is able to accept a large number of points. I haven't checked the documentation in detail yet but it *may* be feasible to do this for v8.
QA029	Overview plots – invalid date error re-occurred when replaying saved document	03/08/13	Jim L		Pat	Accidentally selected date 2007-01-01 first time through, error reoccurred on playback.
QA054	Calculate – adding variable twice in succession only adds it once	03/14/13	Pat			If I have one variable loaded, select the variable to add it to my calc window, then click it again to add it a second time, the variable is only added the first time. The history window does note my additional selections, just somehow, they're being ignored.
QA027	Layout options – overflowing labels	03/08/13	Eric			in test 11 (q), y axis labels from from panel 3 do run into the trace labels for panel 2 (the test says to make sure the y axis labels from panel 3 don't run into panel 2)
QA016	Markers – remove desensitized “use marker name as default” menu item	03/07/13	Aaron
QA055	Type mismatch loading TGD file (generated idl 8.2.2, loaded idl 7?)	03/15/13	Pat			When I try to run this document, I get the following error:THM_UI_READWRITE::BUILDFROMDOMELEMENT: Type mismatch: class THM_UI_PAGE_SETTINGS, attribute LEFTPRINTMARGIN, expected double, got float
QA046	Dynamic power spectra				Jim M	The dynamic power spectra produced from thb_peif_flux and thb_peif_t3 (with default settings) do not cover the entire time range of the data. Example plot attached.
QA013	legend options	03/06/13	Eric			Frame caption and variable names frames not shown, “Variables” label in bottom frame cut off on left, “Apply to All” and “Save to Template” text cut off (buttons too small). Linux specific?
QA030	Performance issue, draw window	03/08/13	Aaron			When I load an unusual amount of data (in this case all ESA, all probes, one day) the performance of the GUI is understandably slowed. Every time I move the cursor from the draw area to the rest of the GUI I get a short delay. If the cursor is quickly moved outside the GUI then the delay does not occur until the cursor re-enters the draw area. If I do this quickly enough that the tracking crosshairs remain on the current panel (quick enough that no other position events are generated) and then move the cursor back to that panel before the hourglass disappears it will create a marker from the cursor's original position to its new position.
QA039	Interpolate, tests 6 and 7	03/11/13	Cindy			Interpolating to a shorter time frame seems to do nothing. The data is not shortened or changed although a new variable is created with the correct suffix. Longer time range also does not extend the data set. Here’s where I’m confused - the instructions claim the result will have the same time range. If my range doesn’t extend what then is the point of interpolating? I asked Aaron if this was the intended functionality for this panel and he did not think so.
QA056	Memory leak when switching pages? (idl 8.2.2)	03/15/13	Nick			Happens in IDL 7.1, not 7.0.6. Not obvious where the leak is. One test that I did is having just two pages, one with three panels and / another one completely empty. When I change pages (Pages -> Page:1, / Page:2) every time I go to the page with the panels the memory usage goes / up about 50MB! If I go to the empty page, I also get an increase, but much / Smaller.
QA019	Calculate: adding variables vs. functions and operators	03/08/13	Aaron			Variables are added to the current program with the add key, however functions and operators are still added upon selection. It would be useful and more consistent to have them behave the same as variables; either with a separate "add" button or with the current button if we can reliably determine which widget was last in focus. If using the current button a label could be added at the bottom to display the current selection.
QA032	thm_load_fit, different # elements in X and Y components	03/08/13	Aaron			While loading FIT data I received errors that the following quantities could not be imported for probes A, D, & E (2013-03-05) because their X & Y components contained different numbers of elements: th?_fgs_sigma, th?_efs_sigma, th?_efs_0_dsl, th?_efs_dot0_dsl
QA021	Legend options – enable tabbing	03/08/13	Aaron			It would be convenient to have tabbing enabled (should be single keyword to top level base). Also, add status bar and slightly enlarge panel.
QA036	Legend options, units in dropdown menus	03/11/13	Aaron			Do we need different units settings for each spinner, or should we just have one units setting that applies to all. Same issue with Panel Options.
QA061	Legend options – trace dropdown	03/21/13	Eric			When the user changes panels, the traces drop-down should be populated with the traces from the selected panel. This doesn't appear to be working on Windows/IDL 7.0.6 (or Linux/IDL 7.1).
QA062	Panel options -- “Relative Vertical Size” not sensitized	03/22/13	Eric			Remove control until functionality is implemented.
QA058	ERG updates	03/19/13	Jim L		Cindy	Do we need to re-apply modifications that we made to their last version of the plugin? What has changed since last time?
QA059	IUGONET updates	03/19/13	Jim L		Cindy	Do we need to re-apply modifications that we made to their last version of the plugin? What has changed since last time?
QA060	rename terms_of_use.pro	03/21/13	Jim L			should have “spedas” prefix and be in a separate directory. Can it be extended to handle the multiple acknowledgements that IUGONET needs?
QA069	Axis options – apply all	03/25/13	Cindy			Test 48. The 'Apply to all' panels button on the title tab did not function properly. I believe we do not apply the 'apply all' to text items (like titles/labels). The message in the status bar is confusing because it says it changed, but nothing happened. Maybe the 'apply all' button in the title tab could be grayed out?
QA071	Z axis options “save to template”	03/25/13	Jim M			Z-axis opitons failed for me. QA014 is fixed. But the 'save to template' / button on the Z-axis options panel (step 25) does not work for me. It says / that a template is saved, but does not prompt for a filename or save a / file. If i save and relaod a template using the template opiton under the / file pulldown button, then everything works. / Linux, IDL 7.1
QA043	ESA extended (axis options)					Y-axis range and scaling options are copied to other panels after selecting "Apply to all Panels" despite none of the Range tab options being touched. If the current page's panels have different range and scaling options this makes the "apply to all" option largely unusable.
QA073	GUI Overview plots	03/25/13	Nick			When panels are unlocked, all panels disappear and “no room for panels” error messages is displayed. Can anything be done?
QA079	Timestamps on history and statusbar messages	03/26/13	Nick			update methods should prepend a data/timestamp
QA087	Data processing – interpolate window	03/25/13	Eric			'Quadradic' should be 'Quadratic'
QA076	Markers unintentionally created in some situations	03/26/13	Aaron			control/shift flags in info structure get “stuck” sometimes. Making data processing window modal might help. Aaron knows how to reproduce.
QA084	calculate, add button tooltip and label not cleared	03/26/13	Eric		Eric	if you click the function/operator/constants list and then click the 'insert variables' tree (but don't select a variable), the 'add' button tooltip and label aren't cleared. This creates a situation where the label and 'add' button tooltip both say 'Insert function: [function name]' but clicking the add button doesn't work
QA104	thm_crib_calc	04/01/13	Cindy			** Structure <4781038>, 3 tags, length=36, data length=36, refs=1: / TYPE STRING 'error' / NAME STRING 'Globbing variable with no match' / VALUE STRING '"?%3"' / "?%3" / % Stop encountered: $MAIN$ 116 C:\Users\clrussell\Desktop\tdas8-2\tdas_8_00\idl\themis\examples\thm_crib_calc.pro
QA105	thm_crib_calc	04/01/13	Cindy			STRING_GLOB_PREPROCESS(188): Warning: globbing used in operand variable when output variable is not a globbable / STRING_GLOB_PREPROCESS(195): Error: globbing variable has no match: "?%3" / % Stop encountered: $MAIN$ 123 C:\Users\clrussell\Desktop\tdas8-2\tdas_8_00\idl\themis\examples\thm_crib_calc.pro
QA035	Suggestion, closing pages	03/11/13	Nick			Prompt does not appear on Linux when using ctrl-Z to close last window, due to accelerator keys being handled in their own bit of code. Easy fix: duplicate code in other event handler. Possible to do a cleaner fix to avoid duplicating code?
QA094	variable options format option	03/28/13	Aaron			(minor/not OS specific) The "Format" option in the Variable Options window would be more correctly labeled "Precision".
QA066	Axis options – align ticks	03/25/13	Cindy			Error message for invalid entry disappears too quickly (overwritten by “changes applied” message) Remove “changes applied” message?
QA076	Data processing menu	03/26/13	Aaron			I noticed the right-click-menu item to bring up the data processing window reads "Data Analysis" while the GUI's main menu bar and the window itself read "Data Processing".
QA088	Possible extrapolate issue	03/27/13	Aaron			Extrapolate may not be working with the spline option 4/04/2013: Can't reproduce now.
QA096	currently selected page	03/28/13	Aaron			(enhancement) It could be useful to list the currently selected page somewhere in the main GUI window, perhaps in the window title bar.
QA092	status bar reappears if main window resized	03/28/13	Eric			Deselecting 'Status Bar' on the 'View' window gets rid of the status bar on the main window, as expected. However, if the user changes the size of the window (by clicking a corner and dragging), the status bar comes back...
QA030	Control & click flags get stuck	03/08/13	Aaron			I can now consistently reproduce QA30, which turned out not to be performance related. The "ctrl" and "click" flags in the info structure end up getting stuck at 1 in some circumstances. This causes the GUI to interpret mouse movements within a panel as a marker being drawn. Usually those flags are properly reset when the cursor leaves the GUI but for some reason they are not in this case, causing the bug to persist until an actual marker is drawn. / a) The "ctrl" flag gets stuck if the first clicks in the data processing window are ctrl-clicks. This could be cleanly fixed by making the window modal. / b) (No Repro, win 7/idl 7.0.6) The "click" flag gets stuck if you open the right click menu in the draw area then click and the drag the cursor from within the draw area to outside of it.
QA093	load data window layout	03/28/13	Aaron		Jim L	(minor) The load data window has a lot of empty space at the bottom between the "Done" button and the rest of the widgets. Jim L to verify on Mac 4/04/2013: By design, closing.
QA091	copy/paste into Word	03/28/13	Eric			When the user copy+pastes the current window into Word, the legend for each panel is copied with the trace names but without any values. It seems to me that we would want this to just copy the page with no legends.
QA074	Axis options – grid tab	03/25/13	Pat			On the grid tab, the "panel outline thickness" setting has appeared. It is a little odd for two reasons. / #1 Why isn't it on panel options? / #2 It changes the thickness of major ticks, minor ticks, & grids, in addition to panel frame thickness.(Affecting both x axis & y-axis & panel, All at the same time)
QA078	Overview plots – enable “track one panel”	03/26/13	Pat			Legends are overlapping and illegible. We used to enable “track one panel” for overview plot pages, but not happening now...needs to be restored.
QA106	Obsolete error handling in cdf_load_vars.pro	04/02/13	Aaron			I did notice that the "message" call I was dropped to at the bottom of cdf_load_vars references an obsolete system variable "!err_string". The IDL documentation claims that code using this variable will still work, but they advise against using it. I was unable to run the line in question, although I did first enter several other commands into IDL before attempting to move past it - something I did may have broken the supposed backward compatibility.
QA100	Blank plots, sst contamination	04/01/13	Aaron			1. (not platform dependent) Plots 9 and 10 come out blank. It appears the data exists but the y-axis range does not cover the data's range. Plots 11 and 12 show some data but also appear to have misaligned y-axis ranges. This may actually be an issue with the test suite itself.
QA110	thm_load_gmag dlimits	04/03/13	Pat			Should set dlim.data_att.units to 'nT' where applicable
QA097	enhancement: status bar, history window	03/28/13	Aaron			A wrapper routine with keywords for updated the status bar or history window or both would cut down on some of the repetition in the error reporting code.
QA067	Axis options – align ticks	03/25/13	Cindy			Test 20.c.d / If I use an invalid value into the Align Ticks at text box (for ex: 2007/0"ewrt5hd"3/23-00:00:00) The invalid status message is displayed and then before a user could note the error a changes applied message is displayed. This is like the one I reported at standup - the date is changed back to 2007/03/23-00:00:00, however this does more and changes the Major Ticks by Number radio button from 'Major Ticks by Number' to '2007/03/23-00:00:00'. That radio button stays at that until the panel is closed. This situation occurs only when there was an invalid entry in align ticks. This is easily repeatable.
QA103	thm_crib_eclean_subsolar, thm_crib_cleanefp	04/01/13	Eric, Cindy			Removing spikes in Ez... / % Loop limit expression too large for loop variable type. / <LONG ( 55272)>. / % Execution halted at: THM_QFIT 229 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\spacecraft\fields\LASP\thm_qfit.pro / % THM_LSP_REMOVE_SPINTONE 98 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\spacecraft\fields\LASP\thm_lsp_remove_spintone.pro / % THM_EFI_CLEAN_EFP 516 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\spacecraft\fields\LASP\thm_efi_clean_efp.pro
QA107	thm_crib_esa_slice2d assumes Windows filenames	04/02/13	Jim M			thm_crib_esa_slice2d / also worked, but generates a bunch of png files with names like this: / C:THEMIS20080226_045400thbpeib.png / It seems to be optimized for Windows, so we might want to change that.
QA102	thm_crib_gmag.pro	04/01/13	Nick			Problem when selecting a time interval: % Attempt to subscript RES with <INT ( 1)> is out / of range.
QA077	Save to template confusing	03/26/13	Jim M			Rename button or provide tooltip to explain what it does?
QA083	Calculate, spurious newline added	03/26/13	Eric		Pat	if you add something and close and then reopen calculate it adds a newline to the beginning of the program. Only happens once (so if you do it multiple times, there aren't multiple newlines added)
QA085	calculate enhancements	03/26/13	Eric		Pat	Add 'Clear' button for program / -- Add constant 'Re' for earth radius
QA086	calculate event handler	03/26/13	Eric		Pat	Edit event handler so that double click on insert function or operator listbox adds the selection to the program
QA089	Page options layout tab	03/27/13	Pat		Pat	For some reason the default left margin is displaying as: / 1.649999976158 / Not a huge deal, but it should probably default to 1.65 / (platform specific?)
QA115	possible click events bug	04/03/13	Aaron			I noticed some odd behavior in the GUI over the last day or two. Every now and then I seem to be getting "stuck" in a state where tracking is off and clicks within the draw area are not registered. I don't know how to consistently reproduce it yet, but I haven't seen this particular behavior before so I'm guessing it's related to a recent change.
QA113	Use statusbar/history wrapper in axis options code	04/03/13	Aaron			Replace simple usages that are likely to be exercised in regression testing, save more complex or hard-to-reach cases for later.
QA112	layout panel “row span” field not updated properly	04/03/13	Pat			If I create an overview plot, then open the layout panel, select panel 14(the last panel) then select delete until only panel 1 remains, I notice a few things. #1 Each time that I delete, it says that the row span=row of the panel. (This is wrong) #2 When I reach the last remaining panel(panel 1) it says the row is 1 and the row span 1. If I try to reduce the rows per page, it will only let me reduce the rows per page to 4. (Because the row span is actually 4 not 1) #3 If I close & reopen the layout panel, it correctly lists the row span as 4
QA068	Axis options – overlapping labels	03/25/13	Cindy			Test 47(abc) In the title tab when going from bottom to top in the second panel the labels overlap. This always happen with the lower panels however initially it does happen not the top panel. You can play around long enough you can get titles to overlap. This issue only occurs when the horizontal button is selected.
QA078	Data processing, cotrans	03/26/13	Aaron			When the window automatically loads state data for a coordinate transformation it leaves behind the spin_ras and spin_dec variables but no others. I don't think this is necessarily an issue rather thought it was strange as I would expect either all or no variables to be left behind.
QA063	“Last change to all panels”	03/22/13	Aaron			On hold until we figure out a minimal fix for this release Replace “Apply to all panels” in Axis Options
QA065	omni load routine	03/25/13	Eric			Needs time clipping – if you select a single day, the entire month gets loaded.
QA101	thm_crib_dproc.pro, wavelet error	04/01/13	Eric			There seems to be a problem with plotting the spectrograms of the wavelet transforms in thm_crib_dproc.pro. I get the following error at line 139: / "TPLOT(222): No valid variable names found to tplot! (use TPLOT_NAMES to display)" / and then it crashes on the next step when I try to continue: / % Variable is undefined: INPUTUNITS. / % Execution halted at: TDPWRSPC 133 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\ssl_general\misc\tdpwrspc.pro / % THM_UI_PWRSPC 47 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\thm_ui\thm_ui_pwrspc.pro / % $MAIN$ 145 C:\Users\egrimes\Desktop\space\tdas_8_00\idl\themis\examples\thm_crib_dproc.pro
QA080	Manage data, renaming variable into different branch of data tree	03/26/13	Aaron			(Manage Data) If I edit a variable (two in this case) that is in one branch of the data tree such that it falls into another already existing branch then only the changed variables will be shown in that node. The original variables show up again when the window is restarted.
QA075	Y axis options, IDL formatting codes	03/25/13	Pat			We support IDL formatting codes in our labels now. But there is no way for users to know that. We should probably have a help or examples button that briefly shows how to use it. / #3 IDL formatting codes largely make the "symbol" and "monospace symbol" fonts useless. (Well more useless, they were already pretty useless....) We should probably take them out.
QA098	sst_contamination_test failed on solaris	03/29/13	Jim M			Test 8 Failed: electron burst mask/sun / ERROR: -225 / ERROR: % Expression must be a structure in this context: DAT. / ERROR: % Execution halted at: EDIT3DBINS 33 / /home/jimm/thmsoc_sw/idl/ss / l_general/science/edit3dbins.pro / ERROR: % THM_SST_CONTAMINATION_TEST 223 / /home/jimm/thmsoc / _sw/QA_testing/thm_sst_contamination_test.pro / ERROR: % $MAIN$
QA049	Slice2d – displaced cuts, geometric mode	03/13/13	Aaron			Doesn't appear to be a bug. Displaced cuts using geometric mode often have bin boundaries that do not look possible. The plots generally match the those done with 3D interpolation so my guess is that there's a small mathematical error in the algorithm used to determine bin extent that only shows up when the slice plane does not intersect the origin.
QA077	Smoothing with no time interpolation	03/26/13	Aaron			The No Time Interpolation option for the smoothing function is very slow and will sometimes cause IDL to become non-responsive (e.g. a 28,000 sample vector takes ~2-3 minutes; for a 175,000 sample vector IDL will still be non-responsive after 30 minutes). If this is a useful feature to have the GUI we may want to add a more specific warning, perhaps even a pop-up.
QA079	Data processing, block average	03/26/13	Aaron			The Limit Time Range option in the Block Average options does not appear to do anything. Also, once implemented we should add a tooltip to the checkbox to specify whether it clips the variable or only applies an average over the specified interval (I'm guessing the latter is the intended behavior).
QA046	Dynamic power spectra				Jim M	The dynamic power spectra produced from thb_peif_flux and thb_peif_t3 (with default settings) do not cover the entire time range of the data. Example plot attached. Still some problems: Double checking QA046 and I think there might be something that isn't working right. / If I use tha_peif_flux data from 2007-03-23. There aren't enough data points with the default window/shift options, so I just get one point for the day. / If I reduce to a window of 32 points and a shift of 32 points, I get the first attached plot which is strange, but maybe not wrong? / if I use a window of 256 points and a shift of 32 points, I get a result that is definitely wrong. The second attached plot. (Dates in 1970 should not be happening. When the widget tree lists the start and stop times for the data in layout options it lists "2007-03-23/08:08:22 to 1970-01-01/00:00:00")
QA095	loaded data tree in data processing	03/28/13	Aaron		Jim L	Verified on Mac and Linux. The loaded data tree in the Data Processing window is very small (each side is maybe 60% the size of the corresponding side of the Active Data list).
QA057	file_http_copy suggestions	03/19/13	Jim L			Issues with RBSP data server – they have suggested modifications to file_http_copy, should we implement?
QA099	weird colors, thm_crib_tplot_layout	04/01/13	Eric			No repro on Windows from fresh IDL session? I made it through 'thm_crib_tplot_layout' with only one minor issue: the procedure to set the color scheme (init_crib_colors) doesn't seem to be working correctly on my machine (IDL 7.0.6/Win 7). All of the figures created by the tplot layout crib have a red background with line colors that appear to be different shades of black/grey.
QA108	draw_color_scale zrange annotations for log scaling	04/02/13	Christine G			Closing, would be hard to fix and a good workaround already exists. For small ranges only 1 annotation is shown – should display min and max values for this case.
QA117	GUI cotrans infinite loop	04/10/13	Pat			Trying to overwrite a variable using a cotrans produced an infinite loop of "warning would you link to overwrite errors" / I'm guessing it was caused by modal settings on the warning being changed. The warning popup needs to be modal. / The basic process was tha_state_pos->tha_state_pos_sse->tha_state_pos_sm->tha_state_pos_sse, I think. But I was just clicking stuff, trying to reproduce. QA081/QA02
QA081	Data processing, cotrans	03/26/13	Aaron			I received an "unexpected error" when trying to transform a variable with modified state data from GEI or DSL to SPG (did not test other starting coords). The console output is below. I'm not sure if it was related but it also appears that one of the underlying cotrans routines may be expecting to get the probe designation from the variable's name; which is probably a bad idea. / SPG2SSL(54): spacecraft has to be a, b, c, d or e (third letter of the input name) / SPG2SSL(70): SSL-->SPG / SPG2SSL(112): number of DATA records: 1440 / Traceback Report from THM_UI_COTRANS_NEW: / $MAIN$ / THM_UI_DPROC_PANEL_EVENT <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_dproc_panel.pro( 146)> / THM_UI_COTRANS_NEW <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\panels\thm_ui_cotrans_new.pro( 353)> / ERROR_MESSAGE <C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\themis\thm_ui_new\utilities\error_message.pro( 256)> / Last IDL Error: / % TRANSPOSE: Expression must be an array in this context: RM. / % Execution halted at: SPG2SSL 119 C:\Documents and Settings\aflores\Desktop\tdas_8_00\idl\ssl_general\cotrans\spg2ssl.pro / STORE_DATA(106): Deleted 3 variables
QA121	Users Guide – Eric	04/10/13			Eric	Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA122	Users Guide – Jim L	04/10/13			Jim L	Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA116	“Open Help” brings up web interface guide, should be user's guide	04/09/13	Eric
QA111	thm_map_add	04/03/13	Pat			thm_map_add.sav file not found for non-SSL users, doesn't use file_retrieve to copy it into local_data_dir Add sav file to some TDAS directory, modify thm_map_add to restore from there rather than the data directory.
QA118	file_mkdir2 error handling, if a file already exists at the specified path	04/10/13	Pat			Execution halts, rather than passing the error status back to the caller. Should be handled similarly to write permission error, which is already handled correctly.
QA124	Users Guide – Nick	04/10/13			Nick	Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA114	Move thm_fgm_fit_correlate_tplot.pro and other non-crib/utiilty code out of examples directory	04/03/13	Pat			Also whatindices.pro & whatindex.pro are support routines that are used / by recover_Vxz_mom_early_2007_crib.pro. They should be moved(maybe into / the crib?)
QA120	Users Guide – Cindy	04/10/13			Cindy	Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA126	Error handling, obsolete fonts	04/12/13	Aaron		Nick	When I load the attached .tgd file I receive an expected error (expected because the files uses a font we no longer support). The error is caught and the rest of the window not drawn. However, as soon as an options window (e.g. load data) is opened and closed I get dropped into the font object code. / In addition to ensuring that such errors are caught correctly we may want to put a check into the font code to keep the error from happening in the first place. The now-unsupported fonts are symbol and monospace symbol so I'm not sure if many users would actually run into this, but it would be a simple way to maintain backwards compatibility just in case. / Lastly, the error message that popped up when I loaded the file was not very user friendly ("THM_UI_OPEN--> Attempt to subscript FONTS with INEDEX"). This might be fixed once better error handling is in place, but if not we should see if something more useful could be output.
QA070	Y axis options – poor default tick locations	03/25/13	Pat			I think we've got some regression going on with the automatic tick selection in the y-axis. It is selecting pretty bad default tick locations.(for log axes) For example, when I plot tha_peif_en_eflux, I get sticks at 10^1.3, 10^1.95,10^2.60, 10^3.25,10^3.90
QA123	Users Guide – Jim M	04/10/13			Jim M	Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA072	GUI Overview plots	03/25/13	Nick			Can anything be done about the overlapping labels and legends? Shorten labels to make them more like the online summary plots.
QA128	Axis options control labels	04/16/13	Pat			The "format help" button should probably appear on the title tab. Right now it is only on the labels tab. / Also, in the UI the section controlling style & placement is labeled "Placement:" on the titles tab and "Style:" on the labels tab. Both sections have basically the same set of options. I would recommend the same name for both. Since there is plenty of space in the layout, "Style & Placement:" seems a good choice. Or just "Placement:"
QA129	Remove “Disable status bar” control	04/16/13	Pat			There is an option to disable the status bar. I'm not really sure why it is there at all. I could imagine that you might want to disable it to save a little space on screen. Unfortunately, when you disable it, there is just a blank space where the bar used to be.(At least on linux) And if you resize, the blank space stays. So it doesn't save you screen space.
QA130	Error with mission selection dropdown in GUI configuration options	04/17/13	Aaron		Jim L	state structure is not initialized?
QA064	CL test for file_http_copy	03/22/13	Pat			Should exercise globbing, conflicts with preexisting files or directories, missing permissions, “Load Highest Version” functionality using THEMIS, SPDF, RBSPICE, mirror sites, plus tests of more basic functionality
QA132	Axis Options min/max fields	04/17/13	Aaron			In axis options if Fixed Min/Max is not selected then the fixed min & max fields are updated to reflect the automatically chosen range when the window is opened. However, they are not updated when range options that affect the automatic range are applied(e.g. log scaling, margin). I'm not sure if they ever were updated on apply, but we should double check in case this is a regression.
QA131	Axis Options/Apply to All tooltip	04/17/13	Aaron			The Apply to All button in axis options needs its tooltip updated to reflect the current behavior.
QA133	file_http_copy, th[ade] style wildcards don't work	04/18/13	Aaron			RBSPICE fix caused a regression
QA134	Combine 2 popups when loading themis document					I think we should consider replacing the two pop-ups used when loading TGD files with a single pop-up. Right now the first question asks if the currently loaded data should be kept or deleted and the second reminds the user that all pages will be replaced and gives them an option to cancel. The functionality of both could be contained in a single Yes/No/Cancel pop-up containing the same warning and choice (e.g. "yes" to delete data, "no" to retain it, and "cancel" to not load a document). I'm guessing this is simple enough to implement for this release.
QA119	Users Guide – Aaron	04/10/13			Aaron	Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA125	Users Guide – Pat	04/10/13			Pat	Update documentation, screenshots, etc. for any visible changes you've made since TDAS 7
QA136	Error importing tplot variables	04/19/13	Aaron			I get a error when importing multiple tplot variables whose names match existing GUI variables. After clicking "Yes to All" on the prompt to overwrite the current data I get an error message that reads "THM_UI_VERIFY_DATA--> Error retrieving data for". After selecting OK the Verify Data window comes up as usual only with a blank entry at the top. When I select OK again the window crashes and brings up the help request form.
QA007	Failures in thm_spdf_cltestsuite	03/01/13	Eric			Waiting on SPDF to fix spin_cal files ;Test 3 Failed: SPDF/SPDF L1/L2 comparsion / ;ERROR: -5 / ;ERROR: % $MAIN$: SPDF L1/SPDF L2 Fail / ;ERROR: % Execution halted at: $MAIN$ 103 C:\Users\egrimes\Desktop\Space\thmsoc\trunk\QA_testing\thm_spdf_cltestsuite.pro / ;Test 4 Failed: THEMIS/THEMIS L1/L2 comparsion / ;ERROR: -5 / ;ERROR: % $MAIN$: THEMIS L1/THEMIS L2 Fail / ;ERROR: % Execution halted at: $MAIN$ 122 C:\Users\egrimes\Desktop\Space\thmsoc\trunk\QA_testing\thm_spdf_cltestsuite.pro
QA138	Missing routines, ssw/fits	04/23/13			Jim M	Missing get_pipe_filesize, hprint, repchr routines
QA140	Missing routine, SCM	04/23/13			Jim M	temp_scw_degap, used in thm_cal_scm.pro
QA144	Misplaced definition, thm_scm_modpha	04/23/13			Jim M
QA143	Missing routine, EFI	04/23/13			Jim M	notch_filter, used in thm_efi_despin.pro
QA139	Missing routine, dprint	04/23/13			Jim L	dprinttool, used in dprint.pro
QA141	Missing routine, SST	04/23/13			Pat	sst_calib_params_com, used in thm_sst_energy_cal.pro
QA146	Slight difference in FGM L1 calibrated vs. L2 data	04/23/13	Nick		Jim M	Maybe a time_clip issue, some other difference between TDAS L1 calibration and thmsoc L1->L2 processing?
QA135	Create virtual machine .sav file from tdas zip file	04/19/13				Use current zip file for dry run, will repeat with final zip file.
QA142	Misplaced definition, function_list	04/23/13			Eric	Compile before building VM .sav file Defined in mini_routines.pro, used in mini-predicates.pro, calc,pro. Also, function_list is used as a keyword argument.
QA145	Misplaced definition, aacgm_load_coef	04/23/13				ERG plugin, defined in aacgmloadcoef.pro (no underscores). DLL/DLM needed, or is IDL definition sufficient?
Compat001	Name conflict: thm_ui_new/utilities/color_bar__define.pro		Lydia/Dan Weimer			Object with same name exists in IDL 8.0+
Compat002	Name conflict: ssl_general/misc/getcolor.pro		Lydia/Dan Weimer			Two IDL demo programs define their own getcolor routine.
QA004	IDL 8.1 dprint formatting different, routine name and line number no longer on same output line as message.	1/18/2012	Aaron			Fixed by Davin's update to dprint?

## QA v8.0 Suites and Scripts
Task #	Task Description	Initial Status	Retest#1	Retest#2	Retest#3	IDL version	Operating System	Assignment	Notes

	Command-Line Test Scripts

	fac_testscript.pro	Pass				7.0.6	Windows XP	Aaron
	kyoto_load_testsuite.pro	Pass				7.0.6	Windows XP	Aaron
	mva_testscript.pro	Pass				7.0.6	Windows XP	Aaron
	rot_testscript.pro	Pass				7.0.6	Windows XP	Aaron
	slp_test.pro	Not for TDAS						Aaron
	test_cotrans.pro	Pass				7.0.6	Windows 7	Aaron
	thm_ascii_cltestsuite.pro	Pass				7.0.6	Windows 7	Cindy
	thm_asi_load_cltestsuite.pro	Pass				7.0.6	Windows XP	Aaron	3 tests ran out of memory, retest on different machine? Passes on different machine with 16 Gb RAM (Win 7, IDL 7.1)
	thm_ask_load_cltestsuite.pro	Pass				7.0.6	Windows XP	Aaron
	thm_calc_testsuite.pro	Pass				7.0.6	Windows XP	Aaron
	thm_cotrans_all_combos.pro	Pass				8.22	Windows 7	Nick	Very slow. Retest with different environment?
	thm_cotrans_cltestsuite.pro	Pass				8.22	Windows 7	Nick
	thm_cotrans_test.pro	Pass				8.22	Windows 7	Nick
	thm_dproc_cltestsuite.pro	Pass				8.22	Windows 7	Nick
	thm_dproc_fbk_testsuite.pro	Pass				8.22	Windows 7	Nick
	thm_efi_cal_cltestsuite.pro	Pass			Pass	8.22	Windows 7	Aaron
	thm_efi_cotrans_template.pro	Pass				8.22	Windows 7	Nick	Very slow on 8.2.2, OK under 8.1 and 7.1.0
	thm_efi_load_cltestsuite.pro	Pass				8.22	Windows 7	Nick
	thm_esa_cal_cltestsuite.pro	Pass				8.22	Windows 7	Nick
	thm_esa_cotrans_cltestsuite.pro	Pass				8.22	Windows 7	Nick
	thm_esa_load_cltestsuite.pro	Pass				8.22	Windows 7	Nick
	thm_fac_testscript.pro	Pass				7.0.6	Windows 7	Cindy
	thm_fbk_cal_cltestsuite.pro	Pass				7.0.6	Windows 7	Cindy
	thm_fbk_load_cltestsuite.pro	Failed	Pass			7.0.6	Windows 7	Cindy	Test 19, valid names (error in fresh session, no error if test repeated?) see qa002
	thm_fft_cal_testsuite.pro	Pass				7.0.6	Windows 7	Cindy
	thm_fft_load_cltestsuite.pro	Failed	Pass			7.0.6	Windows 7	Cindy	Test 17, valid names (error in fresh session, no error if test repeated?) see qa001
	thm_fgm_cal_cltestsuite.pro	Pass			Pass	7.0.6	Windows 7	Aaron
	thm_fgm_cotrans_template.pro	Open						Jim L	Obsolete, removed from SVN
	thm_fgm_cotrans_testsuite.pro	Pass				6.4	Linux	Jim L	No SVN reference plots
	thm_fgm_load_cltestsuite.pro	Pass				6.4	Linux	Jim L	No SVN reference plots
	thm_fit_cal_cltestsuite.pro	Failed	Pass			6.4	Linux	Jim L	See qa006 All tests failed with similar error: ;Test 0 Failed: thm_cal_fit,probe='a',datatype='efs' / ;ERROR: -163 / ;ERROR: % Subscript range values of the form low:high must be >= 0, < size, with low / ;ERROR: <= high: <No name>. / ;ERROR: % Execution halted at: THM_CAL_FIT 455 /home/jwl/tdas_8_00/idl/themis/spacecraft/fields/thm_cal_fit.pro / ;ERROR: % $MAIN$ 42 /home/jwl/tdas_8_00/QA_testing/thm_fit_cal_cltestsuite.pro
	thm_fit_cal_template.pro	Failed	Pass			6.4	Linux	Jim L	Obsolete. See qa005 THM_CAL_FIT(334): No good fit codes, assuming that E12 is used for EFS / % Variable is undefined: NE34. / % Execution halted at: THM_CAL_FIT 355 / /home/jwl/tdas_8_00/idl/themis/spacecraft/fields/thm_cal_fit.pro / % $MAIN$ 51 / /home/jwl/tdas_8_00/QA_testing/thm_fit_cal_template.pro
	thm_fit_cotrans_cltestsuite.pro	Failed	Pass			6.4	Linux	Jim L	See qa005 THM_CAL_FIT(334): No good fit codes, assuming that E12 is used for EFS % Variable is undefined: NE34. % Execution halted at: THM_CAL_FIT 355 /home/jwl/tdas_8_00/idl/themis/spacecraft/fields/thm_cal_fit.pro % $MAIN$ 51 /home/jwl/tdas_8_00/QA_testing/thm_fit_cal_template.pro
	thm_fit_load_cltestsuite.pro	Pass				6.4	Linux	Jim L
	thm_gmag_load_cltestsuite.pro	Failed	Pass	Pass		8.1	Linux	Jim L	Test 22 failed (test DTU sites)
	thm_lasp_cltestsuite.pro	Pass				8.1	Linux	Jim M
	thm_mirror_cltestsuite.pro	Failed		Pass	Pass	8.1	Linux	Nick	SPDF test failed (URL changes?)
	thm_mom_cal_template.pro	Not for TDAS						Jim M
	thm_mom_cotrans_cltestsuite.pro	Failed				8.1	Linux	Jim M	Script is obsolete, needs total rewrite. (QA010)
	thm_mom_load_cltestsuite.pro	Pass				8.1	Linux	Jim M
	thm_mouse_testsuite.pro	Pass				7.0.6	Windows XP	Aaron
	thm_neutral_sheet_cltestscript.pro	Pass				7.0.6	Windows XP	Aaron	Passes after script editing. No comparison plots?
	thm_overplot_testsuite.pro	Pass				7.0.6	Windows 7	Cindy
	thm_part_getspec_testscript.pro	Pass				6.4	Linux	Jim L	Switching to another virtual desktop results in corrupted PNGs (plot windows are iconified), retest worked when staying on same desktop.
	thm_part_moments_cltestsuite.pro	Pass				8.1	Linux	Jim M
	thm_plot_options_testsuite.pro	Pass				7.1	Windows 7	Eric	No SVN reference plots
	thm_plotxy_testsuite.pro	Pass				7.1	Windows 7	Eric	No SVN reference plots
	thm_plotxyz_testsuite.pro	Pass				8.22	Windows 7	Nick
	thm_scm_cal_cltestsuite.pro	Pass				8.22	Windows 7	Nick
	thm_scm_cotrans_cltestsuite.pro	Pass				7.0.6	Windows XP	Aaron
	thm_scm_dproc_cltestsuite.pro	Pass				7.1	Windows 7	Eric
	thm_scm_load_cltestsuite.pro	Pass				7.1	Windows 7	Eric
	thm_slice2d_cltestsuite.pro	Failed	Pass			7.1	Windows 7	Eric	See qa003, qa004 Blank plots for tests 1-10, test 11 failed (multiple distributions) ESA worked, SST failed
Obsolete	thm_spdf_cltestsuite.pro	Failed				7.1	Windows 7	Eric	See qa007 Tests 3 (SPDF L1/SPDF L2) and 4 (THEMIS L1/THEMIS L2) failed
	thm_specplot_cltestsuite.pro	Pass				7.1	Windows 7	Eric
	thm_sst_contamination_test.pro	Pass		Pass		7.1	Windows 7	Jim L	plots differed, but look reasonable, SVN reference plots out of date?
	thm_sst_load_cltestsuite.pro	Pass				7.1	Windows 7	Eric
	thm_state_load_cltestsuite.pro	Pass				7.1	Windows 7	Eric	Test 14 commented out?
	thm_tplotxy_testsuite.pro	Pass				7.1	Windows 7	Eric
	thm_trg_load_cltestsuite.pro	Pass				7.1	Windows 7	Eric
	thm_tsy_cltestsuite.pro	Pass				7.1	Windows 7	Eric
	thm_ttrace_cltestsuite.pro	Pass				7.1	Windows 7	Eric

	GUI Test Suites

	gui_tplot	Pass				7.0.6	Windows XP	Aaron	Rename script or update spreadsheet?
	nudge	Pass				7.0.6	Windows 7	Cindy
	Data Processing	Failed	Some issues	Pass		8.22,7.06	Linux, Win XP	Aaron	QA028 (load sun/moon data failed when replaying themis document)
	layout options	Minor issue						Eric	QA027 (overflowing labels)
	line options	Pass				6.4	Linux	Jim L
	Axis Options (X axis only)	Pass	Some issues	Pass		7.1	Linux	Nick	QA015 (equal X Y axis scaling never sensitized)
	Axis Options (Y axis only)	Pass	Some issues	Issues	Pass	7.1	Windows 7	Nick	QA127 - “apply” affects multiple panels
	markers	Pass				7.0.6	Windows XP	Aaron	QA016 – unreachable menu item for markers, QA024
	panel Options	Pass				7.0.6	Windows 7	Cindy
	rubberband	Pass				8.22	Windows 7	Nick
	variable options	Pass				7.1	Linux	Eric
	legend options	Failed	Pass			7.1,6.4	Linux,Linux	Jim L	QA013: there seems to be some issues with the frames on the right hand side of the window. (platform dependent?) Also QA021, QA022, QA023
	Calculate	Some issues	Pass	Pass	Pass			Eric (VM version)	QA017, QA018, QA019, QA020
	part getspec	Pass				7.0.6	Windows 7	Cindy
	save data as	Pass				8.22	Windows 7	Nick
	Export to Image	Pass				7.1	Linux	Eric
	Save Open	Pass				6.4	Linux	Jim L
	page options	Pass				8.22	Windows 7	Nick
	z axis	Pass				7.1	Linux	Jim M	QA014 – 'Major ticks' sensitized when no panels added yet
	load themis data	Failed	Pass			7.0.6,8.22	Windows XP, Win 7	Nick	Issues loading fit (QA032) and mom (QA033)
	pulldown menus	Pass		Minor issue	Pass	6.4	Linux	Jim L	QA129 “Disable status bar” useless
	toolbar	Pass				8.22	Windows 7	Nick
	pages	Pass				7.1	Linux	Eric
	ESA Full Suite	Failed	Some issues	Pass	Pass	7.0.6	Windows XP	Aaron (VM)	QA043, QA044, QA045, QA046
	FGM Full Suite	Pass				7.0.6	Windows 7	Cindy
	GMAG Full Suite	Pass		Pass		8.22	Linux	Cindy	Minor issue with labels (QA037)
	ASK Reduced Suite	Pass				8.22	Windows 7	Nick
	SST Reduced Suite	Pass				7.0.6	Windows 7	Cindy
	SCM Reduced Suite	Pass						Nick
	FIT Reduced Suite	Pass				7.1	Linux	Eric
	MOM Reduced Suite	Failed	Pass			7.1	Linux	Eric	Excessive memory usage (QA038)
	EFI Reduced Suite	Pass				7.1	Linux	Eric
	FFT Reduced Suite	Pass						Nick
	STATE Reduced Suite	Pass				7.1	Linux	Eric
	Slices Suite	Minor issues						Aaron	QA047-QA053
	thm_ui_journal_history_help	Pass				7.0.6	Windows 7	Cindy	No error message for invalid filename characters, but it was clear that the file was not created. Update instructions? Confirmed platform dependent, works on Linux.
	thm_ui_interpolate	Failed	extrapolate splines	Pass				Nick (IDL 8.2.2)	QA039, QA040
	thm_ui_dproc_power_spectra	Failed	Pass			8.22,7.1	Windows 7, Win 7	Eric	QA041
	thm_ui_overview_plots	Failed	Pass			8.22	Windows 7	Nick	QA025 – crash in calendar widget, QA029 – error reoccurred replaying themis document
	thm_ui_graphic_rendering	Pass				8.22	Windows 7	Nick
	thm_ui_horizontal_bar	Pass				7.1	Linux	Eric
	thm_ui_error_message.txt	Pass						Jim L
	thm_ui_fileconfig.txt	Pass						Jim L
	thm_ui_load_cdf_ascii.txt	Pass						Cindy
	thm_ui_tplot_manage_data.txt	Failed	Pass		Pass			Nick	QA136, problem importing multiple variables if they already exist in GUI

	Platform Compatibility Tests

	GUI rubberband (Mac)	Pass						Aaron
	GUI rubberband (Solaris)	Pass						Jim M
	GUI thm_ui_interpolate (IDL 7.1)	Memory usage > 5 GB, fails						Eric
	GUI thm_ui_interpolate (IDL 7.0.6)	Pass						Eric
	GUI Pulldown menus (Windows)	A few minor issues						Pat
	GUI Pulldown menus (Mac)	Pass						Cindy
	GUI Pulldown menus (Solaris)	Pass						Jim M
	thm_cotrans_all_combos (IDL 8.1 or below)	Pass						Pat
	thm_cotrans_all_combos (IDL 8.2.2)	Pass (time?)						Pat
	thm_fgm cal_cltestsuite (IDL 8.1)	8 mins	8 min					Nick
	thm_fgm cal_cltestsuite (IDL 8.2.2)	5+hours	1 hour					Nick
	thm_efi cal_cltestsuite (IDL 8.1)	16 mins	22 min					Nick
	thm_efi cal_cltestsuite (IDL 8.2.2)	6 hours	90 min					Nick
	thm_sst_contamination_test (Solaris)	Failed						Jim L	QA098
	thm_sst_contamination_test (Mac)	Blank plots						Aaron
	thm_asi_load_cltestsuite (Mac)	Pass (no memory error!)						Aaron
	thm_asi_load_cltestsuite (Solaris)	Out of memory						Jim M

	Crib sheets/examples

	ssl_general/examples:

	thm_crib_tplot_annotation.pro	color map issue						Jim L
	thm_crib_tplot_export_print.pro	Pass						Cindy
	thm_crib_tplot_layout.pro	color map issue						Eric	QA099
	thm_crib_tplot.pro (Windows)			Pass				Nick
	thm_crib_tplot.pro (Linux)	color map issue		Pass				Jim L
	thm_crib_tplot_range.pro	color map issue						Eric
	time_correlate_crib.pro	Pass						Nick

	themis/examples:

	crib_lshell.pro	Pass						Aaron
	fac_crib.pro	Pass						Aaron	after L2 data specified in fgm load calls
	mva_crib.pro	Pass						Aaron	after L2 data specified in fgm load calls
	recover_Vxz_mom_early2007_crib.pro	Pass						Aaron
	rxy_crib.pro	Pass						Aaron	after L2 data specified in fgm load calls
	sse_crib.pro	Pass						Cindy
	thm_crib_asi.pro	Pass						Cindy
	thm_crib_calc.pro	Pass						Cindy
	thm_crib_cleanefp.pro	Failed						Cindy	QA103
	thm_crib_cleanefw.pro	Pass						Cindy
	thm_crib_cotrans_lmn.pro	Pass						Eric
	thm_crib_cotrans.pro	Pass						Eric
	thm_crib_dproc.pro	wavelet issue		Pass				Eric	QA101
	thm_crib_eclean_subsolar.pro	Failed		Pass				Aaron	QA103
	thm_crib_efi_cal.pro	Pass						Eric
	thm_crib_efi.pro	Pass						Jim L
	thm_crib_esa_bgnd_remove.pro	Pass						Jim L
	thm_crib_esa_da.pro	Pass						Jim L
	thm_crib_esa_extrapolation.pro	Pass						Jim L
	thm_crib_esa_moments.pro	Pass						Jim L
	thm_crib_esa_read_gmoms.pro	Pass						Aaron	obsolete error reporting code in cdf_load_vars
	thm_crib_esa_slice2d.pro	Pass						Eric
	thm_crib_export.pro	Pass						Nick
	thm_crib_fac.pro	Pass						Pat
	thm_crib_fbk.pro	Pass						Eric
	thm_crib_fft.pro	Pass						Nick
	thm_crib_fgm.pro	Pass (slow on 8.2.2)						Nick
	thm_crib_fit.pro	Pass						Nick
	thm_crib_gmag.pro	Failed		Pass				Aaron	QA0102
	thm_crib_greenland_gmag.pro	Pass						Nick
	thm_crib_maccs_gmag.pro	Pass						Pat
	thm_crib_make_ae.pro	Pass						Pat
	thm_crib_mom_dead_time_correct.pro	Pass						Pat
	thm_crib_mom.pro	Pass						Pat
	thm_crib_mva.pro	Pass						Pat
	thm_crib_neutral_sheet.pro	Pass						Eric	neutral sheet models need explicit compilation
	thm_crib_overplot.pro	Pass						Eric
	thm_crib_part_getspec.pro	Pass						Eric
	thm_crib_part_slice2d.pro	Pass						Nick
	thm_crib_plotxy.pro	Pass						Nick
	thm_crib_plotxyvec.pro	Pass						Nick
	thm_crib_plotxyz.pro	Pass						Jim L
	thm_crib_poynting_flux.pro	Pass						Jim L
	thm_crib_read_write_ascii_cmdline.pro	Pass						Jim L
	thm_crib_scm.pro	Possible issue?		Pass				Jim M	The plot for the diagnostic parameter 'thd_scp_iano' is empty on the second figure produced, not sure if there's supposed to be something there.
	thm_crib_scpot2dens.pro	Pass						Eric
	thm_crib_slp_sse.pro	Pass						Eric
	thm_crib_spinfit.pro	Pass						Nick
	thm_crib_sst_calibration.pro	Pass						Nick
	thm_crib_sst_contamination.pro	Pass						Nick
	thm_crib_sst_extrapolation.pro	Pass						Pat
	thm_crib_sst.pro	Pass						Nick
	thm_crib_sst_set_calibrations.pro	Pass						Pat
	thm_crib_state.pro	Pass						Cindy
	thm_crib_superpo_interpol_histo.pro	Pass						Cindy
	thm_crib_tplot_overlay.pro	Pass						Cindy
	thm_crib_tplotxy.pro	Pass						Eric
	thm_crib_trace.pro	Pass						Eric
	thm_crib_twavpol.pro	Pass						Eric
	thm_crib_validate_high_freq_using_phase.pro	Pass						Pat
	thm_fgm_fit_correlate_tplot.pro	not a crib						Pat
	thm_map_examples.pro	Obsolete						Pat	can't find .sav files
	thm_script_fgm.pro	Pass						Jim L
	twavpol_scm_crib.pro	Pass						Jim L

	Tests for external/contributed code

	erg_gmag_mm2120_load_cltestsuite, erg_gmag_nipr_load_cltestsuite

## QA Suites and Scripts Template
Task #	Task Description	Initial Status	IDL version	Operating System	Notes		A	N	C	JL	JM	P	E			Assignment

	Platform Availability
	Mac Leopard: Jim L, Cindy
	Mac Snow Leopard:
	Mac Lion: ?(UCLA)

	Windows XP: Aaron
	Windows 7: Jim M, Nick, Jim L, Eric?

	Linux: Pat, Nick, Jim L, Eric?
	Unix: Jim M

	Command-Line Test Scripts

	fac_testscript.pro	Open					1
	kyoto_load_testsuite.pro	Open					1
	mva_testscript.pro	Open					1
	rot_testscript.pro	Open					1
	slp_test.pro	Not for TDAS					1
	test_cotrans.pro	Open					1
	thm_ascii_cltestsuite.pro	Open					1
	thm_asi_load_cltestsuite.pro	Open					1
	thm_ask_load_cltestsuite.pro	Open					1
	thm_calc_testsuite.pro	Open					1
	thm_cotrans_all_combos.pro	Open						1
	thm_cotrans_cltestsuite.pro	Open						1
	thm_cotrans_test.pro	Open						1
	thm_dproc_cltestsuite.pro	Open						1
	thm_dproc_fbk_testsuite.pro	Open						1
	thm_efi_cal_cltestsuite.pro	Open						1
	thm_efi_cotrans_template.pro	Open						1
	thm_efi_load_cltestsuite.pro	Open						1
	thm_esa_cal_cltestsuite.pro	Open						1
	thm_esa_cotrans_cltestsuite.pro	Open						1
	thm_esa_load_cltestsuite.pro	Open						1
	thm_fac_testscript.pro	Open							1
	thm_fbk_cal_cltestsuite.pro	Open							1
	thm_fbk_load_cltestsuite.pro	Open							1
	thm_fft_cal_testsuite.pro	Open							1
	thm_fft_load_cltestsuite.pro	Open							1
	thm_fgm_cal_cltestsuite.pro	Open							1
	thm_fgm_cotrans_testsuite.pro	Open								1
	thm_fgm_load_cltestsuite.pro	Open								1
	thm_fit_cal_cltestsuite.pro	Open								1
	thm_fit_cal_template.pro	Obsolete								1
	thm_fit_cotrans_cltestsuite.pro	Open								1
	thm_fit_load_cltestsuite.pro	Open								1
	thm_gmag_load_cltestsuite.pro	Open									1
	thm_lasp_cltestsuite.pro	Open									1
	thm_mirror_cltestsuite.pro	Open									1
	thm_mom_cal_template.pro	Not for TDAS									1
	thm_mom_cotrans_cltestsuite.pro	Obsolete									1
	thm_mom_load_cltestsuite.pro	Open									1
	thm_mouse_testsuite.pro	Open										1
	thm_neutral_sheet_cltestscript.pro	Open										1
	thm_overplot_testsuite.pro	Open										1
	thm_part_getspec_testscript.pro	Open										1
	thm_part_moments_cltestsuite.pro	Open										1
	thm_plot_options_testsuite.pro	Open										1
	thm_plotxy_testsuite.pro	Open										1
	thm_plotxyz_testsuite.pro	Open										1
	thm_scm_cal_cltestsuite.pro	Open										1
	thm_scm_cotrans_cltestsuite.pro	Open										1
	thm_scm_dproc_cltestsuite.pro	Open											1
	thm_scm_load_cltestsuite.pro	Open											1
	thm_slice2d_cltestsuite.pro	Open											1
	thm_spdf_cltestsuite.pro	Open											1
	thm_specplot_cltestsuite.pro	Open											1
	thm_sst_contamination_test.pro	Open											1
	thm_sst_load_cltestsuite.pro	Open											1
	thm_state_load_cltestsuite.pro	Open											1
	thm_tplotxy_testsuite.pro	Open											1
	thm_trg_load_cltestsuite.pro	Open											1
	thm_tsy_cltestsuite.pro	Open											1
	thm_ttrace_cltestsuite.pro	Open											1

							10	11	6	6	6	10	12

							A	N	C	JL	JM	P	E
	GUI Test Suites						8	6	3	4	5	4	2

	gui_tplot	Open					1
	nudge	Open									1
	Data Processing	Open							1
	layout options	Open					1
	line options	Open										1
	Axis Options (X axis only)	Open
	Axis Options (Y axis only)	Open							1
	markers	Open								1
	panel Options	Open							1
	rubberband	Open								1
	variable options	Open					1
	legend options	Open
	Calculate	Open											1
	part getspec	Open					1
	save data as	Open						1
	Export to Image	Open								1
	Save Open	Open						1
	page options	Open						1
	z axis	Open										1
	load themis data	Open						1
	pulldown menus	Open					1
	toolbar	Open						1
	pages	Open						1
	ESA Full Suite	Open								1
	FGM Full Suite	Open										1
	GMAG Full Suite	Open					1
	ASK Reduced Suite	Open									1
	SST Reduced Suite	Open									1
	SCM Reduced Suite	Open									1
	FIT Reduced Suite	Open					1
	MOM Reduced Suite	Open									1
	EFI Reduced Suite	Open											1
	FFT Reduced Suite	Open										1
	STATE Reduced Suite	Open
	Slices Suite	Open					1
	thm_ui_journal_history_help	Open
	thm_ui_interpolate	Open
	thm_ui_dproc_power_spectra	Open
	thm_ui_overview_plots	Open
	thm_ui_graphic_rendering	Open
	thm_ui_horizontal_bar	Open

	Tests for external/contributed code

	erg_gmag_mm2120_load_cltestsuite, erg_gmag_nipr_load_cltestsuite