## Themis Safety Action-Issue List
Issue or Action Number | Status | Date Opened | Sub-System | Must Be Resolved By | Originator | Issue or Action | Who is to Take Action | Comment or Resolution Date | Comment or Resolution
3 | Open | 2004-06-02 | EWR127-1 | 7/28/2004 9/29/2004 | Jamie Burget | #56 - Propellant Off Loading questions. | Safety Meeting |  | Will be discussed with Boeing at the MIWG on 8/31/4. In addition Tom will coordinate feedback from the Range on Michael McCullough's document.
7 | Open | 2004-08-12 | EWR127-1 | 2004-10-29 | SWG | KSC feedback on EWR127-1 Tailoring Sheets to Jamie Harper. | Tom Palo |  | Revised Action item.
7 | Open | 2004-08-12 | EWR127-1 | 2004-11-05 | SWG | KSC feedback onEWR127-1 Tailoring sheets from Jamie Harper to UCB. | Jamie Harper |  | Revised Action item.
12 | Open | 2004-06-17 | Schedule | 2004-11-10 | David King | Complete Mission Schedule Task List | Tim Keepers
16 | Open | 2004-06-23 | RCS | 2004-09-29 | SWG | Review Pyro Category Classification and documentation involved. | Jamie Harper |  | Tom Palo's feedback on the Pyro Category classification needed. Also, Jeff Wethern will get back to the SWG if Themis can increase the pressurant level. 8/25/4 - Jamie Harper will develop a technical memo to address more specifically why the pyro should have a 'B' classification.
18 | Open | 2004-08-12 | Lithium Ion Battery | 2004-10-31 | SWG | Distribute Battery Hazard Analysis Report from Battery Vendor. Review latest information with SWG. | David King
23 | Open | 2004-07-07 | MSPSP | 2004-09-15 | SWG | Determine delivery dates for MSPSP versions, Material Assessment Report and other SMAO deliverables. | SWG
26 | Open | 2004-09-08 | Materials Assessment Report | 2004-09-29 | SWG | Sort out the impact to Themis of this report with KSC. | John Thurber
27 | Open | 2004-09-08 | Fairing Doors | 2004-10-06 | SWG | Sort out with KSC the number of fairing doors. | Jamie Harper
1 | Closed | 2004-06-02 | EWR127-1 | 2004-07-28 | Jamie Burget | #22 - Leak Checking at the Range | SWG | 6/23/2004 6/30/2004 7/7/2004 | Tim will revise and submit to the SWG. Document distributed for review. So far no problems seen with the submitted tailoring. Will review again with KSC and the Range. Rescheduled to 7/21/4. Due to missing SWG members was rescheduled to 7/28/4. Closed 8/12/4.
2 | Closed | 2004-06-02 | EWR127-1 | 2004-06-11 | Jamie Burget | #52,53 - Add Battery Testing Plan reference to sheets. | Tim Keepers | 2004-06-08
4 | Closed | 2004-06-08 | EWR127-1 | 2004-06-23 | Jamie Burget | #46 - Safe and Arm | Tim Keepers | 2004-06-09 | As per SWG should be n/a or tailored out.
5 | Closed | 2004-06-08 | SSPP | 2004-06-30 | Jamie Harper | Section 4.1 - Deliverable Data. RF Safety Interlock Test Plan and Results needed. | SWG |  | Will be removed with the next release.
6 | Closed | 2004-06-17 | EWR127-1 | 2004-06-23 | SWG | Provide link to Astrotech's "Facility Safety Manual". | Tom Palo | 2004-06-21
8 | Closed | 2004-06-17 | MSPSP | 2004-06-30 | SWG | Tom and Jamie Harper to sort out differences between the three installment approach and two installment approach. | Jamie Harper Tom Palo | 2004-06-30 | KSC and the Range will let GSFC know if there is anything that needs to be added to the Initial Themis MSPSP and whether the dates for the MSPSP Draft (launch - 12 months) and Final (Payload Shipment - 120 days) are acceptable such that Themis is not at any undue risk.
10 | Closed | 2004-06-17 | Fuel Off-load | 2004-08-04 | SWG | Tom will talk to Boeing and see where they are with they are with this issue. He and Jamie Harper will review this information and report to the SWG. | Jamie Harper Tom Palo |  | See #3.
11 | Closed | 2004-06-17 | EWR127-1 | 2004-07-09 | David King | Submit Sections 1 and 6 for pre-review | Tim Keepers | 2004-07-09
13 | Closed | 2004-06-23 | GOWIG | 2004-06-30 | Marc Kaylor | When will the GOWG be held. | Tom Palo | 2004-06-30 | GOWG will be 8/31/4 Huntington Beach.
14 | Closed | 2004-06-23 | KSC Safety | 2004-06-30 | SWG | Email KSC Safety Presentation to SWG. | Tom Palo | 2004-06-30 | Presentation distributed.
15 | Closed | 2004-06-23 | Astrotech | 2004-06-30 | SWG | Review understanding from last week's meeting. | SWG | 2004-06-30
17 | Closed | 2004-06-30 | SMAO | 2004-08-18 | SWG | A review of the SMAO presentation will be held at the 8/18/4 SWG Meeting. | Tom Palo |  | 7/23/4 - Reschedule on 8/4/4.
19 | Closed | 2004-07-07 | EWR127-1 | 2004-07-21 | SWG | Review AFSPCMAN 91-710 impact to Themis. | SWG |  | No Impact to Themis. Themis will still use EWR127-1.
20 | Closed | 2004-07-07 | EWR127-1 | 2004-07-28 | SWG | Preview on Section 1 and 6 complete. | Jamie Burget Tim Keepers | 2004-08-02
20 | Closed | 2004-07-07 | EWR127-1 | 2004-08-18 | SWG | KSC feedback on Section 1 and 6 to Jamie Harper. | Tom Palo |  | See revised Issue #7
20 | Closed | 2004-07-07 | EWR127-1 | 2004-08-25 | SWG | KSC feedback on Section 1 and 6 from Jamie Harper to UCB. | Jamie Harper |  | See revised Issue #7
21 | Closed | 2004-08-18 | Materials Assessment Report | 2004-08-25 | SWG | Send out examples of this report | Tom Palo
22 | Closed | 2004-07-07 | MSPSP | 2004-09-15 | SWG | Feedback on delivering selected sections early. | David King Tim Keepers
24 | Closed | 2004-09-08 | EWR127-1 | 2004-09-15 | SWG | Remind Garrett to send Set 2 (Sections 1 and 6) of the EWR127-1 to Tom Palo. | John Thurber
25 | Closed | 2004-09-08 | SSPP | 2004-09-29 | SWG | GSFC to get Approval of the SSPP from KSC and the Range. | John Thurber Jamie Harper