## Themis Action-Issue List
Document on Themis UCB FTP site: \1 Management\1.1 Management\1.1.14 Issues and Action Lists\UCB - Swales Issues and Action Lists\Issues and Action List - Swales and UCB.xls
Issue or Action Number | Status | Date Opened | Sub-System | Must Be Resolved By | Originator | Issue or Action | Who is to Take Action | Comment or Resolution Date | Comment or Resolution
1 | Closed | 2004-03-24 | Instruments | 2004-04-21 | Paul Turin | Vibration Test Level Analysis | Terry Sharton Rob Eppler | 2004-04-09 | Per Paul Turin need by the 14th, now slipping to the 16th of April.
[8 empty] | 2004-04-13 | Will be sent to Paul by EOB on the 14th.
[8 empty] | 2004-04-15 | Due to other events the need date has slipped to 4/21 as per Paul.
[8 empty] | 2004-04-21 | Email from Rob: new expected date is eob 4/26.
[8 empty] | 2004-04-26 | Closed
2 | Closed | 2004-03-30 | Mass | 2004-06-11 | Vassilis Angelopoulos | Mass Reduction Analysis Radiation Thinning (BAU) | Michael Cully |  | Awaiting more radiation analysis info from GSFC. This is dependent upon GSFC Radiation Analysis Schedule. GDDS has identified at the BAU Peer Review at least 50 mil reduction of wall thickness. Date will need to be revised. based on GSFC delivery of Radiation Analysis and cycle time at GDDS.
[8 empty] | 2004-05-17 | Rescheduled from 5/10/4 to 5/21/4.
[8 empty] | 2204-05-24 | As stated at the 5/17/2004 Weekly meeting the addition of the third Power Module will more than likely off set any envision savings in wall thickness. A preliminary updated Ray Trace analysis was completed May 19th. Final Report anticipated to be delivered Tuesday the 5/25. This will be forward to GDDS for an assessment. Awaiting cycle time from GDDS.
[8 empty] | 2004-06-03 | Rescheduled from 5/28/4 to 6/111/4.
[8 empty] | 2003-06-04 | Vassilis: The actual mass benefits have not yet been shown and they would be good to show as we are very sensitive to dry mass from the new deltaV forward runs.
[8 empty] | 2004-06-21 | See Status from CDR Electrical Systems presentation on Mass & Power BAU. Reduction in Wall thickness based on latest Radiation Analysis results. Relevant Vugraphs attached.,
3 | Withdrawn
4 | Closed | 2004-03-30 | Mass | 2004-05-10 | Michael Cully | Mass Reduction Analysis Battery Bulkhead Optimization | Michael Cully | 2004-05-05 | In discussions with AEA Technology at KO meeting the weight savings would be minimal due to the large percentage of mass being attributed to cells. Also they have not used magnesium before and this change poses schedule and cost impacts. This should be closed.
5 | Closed | 2004-03-30 | LV | 2004-06-30 | Vassilis Angelopoulos | More mass from the Launch Vehicle | Vassilis Angelopoulos | 2004-05-21 | No more mass savings expected.
7 | Closed | 2004-03-30 | FTP Site | 5/28/2004 6/11/2004 | David King | Swales to organize their FTP site as UCB's new FTP Site (WBS format). PhasC_CDR Peer Review Presentations to be set-up. | Joe Procaccino | 2004-06-01 | Date revised due to Joe P. out of Office
[8 empty] | 2004-06-07 | Folders set-up.
| Closed |  |  | 6/11/2004 7/2/2004 | David King | Other technical documents to be moved to the new folder structure. | Joe Procaccino Michael Cully | 2004-06-21 | Joe will check with Michael to get ICD's and other technical documents out on the site. Date Revised to 7/2/4.
|  |  |  | 2004-08-20 |  |  | Joe Procaccino | 2004-07-30 | Rescheduled to 8/20/4
8 | Closed | 2004-03-30 | BAU, IDPU, Instruments | 4/12/2006 4/14/2004 | David King | Prepare Fact Sheet on ACTEL Processors used. ACTEL to be at UCB on 4/16. | Michael Cully Ron Jackson | 2004-04-13 | Should be for ones that failed and those that were good. Michael to get Ron the GDDS info by 4/12. Only part # available from Swales.
9 | Closed | 2004-03-30 | BAU FSW | 2004-04-30 | David King | Review list of known bugs in commercial operating system to be used | David King | 2004-04-30 | During the Flight Software Review
10 | Closed | 2004-04-02 | Harness | 2004-04-02 | Paul Turin | New Harness diagrams to Swales | Ellen Taylor Paul Turin | 2004-04-02 | Paul emailed Rob info.
11 | Closed | 2004-04-02 | Harness | 2004-05-03 | Paul Turin | Harness ICD to Swales | Ellen Taylor | 2004-05-06 | Harness document sent.
12 | Closed | 2004-04-02 | Harness | 2004-05-07 | Paul Turin | List of updated lengths from Swales | Rob Eppler | 2004-05-17 | Awaiting Ellen's feedback if this can be closed.
13 | Closed Re-opened Closed Re-opened Closed | 4/2/2004 4/23/2004 5/20/2004 6/11/2004 | COMM | 2004-04-02 | Manfred Bester | NTIA info needed from Swales/L3COMM | Michael Cully | 2004-04-09 | Re-opened on 4/23/4. Manfred needs one more number from L3-COMM. L#-Com sent out information on 4/29/2004 which should have addressed all remaining data deficiencies.
[8 empty] | 2004-05-06 | As per Manfred: t would be fine to obtain PCM/PSK/PM RF spectra from a transponder that has a 1.7 MHz subcarrier, as long as the six data rates are identical to those that are used with THEMIS and the modulation index is adjusted to 1.6 rad.
[8 empty] | 2004-05-07 | Needed: A full calculated spectrum plot for each data rate, not just a few numbers. The latter is what has been provided so far on the NTIA form from L3-COMM.
[8 empty] | 2004-05-07 | Manfred had a phone conversation with L3-COMM and they said they would supply plots shortly.
[8 empty] | 2004-05-14 | L3-plots do not make sense.
[8 empty] | 2004-05-17 | Needed clarification given to NTIA.
[8 empty] | 2004-05-20 | Paper work to be completed by ITT by 5/21/4 and submitted to GSFC Spectrum Manager and then on to NTIA.
[8 empty] | 2004-06-01 | ITT not understanding L3-Comm data.
[8 empty] | 2004-06-03 | ITT going to check if they can proceed for License without add'l L3-COM data. L3-COM to provide add'l data after their CDR.
[8 empty] | 2004-06-10 | ITT going to forward to GSFC today.
14 | Closed | 2004-04-12 | Magnetics | 2004-04-16 | Ellen Taylor | Write-up on the AEAT Magnetics Plan | Tom Ajluni | 2004-04-22
15 | Closed | 2004-04-13 | CDRL's | 2004-04-23 | David King | Swales to deliver to UCB the following CDRL's: | Michael Cully | 2004-04-30 | Resubmitted documents with CM numbers to UCB on 4/23/04, 4/28/04, 5/03/04. Documents to be shipped out the week of 5/10-5/14/4.
SSPP - Draft
PRA - Preliminary
FTA - Preliminary
PHA - Preliminary
16 | Closed | 2004-04-15 | ICD | 2004-05-01 | Rob Eppler | Feedback on Instrument to Bus ICD's | Paul Turin | 2004-05-04
17 | Closed | 2004-04-16 | BAU | 2004-05-07 | David King | BAU Schedule Analysis Review | Prushina Patel
18 | Closed | 2004-04-23 | Documents | 2004-05-14 | Ellen Taylor | Swales to provide document status list on UCB Themis FTP site. | Michael Cully | 2004-05-21 | Provided with Monthly 5/21/04. This Action Item is closed.
19 | Closed | 2004-04-23 | Documents | 2004-04-30 | David King | Swales to provide the following documents for IV&V: | Michael Cully | 2005-05-04
[6 empty] | SAI-SPEC-1142; THEMIS-BSW-SRS |  |  | Preliminary Copy 5/04/2004. Will be released at CDR
20 | Closed | 2004-05-03 | Safety | 2004-05-20 | David King | Swales Feedback to UCB on Instrument Safety Hazard Sheets | Tom Ajluni | 5./20/2004 | Tom and Ellen sorted out changes .
21 | Closed | 2005-05-03 | Safety | 2004-05-07 | David King | Swales Feedback on Safety Schedule as per spreadsheet | Michael Cully
22 | Closed | 2005-05-03 | Mechanical | 2004-05-24 | Paul Turin | SPB Footprint to UCB | Rob Eppler | 2004-05-17 | Rescheduled from 5/10 to 5/24.
Rob waiting info from Chris Smith who is awaiting info from Rommel.
[8 empty] | 2004-06-03 | UCB does not need to change their footprint
23 | Closed | 2004-05-05 | DCB-GDDS | 2004-05-21 | Peter Harvey | Sort out date and location for test of DCB-GDDS interface. | Michael Cully | 2004-05-21 | Michael will send an email to confirmed the added tests to the schedule and their dates. Email sent 5/21/2004. Peter Harvey confirmation received 5/24/2004. This action item is closed.
24 | Closed | 2004-05-12 | Documents | 2004-06-15 | Peter Harvey | Final Orbital Debris Report CDRL | Michael Cully | 2004-06-21
25 | Closed | 2004-05-12 | IV&V | 2004-05-17 | David King | BAU FSW Peer Review Requirement comments - Responses. | Michael Cully | 2004-05-24
26 | Closed | 2004-05-17 | Solar Array | 2004-05-28 | Vassilis Angelopoulos | Side Panel Layout provided by swales | Michael Cully | 2004-05-24 | Email of latest layout sent Wednesday, May 19, 2004 9:35 AM to Vassilis from Kevin Brenneman. UCB participated in the latest teleconference. Next iteration was sent out Monday the 24th. This action is closed.
27 | Closed | 2004-05-17 | Magnetics | 6/4/2004 6/10/2004 | Michael Cully | Feedback on layout for Solar Array magnetics. | Ellen Taylor | 2004-06-04 | Rob revised date to post CDR.
2004-06-21
28 | Closed | 2004-05-17 | Vibration | 2004-06-04 | Paul Turin | Stiffen panels and get new levels. | Rob Eppler | 2004-06-21
29 | Duplicate
30 | Closed | 2004-07-01 | RCS | 2004-07-09 | David King | UCB to give Swales Feedback on whether the RCS Pyro should be Category A/B. | Vassilis Angelopoulos David King | 2004-07-02 | Category B until further notice. David King will sort out with GSFC, KSC and Range what is the cut off to switch to Category A if needed.
31 | Closed | 2004-07-02 | IDPU | 7/26/2004 8/10/2004 | Michael Cully | UCB to give Swales feedback on whether additional insert for IDPU is post or pre-bonded. | Paul Turin | 2004-07-06 | Paul let Rob know there would be an additional insert. From Paul to Rob 8/13/4 No additional insert needed.
[8 empty] | 2004-07-27 | Paul will provide insert location and ICD update on 8/10/4
32 | Closed | 2004-07-02 | Open Plan | 2004-07-23 | David King | Create a plan to get Open Plan to correctly produce Microsoft Project schedules. | Michael Cully | 2004-07-23 | It will not be possible to create a Microsoft Project schedule from Open Plan.
33 | Closed | 2004-07-02 | PIMS | 2004-07-09 | David King | IIRT PIMS logons for David King and Warren Chen. | Frank Snow | 2004-07-06
34 | Closed | 2004-07-02 | PIMS | 2004-07-16 | David King | Liaison with IIRT the entering of the CDR RFA's into PIMS database. | Frank Snow | 2004-07-19
35 | Closed | 2004-07-07 | RFA's | 11/30/2004 12/30/2004 1/10/2005 1/12/2005 | David King | Info/scope for RFA MCDR-2 Vulnerability Assessment. | Frank Snow | 2005-01-19 | Per Dennis Lee: Explorers Program Office has requested a mission vulnerability assessment from Goddard/Code 593. 10/25/4 due date revised to 11/30/4.
36 | Closed | 2004-07-09 | Defueling | 2004-07-30 | David King | Generate a draft defueling procedure that assumes one fairing door. | Michael Cully | 2004-07-28
37 | Closed | 2004-07-20 | Fairing Doors | 2004-07-23 | David King | More detail information on the need for two fairing doors instead of one. | Tom Ajluni | 2004-07-22
38 | Closed | 2004-07-21 | I&T Schedule | 2004-08-20 | David King | Resolve Inconsistencies in the UCB and Swales I&T Schedule (Mass Properties). | Michael Cully Peter Harvey | 2004-08-19 | To be resolved at the scheduling meeting on 8/19/4.
39 | Closed | 2004-07-21 | IV&V | 2004-07-24 | David King | MRD requirement PB.CDH-34 states: C&DH subsystem ACS telemetry data shall be time-tagged with acquisition time accurate to within +/- 0.25 ms. Does this really mean one quarter of a millisecond or does it mean 25 milliseconds? Does FSW do this? If so it should be documented in the SRS. | Bob Kraeuter | 7/26/2004 7/28/2004 | Sent Michael Cully a request for feedback by cob 7/27/4.
40 | Closed | 2004-07-23 | Fairing Doors | 2004-07-26 | Peter Harvey | Comment on the Swales/UCB recommendation to go with two doors. | Frank Snow | 2004-07-26 | Two doors is approved.
41 | Closed | 2004-07-23 | MCDR RFAs | 2004-07-30 | Warren Chen | Comment on Warren Chen's proposed process for S/C MCDR RFA's response submittals. | Peter Harvey | 2004-07-26 | Warren's name will be on the spacecraft RFA's in the PIMS system. He will keep Ellen informed.
42 | Closed | 2004-07-26 | Thermal | 2004-08-06 | David King | Provide an Agenda for 8/13/4 Thermal delta CDR. | Michael Cully | 2004-07-28
43 | Closed | 2004-07-27 | Thermal | 2004-08-20 | David King | UCB to provide Swales backpark cycles on S/A's for low temperatures. | Ellen Taylor | 2004-08-05
44 | Closed | 2004-07-27 | Magnetics | 2004-08-20 | Ellen Taylor | Swales to provide UCB Heater Thermostat Wiring diagrams. | Tom Ajluni | 2004-08-16
45 | Closed | 2004-07-28 | Safety | 2004-08-02 | David King | EWR127-1 Tailoring formal delivery to GSFC: Will a cover page with the signatures be sufficient as opposed to signing every sheet. | Frank Snow | 2004-08-02 | Only a cover page with signatures will be necessary.
46 | Closed | 2004-08-06 | Magnetics | 2004-08-13 | Ellen Taylor | Swales to provide real need date for Outline of Magnetics test. | Marc Kaylor | 2004-09-07 | Ellen will provide to Marc by 9/22/4.
47 | Closed | 2004-08-06 | Magnetics | 2004-08-13 | Ellen Taylor | What is the real need date for the IDPU simulator? | Marc Kaylor | 2004-08-16 | Mid October.
48 | Closed | 2004-08-06 | Hi-Fi Mockup | 2004-08-27 | Ellen Taylor | Swales to provide date when Hi-Fi mock-up will be available to Instruments use. | Marc Kaylor | 2004-09-07 | Marc requestsed from Ellen UCB need date. From Ellen: 9/24/4.
49 | Closed | 2004-08-10 | CAD Model | 2004-08-27 | Dennis Lee | Current CAD model of the probe and probe carrier in DXF or Lightwave format. | Michael Cully | 2004-08-16 | Dennis will follow up with Rob Eppler.
50 | Closed | 2004-08-12 | Instrument Mass Models | 8/232004 | Paul Turin | What is the minimum acceptable first mode frequency for the instrument mass models? | Rob Eppler | 2004-08-23
51 | Closed | 2004-08-12 | Mass Properties | 2004-08-17 | Garrett Skrobot | Payload Mass Properties clarification. | Tom Ajluni | 2004-08-12
52 | Closed | 2004-09-03 | Swales FTP Site | 2004-09-17 | David King | Set-up url's for Themis folks to access Swales Themis FTP site | Joe Procaccino | 2004-09-17
53 | Closed | 2004-09-07 | Hi-Fi Mockup | 9/24/2004 10/15/2004 | Ellen Taylor | Swales to provide Hi-Fi Mock-up to UCB. | Marc Kaylor
54 | Closed | 2004-09-07 | I&T Revised Schedule | 2004-08-26 | David King | Revised I&T schedule to be changed with three action items from 8/19/4 review, | Marc Kaylor | 2004-09-09
55 | Closed | 2004-09-13 | Pressurant Tank Brackets | 9/20/2004 10/4/2004 10/8/2004 10/27/2004 | Paul Turin | Swales to provide to UCB the pressurant tank and antennae bracket design. | Rob Eppler | 2004-10-27 | 9/24/4 Revised due date to 10/4/4 9/27/4 Revised due date to 10/8/4 10/25/4 Revised due date to 10/26/4
56 | Closed | 2004-09-13 | FM1 AXB Tube | 11/12/2004 1/7/2005 1/23/2005 | Swales | UCB to provide the FM1 AXB tube with mass dummies. | Paul Turin | 2005-01-26 | 10/25/4 Revised due date of 1/7/5 due to needed info not available.
57 | Closed | 2004-09-23 | Telemetry Spec | 2004-10-04 | Ellen Taylor | Swales to Provide a Telemetry Spec by 10/4. | Bob Kraeuter | 2004-10-08
58 | Closed | 2004-09-23 | BAU Parts List | 9/28/4 - 9/30/2004 12/24/2004 2/7/2005 | Ron Jackson | Swales to Provide UCB BAU Parts list as follows: Processor - 9/28/04, Comm- 9/29/04, Power - 9/30/04 | Nick Virmani Michael Cully |  | Draft copy received 10/29/4 90% complete. 11/1/4 Michael Cully will get status for 11/8/4 meeting. 11/22/4 Michael Cully will get the status for the 11/29/4 meeting.
59 | Closed | 2004-09-24 | Antennae | 9/22/2004 9/29/2004 | John Bonnell | Swales to provide Antennae Mast Height and Mass. | Tom Ajluni | 2004-10-15 | Height has been set at 12.75" and mass estimate at 598g. Awaiting final mass.
60 | Closed | 10/22/2004 11/1/2004 | Mass Properties | 10/29/2004 11/5/2004 11/22/2004 12/20/2004 1/28/2005 new date tbd | Ellen Taylor | Swales to provide UCB with updated mass properties. 11/1/4 Need spin balance mass properties. | Rob Eppler | 2005-02-16 | 11/15/4: Due Date for spin balance mass properties set for 11/22/4.
61 | Closed | 2004-10-29 | Transponder ICD | 2004-11-05 | Manfred Bester | Swales to provide Rev. 5 of the Transponder ICD. | Michael Cully | 2004-11-05
62 | Closed | 2004-10-29 | S/A Testing | 2004-11-05 | Vassilis Angelopoulos | Response to Vassilis comments on S/A Testing. | Michael Cully | 2004-10-29
63 | Closed | 2004-11-22 | IDPU/BAU Testing | 2004-12-03 | David King | UCB to tell Swales when the interface test can be held the week of 12/6/4. | Peter Harvey | 2004-12-03 | 11/29/4: 12/6/4 date proposed. Swales to confirm.
64 | Closed | 2004-11-22 | Antennae | 2004-12-22 | Manfred Bester | Swales to provide Antennae 6 element array pattern test data. | Tom Ajluni | 2004-12-21
65 | Closed | 2004-11-22 | Harness Wiring | 2004-12-03 | David King | Swales to set-up a Harness Wiring Diagram Review. | Michael Cully | 2004-12-03
66 | Closed | 2004-11-22 | 533Q | 2004-12-15 | Peter Harvey | Swales to provide a 533Q for Jan - Mar 05 cost projections. | Michael Cully | 2004-12-04
67 | Closed | 2004-11-22 | Bolt Cutters | 2004-12-15 | David King | Swales to provide the plan for mitigating the shortage of bolt cutters. | Michael Cully | 2004-12-07
68 | Closed | 2004-11-23 | AXB Simulators | 1/19/2005 2/2/2005 2/11/2005 4/29/2005 | Rob Eppler | UCB to provide 5 AXB Simulators for Aerojet. | Paul Turin Michael McCullough | 2005-04-22 | 11/29/4: one 1/10/5, 2 more in Feb, two more in March. Paul will take to Aerojet for the MRR. 2/3/5: First one awaiting no cost purchase order by Swales, 2 more to be sent to Aerojet 5/11/5 and the last two 6/23/5. Awaiting no cost purchase order from Aerojet. 2/17/5: No Cost PO received for the first one.
69 | Closed | 2004-11-24 | Harnessing | 2004-12-10 | Rob Eppler | UCB to provide harnessing information. | Chris Schultz | 2004-12-08
70 | Closed | 2004-11-24 | Magnetics | 2/1/2005 2/18/2005 3/4/2005 | Dennis Lee | UCB to flush out Mag Test Plan | Michael Ludlam Vassilis Angelopoulos | 2005-03-09
71 | Closed | 2004-11-29 | IV&V | 2004-12-09 | Judi Connelly | Provide Supportive Testing Documents. | Ellen Taylor | 2004-12-09
72 | Closed | 2004-12-06 | FM1 AXB Tube | 2005-02-01 | Sally | UCB to provide the AXB blanket mock-up with enable plug. | Paul Turin | 2005-01-26
73 | Closed | 2004-12-20 | SCN's | 2004-12-22 | Tom Ajluni | Update mass properties and spin plan boom scn's. | Ellen Taylor | 2004-12-28
74 | Closed | 2004-12-20 | ICD's | 2005-01-07 | Rob Eppler | SPB and AXB ICD's | Paul Turin | 2005-01-11 | SBP Already delivered.
75 | Closed | 2005-01-11 | Hi Fi Mockup | 2005-01-21 | Rob Eppler | AXB Hi Fi Mockup | Paul Turin | 2005-02-01 | One will be done on 1/18/5, the other 1/21/5.
76 | Closed | 2005-01-14 | Raw Telm Data | 2005-01-21 | Manfred Bester | Raw Telemetry Data | Michael Cully | 2005-01-31
77 | Closed | 2005-01-18 | IDPU ICD | 2/7/2005 2/14/2005 3/9/2005 | Swales | UCB to provide Swales with an Updated IDPU ICD | Peter Harvey | 2005-03-10 | 2/28/5 UCB to resolve issues in feedback from Swales.
78 | Closed | 2005-01-27 | TRR | 2005-02-11 | Dennis Lee | Informal TRR for Probe 1 Structural Qual | Michael Cully | 2005-02-08
79 | Closed | 2005-01-27 | Defueling | 2/18/2005 3/9/2005 | David King | Cost estimate for tool, procedures, training, etc to defuel the top probe. | Michael Cully | 2005-03-17
80 | Closed | 2005-01-31 | Antennae | 2/28/2005 3/18/2005 | Manfred Bester | Swales to provide UCB with updated Antennae data. | Kevin Brenneman | 2005-03-11
81 | Closed | 2005-02-03 | NTIA License | 2/18/2005 3/1/2005 | Manfred Bester | Swales to review and answer questions on the out-of-band emission levels. | Jim Jew | 2005-03-10 | 2/11/5 Swales provided responses to questions from ITT. ITT's requested additional info and Swales will provide by 3/1/5.
82 | Closed | 2005-02-14 | BAU Parts | 2005-03-11 | David King | Swales to provide feedback on schedule impacting BAU Power Module Parts. | Michael Cully | 2005-03-11
83 | Closed | 2005-02-14 | CTV | 2005-02-18 | David King | Determine if CTV of P1 can be scheduled, how long would it take and could it be started on a Friday and completed by Sunday. | Dennis Lee | 2005-02-24
84 | Closed | 2005-02-27 | Magnetics | 2005-03-11 | Paul Turin | Swales to provide S/C magnetic modeling data to UCB. | Kevin Brenneman | 2005-03-02
85 | Closed | 2005-03-07 | MSPSP | 2005-03-21 | Tim Keepers | UCB to Provide Purge Section of the MSPSP | Jeremy McCauley | 2005-03-28
86 | Closed | 2005-03-08 | FM2 AXB | 2005-03-22 | Rob Eppler | UCB to provide FM2 AXB to Swales with mass mockups. | Paul Turin | 2005-03-21
87 | Closed | 2005-03-08 | 533M | 2005-03-04 | Kate Harps | Swales to provide a corrected 533M for month ending Jan 05 | Michael Cully | 2005-03-10
88 | Closed | 2005-03-08 | 533M | 2005-03-15 | Kate Harps | Swales to provide a 533M for month ending Feb 05 | Michael Cully | 2005-03-10
89 | Closed | 2005-03-08 | 533Q | 2005-03-15 | Kate Harps | Swales to provide a 533Q | Michael Cully | 2005-03-10
90 | Closed | 2005-03-21 | Hot LAPSS SOW | 2005-04-08 | Peter Harvey | Complete Hot LAPSS SOW. | Dennis Lee | 2005-03-28
91 | Closed | 2005-03-28 | Transponder | 2005-05-20 | David King | Out of Band Width Issue | Jim Jew
92 | Closed | 2005-05-02 | Transponder | 2005-05-06 | David King | Email concerning parts and no need for additional PCB review. | Michael Cully | 2005-05-09
93 | Closed | 2005-05-05 | Draft MSPSP | 2005-05-27 | David King | RCS Section | Michael Cully | 2005-05-30
94 | Closed | 2005-05-05 | Draft MSPSP | 2005-05-27 | David King | GSE Section (s) | Michael Cully | 2005-05-30
95 | Closed | 2005-05-06 | Fueling | 2005-05-20 | Michael Sholl | Turn on Fueling contract KSC/Astrotech | Frank Snow | 2005-05-23
96 | Closed | 2005-05-06 | GSFC Badges | 2005-05-13 | David King | Renew Temp GSFC Badges for UCB personnel (Greg, Chris and Manfred) | Dennis Lee | 2005-05-12
97 | Closed | 2005-05-09 | Solar Arrays | 2005-05-20 | David King | Re-Pricing of Hot LAPS Testing | Michael Cully | 2005-06-10
98 | Closed | 2005-05-18 | BAU<>IDPU | tbd | David King | Schedule and Define next BAU<>IDPU Interface Test | tbd | 2005-05-30
99 | Closed | 2005-05-19 | Draft MSPSP | 2005-05-20 | David King | EWR127-1 Tailoring (non Battery) | Michael Cully | 2005-06-09
100 | Closed | 2005-05-19 | Draft MSPSP | 2005-06-24 | David King | EWR127-1 Tailoring (Battery) | Michael Cully | 2005-07-01
101 | Closed | 2005-05-19 | Draft MSPSP | 2005-05-27 | David King | Draft MSPSP Hazard Reports Section | Michael Cully | 2005-06-10
102 | Closed | 2005-05-19 | Draft MSPSP | 2005-05-27 | David King | Draft MSPSP Ground Ops (Refinement) | Michael Cully | 2005-05-30
103 | Closed | 2005-05-19 | Draft MSPSP | 2005-05-27 | David King | Revise Section 2.0 of SSPP | Bill Donakowski Michael Cully | 2005-06-10
104 | Closed | 2005-06-06 | BAU FSW | 2004-06-27 | David King | Build 2 Release to IV&V | Michael Cully | 2005-07-05
105 | Closed | 2005-06-07 | BAU FSW | 2005-06-17 | David King | Set Date for SQR at Hammers | Michael Cully | 2005-06-20
106 | Closed | 2005-06-13 | Safety | 2005-06-17 | Jamie Burget | PC Lifting and Handling Procedures to be submitted to GSFC. | Michael Cully | 2005-06-20
107 | Closed | 2005-06-15 | IV&V | 2005-06-20 | David King | The new BAU SRS 2.2 which IV&V has refers to Rev B of the THEMIS Attitude Control System (ACS) Specification, SAI-SPEC-1142. They would like this document. | Michael Cully | 2005-06-20
108 | Closed | 2005-06-20 | RCS | 2005-06-24 | Mike Sholl | Schematics of PPMU Test Box | Michael Culy | 2005-06-24
109 | Closed | 2005-06-20 | Transponder | 2005-06-24 | Manfred Bester | Electronic copy of Tansponder CDR to Manfred | Michael Cully | 2005-06-20
110 | Closed | 2005-06-20 | Safety | 2005-06-24 | David King | Re-submit Hazard Reports | Michael Cully | 2005-07-06
111 | Open | 2005-06-23 | Safety | 2005-07-08 | David King | Non Battery Tailoring revision based upon GSFC Safety comments Hazard Reports | Michael Cully
112 | Closed | 2005-06-27 | BAU | 2005-07-01 | David King | Differences between EDU's and Flight BAU's | Michael Cully | 2005-06-28
113 | Closed | 2005-06-28 | Safety | tbd | David King | Revisions to the Draft MSPSP based upon GSFC Safety Comments | Michael Cully | 2005-07-20
114 | Open | 2005-06-28 | Safety | 2005-07-15 | David King | Revisions to the SSPP based upon GSFC Safety Comments | Bill Donakowski
115 | Closed | 2005-06-28 | BAU FSW | 2005-07-08 | David King | Responses to IV&V Comments concerning the BAU FSW Boot Code walkthru | Michael Cully | 2005-07-01
116 | Open | 2005-06-28 | BAU Hardware | tbd | David King | Responses to IV&V TIMS #1036 and 1037 concerning BAU Hardware | Michael Cully
117 | Open | 2005-06-28 | Ground Ops | tbd | David King | Submit to IV&V Ground Ops Test Plan, Procedures and I/F Reqr Document | Manfred Bester
118 | Deleted | 2005-06-28 | Transponder | tbd | David King | Transponder PTP Test at Swales | Manfred Bester Jim Jew | 2005-07-01
119 | Closed | 2005-06-28 | Mechanical | 2005-07-01 | David King | Mech/Manual Lifting and Handling procedures Checklist | Michael Cully | 2005-07-01
120 | Open | 2005-07-06 | Safety | 2005-07-15 | David King | UCB Mechanical to view Safety CD | Paul Turin
121 | Closed | 2005-07-05 | Battery | 2005-07-08 | David King | Send Procedures to UCB: 1. BAU EDU Integration 2. PC Lifting and Handling 3. PC Modal and Acoustic Test | Michael Cully | 2005-07-15
122 | Open | 2005-07-06 | BAU | 2005-07-15 | David King | Swales to respond to how the BAU scheule can be recovered | Michael Cully
123 | Closed | 2005-07-13 | Safety | 2005-07-22 | David King | Swales to provide revisions to the Battery Tailoring | Michael Cully
124 | Closed | 2005-07-13 | Battery | 2005-07-15 | David King | Swales to respond to UCB questions on the Battery. | Michael Cully | 2005-07-19
125 | Open | 2005-07-18 | QA | 2005-08-12 | David King | GIDEP inputs from UCB (Instruments) and Swales (BUS) | Ron Jackson Michael Cully