Mr. Frank Snow, Code 410.0

THEMIS Mission Manager

Goddard Space Flight Center

Greenbelt, MD. 20771

Subject: THEMIS Monthly Technical Report

Dear Frank,

Enclosed is a copy of the monthly technical report for the THEMIS project. Copies have been distributed as itemized below.

Additional details on the status of the program are available at any time at the THEMIS ftp site:

ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/REPORTS/

If have any questions, please don’t hesitate to call.

Sincerely,

Peter R. Harvey

THEMIS Project Manager

University of California, Berkeley

Cc: 	Brenda Brady, Contracting Officer, 214.4

Publications and Graphics Services Section, 253.1

Center for AeroSpace Information

Dr. Vassilis Angelopoulos, Principal Investigator

Dr. David Sibeck, Project Scientist

# Summary Status and Accomplishments

## Mission Management

Prime Contract Status. The NASA-UCB contract is currently funded through the end of August while we work out the contract terms and conditions for the full contract. We are currently authorized to purchase long lead items and are in the process of placing long lead items. These subcontracts are needlessly complicated by not having a prime contract signed and both cost & schedule impacts are possible in this configuration.

Reviews. The THEMIS team held the Mission Systems Requirements Review (SRR) at UCB. Requests for Action (RFA) and recommendations were sent to the project office at the end of the period and we finished the period actively writing responses.

## Systems Engineering

Systems. Reported by Ellen Taylor.

1. Requirements - A successful Systems Requirements Review (SRR) was held early in the period. A number of RFAs were generated by the Review team members and are currently be worked by the development team. Revision A of the Mission Requirements Database (MRD) was distributed at the Review.  Revision B will be released following close-out of the immediate RFAs.

2. a). Electrical Interfaces - The Fluxgate Magnetometer (FGM) and Search Coil Magnetometer (SCM) ICDs have been reviewed and continue to be revised.  The Digital Fields Board (DFB), Boom Electronics Board (BEB) and EFI electrical interface definition continues to progress well. A draft electrical EFI-to-IDPU ICD (containing all three elements) will be released in the next period. Power and Data interfaces for the Solid State Telescope (SST), and Electrostatic Analyzer (ESA) are starting to become defined. The Probe to IDPU electrical interface is being discussed with Swales. A draft Probe-to-IDPU ICD has been developed and a preliminary version of the ICD will be released in the next period.

b). Mechanical/Thermal Interfaces - Mechanical interfaces between the instruments and the Probe Bus are being discussed at bi-weekly telecons between the UCB and Swales mechanical teams. Draft ICDs for many of the instrument boxes will be developed in the next period.

3. Systems Engineering Management Plan (SEMP) - A preliminary draft of the SEMP has been developed using examples provided by GSFC and Swales. The SEMP will be a joint effort between UCB and Swales. The draft will be sent to Swales for comments/input early in the next period and a preliminary version will be released for review.

4. Resource Budgets - Power, Mass and Data budgets continue to be tracked. Expect budgets will be revised significantly in the next period as teams provide estimates from preliminary design work.

5. System Design - Signal List and Power Distribution lists have been started. Harness diagram and detailed system block diagram will be developed in the next period.

Orbit Design. Written by Manfred Bester.

Additional analyses have been conducted to further refine the mission orbits in order to optimize science and to conserve fuel. The Berkeley team has been working with GSFC/GNCD to update the GMAN Spacecraft Data Files with more accurate probe mass properties, tank and thruster placement, and thruster performance data. This effort is nearly complete.

Mechanical Systems. Written by David Pankow. The pace of activities is accelerating as a number of people are joining the Themis team. Personnel are transitioning from Stereo-Impact to Themis. Four new hires will be starting over the next several weeks. Setting up offices, telephones, etc. will be a short term distraction, as well as pending vacations. Solid Works will be the groups common CAD system, and PDM (product data management) is planned for configuration control. The annex network will shortly be upgraded to accommodate the increased traffic. In contrast, Swales as a company remains fully committed to Pro Engineer (which often reviews as both more costly and cumbersome). The Step & other interfaces between these CAD  systems do seem to work, and we are hoping they will be adequate. Regularly scheduled telecons with the Swales engineering team has begun. A focus of these discussions is the instrument interfaces, as well as the needed structural and thermal modelling interactions.

The science team currently has the lead with a major focus of achieving the best science, for the limited Themis' resources. A common thread is the significant mission radiation and thermal constraints. Modest packaging revisions are actively being pursued in several areas, to make the instruments more tolerant. Separation of the detector heads (and Amptek modules) from the instrument electronics for the ESA and SST is now being internally examined, to make them more temperature and radiation tolerant. In a similar context, alternate packaging techniques for the EFI preamps (the so called hockey pucks) are also being developed. Further puck packaging refinements await the ongoing electrical bread-boarding efforts. The SRR was successfully completed, with only two minor recommendations in the mechanical area.

# Space Segment Development

## Instruments

2.1.1. Instrument Data Processor Unit

Boom Electronics Board (BEB). Written by Stewart Harris. Activities for July:

- Based on the previous BEB designs, a trade off study was performed on suitable replacement op amps for the BEB, with at least three presenting themselves as adequate candidates.

- A single channel, breadboard BEB was designed and fabrication begun.  The purpose of the breadboard is to 1) test these three op amps in circuit, and 2) provide a test box for future preamp testing and system level testing.

- We began motor driver circuit design for the brushless DC motors that have been selected for boom wire actuation units (radial booms).

- We’ve submitted one channel of BEB analog circuit design to layout, to get preliminary board area requirements.

Activities for next period will include:

- Op amp testing, completion of testing of breadboard BEB.

- Based on op amp selection, complete the design for the analog section of a 6-channel BEB.

- Test a breadboard level sample and hold DAC concept in which we can compactly implement 24 DACs.

- Write an IDPU ICD to define I/O and connector interfaces.

Digital Fields Board (DFB ). No report.

Data Controller Board (DCB). Written by Dorothy Gordon.

1.  Released Preliminary DCB Specification: Includes 8085 CPU, PROM, SEU-Immune SRAM, FPGA resident control logic and SDRAM for Bulk Memory Storage. (Compression implementation is still TBD.)

2. Obtained quote from 3D-Plus for SDRAM.  The 3D-Plus offering is currently beging evaluated for its radiation tolerance and SEU susceptability.

3. Need to specify interfaces to DCB: these include the instrument serial I/Fs and C&DH interaction with the DCB based solid state recorder.

4. Need to work with DCB software engineer in order to detail DCB control logic and hardware/software interaction.

Low Voltage Power Supply (LVPS).  No report.

Harnessing. No report.

2.1.2. Electric Field Instrument

Written by John Bonnell.

Science and performance requirements on the EFI were presented at the System Requirements Review July 8-9.  A more detailed calculation of the probe-spacecraft current balance was performed to determine bias current levels in different plasma regimes, as well as the expected range of probe coupling impedances. An initial mechanical design for the preamp enclosure and connector was developed.  Parts selection and planning for radiation testing of preamp parts was begun.  Mechanical tests on initial batch of fine wires were performed, and additional vendors identified.  Simulation of potential offsets due to asymmetric boom placement were completed, and showed that the predicted electric field offset was a sensitive function of the displacement of the antenna elements, but that symmetric deployment of the axial elements will probably satisfy requirements.  An initial draft of the Electrostatic Cleanliness (ESC) specification was produced.  The use of titanium nitride (TiN) coatings as a replacement for DAG on the radial EFI sensor elements was investigated, and looks promising as a tougher, electrically equivalent coating that will allow for a simple door design and handling protocol.

Activities for the next period will include:

- initial electrical evaluation of candidate preamp design and parts.

- Initial preamp enclosure and connector design.

- Mechanical testing of candidate fine wire samples.

- modeling of E-field attenuation (shorting effect) due to wire and stacer booms.

- Completion of more detailed current balance calculation for alternate biasing schemes and operational regimes.

- Completion of TiN vs. DAG trade study.

- Completion of ESC specification.

2.1.3. Electro Static Analyzer (ESA)

No report during the period

2.1.4. Solid State Telescope (SST).

Having decided upon the Amptek (Wind) design for the SST detectors, much of the preliminary design has gone forward. The detectors were designed in concert with the LBNL group and a specification & statement of work were developed. A contract for the long lead flight detectors is expected to start in the next period. Until detectors are available, we are testing electronics with available past-mission spares.

Electronics block designs and packaging concepts were being developed during the period. The expected radiation dose-depth curve and available parts would conspire to make the SST box rather thick and heavy. A trade study is being conducted to determine if the SST would be better off having the electronics in the IDPU box and only the sensor electronics at the sensor housing.

Key design uncertainty is the A/D converter. The current top candidates need considerable shielding in order to meet the 66 Krad specification. Alternatives take much greater power.

2.1.5. Fluxgate Magnetometer (FGM).

No report this period.

2.1.6. Search Coil Magnetometer (SCM).

### Monthly report SCM

Written by: Abdel Bouabdellah, Christophe Coillot, Bertrand Delaporte, Olivier Lecontel, Alain Roux

#### Sensors

The search coil BBM has been tested. Its characteristics are compliant with our objectives. The frequency response of the sensor, the resonance frequency and the mass are nominal.

#### Preamplifier voltage regulator:

Tests of regulation for voltage supply below 8.5V has shown a bad operating. Requirements from CETP to have +/-10V is confirmed.

#### Preamplifier

BBM preamplifier which will allow to fix the design and the part list has been received at CETP.

Calibration : No change from previous monthly report.

Routing of the final preamplifier board (which includes 3D preamplifier, 3D power supply regulator and calibration) continue.

Tests of BBM Preamplifier have begun : correct operating, measurement of transfer function, and output noise.

Mechanical structure of tri axis antennas.

Structure design is under definition with the firm GDTech.

#### Harness SCM to PA

Harness pin out is defined. Abdel will send harness description at the end of August.

### Magnetometer Booms.

Written by Hari Dharan.

Design

1. Obtained preliminary design of composite boom geometry.

2. Designed composite layups to meet specifications for stowed and deployed configurations.

3. Established mechanical interface requirements with FGM and SCM instrument groups.

4. Began preliminary design of prototypes of boom supports and joints, i.e. base brackets and hinges.

Fabrication.  Identified manufacturer and obtained firm quotation and delivery schedule for tube fabrication equipment.

Budget and personnel. Completed hiring personnel and preparation of preliminary budget for mag booms.

Reviews. Attended SRR on July 8-9, 2003.

## Probe  and Probe Carrier

See Reference : ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/REPORTS/thm_monthlyreport_0307_ppc.pdf

# Ground Segment Development

3.1. Mission Operations Development. Written by Manfred Bester.

MOC Design. A detailed schedule for the design and implementation of the THEMIS Mission Operations Center and all of its support functions is currently being developed. The operations team has started to draft plans for an on-line database system that will be used to keep track of the operational status of all probes. Team members also began to familiarize themselves with the attitude determination software MSASS. A training session at GSFC/GNCD is planned for later this summer.

The operations team has closely worked with systems engineering to develop detailed plans for the C&DH subsystem on the probes, as well as strategies to perform data compression and telemetry transmission.

Communications and NTIA License.  A trade study is being performed to determine the optimum communications scenario, i.e. modulation types, data rates, link margin and contact intervals as a function of probe range and power margin. Communications options via TDRSS in support of maneuver execution near perigee are being discussed with GSFC. A preliminary TDRSS link analysis has been performed  by GSFC/CLASS.

The Berkeley team is also working the GSFC Spectrum Management Office and ITT Industries regarding application for the THEMIS NTIA license. A baseline for a PSLA is being developed, taking into account required data volumes and predicted downlink schedules.

3.2. Science Operations Development. Written by Tim Quinn.

Particpated in the Program Requirements review meeting on July 12 and 13. Presented current basic design of THEMIS SOC. Continued further design of spacecraft and GBO end-to-end ground data processing system.

Particpated in a demonstration of a DVD production system manufactured by Luminex. Using FAST and HESSI as test beds began testing database and web products for possible use by THEMIS for data access and processing.

3.3. Ground Based Observations Developments

Written by Stewart Harris

Work continued in a number of areas:

1. Conceptual design for the GBO enclosures was completed.

2. Testing of the prototype All Sky Imager (ASI) continued.

3. Initial testing of GBO remote, internet connectivity was completed.

4. Development of GMAG and GPS interface electronics continued.

5. Selection of GBO computers was made, test samples purchased.

The conceptual design for GBO environmental enclosure is based on a two box concept. The ASI will be in one enclosure, that can be flexibly mounted separately from the computer enclosure.  Requirements for the enclosures were published on the 'themisg' ftp site.

ftp://themisg@sprite.ssl.berkeley.edu/ProjectDocs/GBO_Req_Review_RevE.xls

Personnel at the University of Calgary continued field tests of the ASI prototype. This included deployment and nightly operation of the ASI at their Athabasca site.  The prototype was designed and fabricated at UC Berkeley.  Real-time images can be viewed by accessing their web site and clicking on "REAL TIME DATA", then selecting site 12:

http://www.phys.ucalgary.ca/NORSTAR/themis/themis_main.html

To address observatory communication issues, a feasibility test of the Telesat satellite internet connection solution was tested by the U. Calgary team. They confirmed that data uplink from the Telesat terminal could consistently support about 80kbps rates. You can read their full report at:

http://www.phys.ucalgary.ca/NORSTAR.new/themis/telesat_hsi_test.html

Planned activities for next period:

- Continue site selection for GBO network.

- Continue preliminary design of GBO environmental enclosure.

- Testing of Datalux/Linux computers that have been selected for use in GBO.

# Education and Public Outreach

Written: Nahide Craig, Laura Peticolas

We contacted Neal Brown at the Space Grant Consortium in Alaska (E/PO partner) to find out about possibly having teachers involved in the maintenance of the two Western Alaskan GBO sites.  We had several discussions with Vassilis Angelopoulos and Stephen Mende regarding this option and whether and how we would implement it.  We also contacted Michelle Larson, of the Montana Space Grant Consortium, who will head the teacher competition in the other THEMIS E/PO sites.

Laura Peticolas presented a teacher workshop as SSL on July 16th to 15 teachers nationally, and part of her sun-earth connection topic workshop also introduced them the THEMIS Mission.

# Problems

## Outstanding Problems

Probe Avionics CPU.  Swales does not currently plan to use the 80196 processor due to concerns about it from other GSFC programs. The alternative is expensive, so GSFC should provide concurrence with this processor solution (i.e. so we don’t do this again).

Communications.  The CSR approach to communications between the probes and the ground systems was only one of many alternative approaches which are possible. UCB and Swales have been debating which is the best solution, but this really requires NASA and NTIA concurrence. We are currently engaging expertise to determine what works best for all concerned.

## New Problems / Problem Avoidance

None this reporting period.

## Resolved Problems

# Risk Management

The plan is in the process of being produced..

# Performance Assurance

Implementation Plan.  A draft Performance Assurance Implementation Plan (PAIP) has been developed for the program. We have requested inputs from Swales and other flight fabrication organizations. At this time, none have responded to our request.

Parts. We are currently up to revision 14 of the parts list, with nearly all parts desires now understood. Radiation test results are being checked and tests identified for parts that need them.

Materials.  No changes.

Supplier Audits. None during the period.

# Mass and Power

During the period, the mass and power have remained unchanged.