Mr. Frank Snow, Code 410.0

THEMIS Mission Manager

Goddard Space Flight Center

Greenbelt, MD. 20771

Subject: THEMIS Monthly Technical Report

Dear Frank,

Enclosed is a copy of the monthly technical report for the THEMIS project. Copies have been distributed as itemized below.

Additional details on the status of the program are available at any time at the THEMIS ftp site:

ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/REPORTS/

If you have any questions, please don’t hesitate to call.

Sincerely,

Peter R. Harvey

THEMIS Project Manager

University of California, Berkeley

Cc: 	Mike Riley, Contracting Officer, Code 410

Technical Information Services Branch, Code 239

Dr. Vassilis Angelopoulos, Principal Investigator

Dr. David Sibeck, Project Scientist, Code 696

# Summary Status and Accomplishments

## 1.1 Mission Management

Written by Peter R. Harvey

In August 2004, the THEMIS flight fabrication began in earnest, with a number of instrument systems cutting metal and making flight boards. The Thermal design review completed a major element of the probe system design, and the first elements of the probe structure were fabricated. The Launch Vehicle contract was initiated and the Mission Integration Working Group met for the first time to discuss how to assemble and launch the five spacecraft. And several Ground Based Observatories were readied for installation in Canada and Alaska.

It is important for everyone involved to realize that this is the toughest part of the project and that we must pull together to make THEMIS a successful mission. Doing so will make all the work worthwhile.  So, at every opportunity, we must share our abilities and our energies within our group, our lab, and our project.

# Space Segment Development

## 2.1 Instruments

### Instrument Data Processor Unit

Boom Electronics Board (BEB).

Written by Stu Harris

Activities to report for Aug

1. BEB ETU FPGA.  Continued work with the FPGA including solving an initial startup case and a power-off case.

2. BEB flight unit status.  PC boards were fabricated in August, and assembly of flight units was begun at Jackson and Tull.  Assembly of first two units was largely completed by the end of Aug.

3. EFI GSE unit construction.  The construction of a second GSE box, designed to support EFI preamp and BEB testing, was begun during August.

Planned activities for next period:

1. BEB flight units are due to begin arriving from Jackson and Tull.  Testing of flight units will begin as soon as possible thereafter.

2. EFI GSE#2 unit construction will be completed, and it will be tested.

Digital Fields Board (DFB ).

Written by Jim Westfall

August Accomplishments:

1. Created simulation test bench for the FFT processor and performed functional debug of the state machine and data path. The processor is now in a verification state where we’re running simulations to validate the data at all stages of processing and the outputs. Initial simulations of a DC waveform and a 10 second chirp have been run. LASP is currently working on IDL to display and analyze the results versus the IDL implementation to verify the algorithm.

2. Performed detailed design of the calculation of derived quantities…implementation to start soon.

3. Test ETU#2. Cross talk appeared to be too high. Spent a lot of time trying to determine the source of cross talk.

4. Modified some component values to reduce cross talk, which was down to acceptable levels.

5. Delivered ETU#2 to SSL.

6. Continued to try to reduce cross talk further. Determined the source. Implementation of solution in process.

September Objectives:

1. Release final (with all currently known features) version of the DFB command and telemetry section of the FPGA document.

2. Implement and document derived quantities.

3. Update implementation and documentation of command and telemetry controller to include spectra and derived quantities.

4. Release logic module placements, pin-out, and power numbers based on fully functional FPGA implementation. Note that start-up items and other enhancements may come later but shouldn’t affect these items.

5. Update schematics.

6. Review PWB design and proceed to final flight layout.

No changes in power and mass.

Data Controller Board (DCB)/ Flight Software

Written by Dorothy Gordon

1. DCB-ETC PCB

The schematics have been revised, checked and sent to the layout designer.  All layout modifications have been completed, and the artwork is being checked. We expect flight board fabrication to begin in early September.

We are planning to build an extra ETU from this "Rev B" artwork, which will be used to verify the layout/fab prior to the flight board population, and will later serve as an extra DCB-ETC prototype.

2. DCB-FPGA

The design of the Rev. 5 DCB-FGPA has completed.  In addition to the ECC Scrubber subsystem, Rev 5 has added a dedicated hardware packet as the High-Speed Telemetry frame fill pattern, and an option to select 32Hz or 16Hz for the DFB "fast" timing tick option.

IDPU Software (FSW)

Written by Peter Harvey

Phase I. The PROM code needed for booting up the processor, accepting commands, generating the 1 Kbps housekeeping, reading and writing the EEPROM is complete and is ready to be verified against the BAU.

Phase II. Power, Housekeeping sampling, Actuator control, Spin Phase Locked Loop controls, and ETC controls are all operational. The FGM module was upgraded to include the new APID 405 (8 Hz vectors). SCM and EFI are in various levels of test but are not yet satisfactory.

Phase III. During the period, UCB delivered phase III software modules which included the Spin Plane Boom Deployment controller, the Spin Fit calculation software (including Floating point routines, trigonometric functions and sine-wave least squares fitter). Software to grab data points from the sensors to feed to the fit routine was not completed during the period and but is not needed for the next several months.

Processor Utilization. The resources are in fair shape with no change to the predicted 45.9% worst case loading (not counting Compression).  The average CPU usage on the bench is about 12%.

Memory Utilization. PROM, EEPROM and RAM utilization is tracked periodically. The overall strategy, of course, will be to put all LEO-required modules into the PROM, followed by as many other modules as can fit. The rest will be put into the EEPROM and loaded in the first few seconds after turn-on.

IV&V. Weekly exchanges with IV&V have been clarifying and filling in detail in the requirements flow-downs. Currently, we have made over 110 changes to the software requirements and are planning a new release of those requirements on October 1st (available for review).

Power Control Board (PCB)

Written by Craig Domeny

During the period, the PCB/FGE circuit boards were fabricated and the coupons were approved for flight. The cards began assembly at both Jackson&Tull and UCB in order to expedite the test of the first board of six.

While the flight boards were in production, the PCB test equipment was assembled. One load simulator is built and is being tested; and a second is planned. Cables for the test setup are in assembly.

Testing of flight assemblies will require either an LVPS, or LVPS simulator, which has identical output character as the LVPS circuit itself.

### Electric Field Instrument (EFI)

#### Spin-Plane Boom Mechanisms

Written by Bill Donakowski

## Progress

- EM Unit Status

  - All Qual testing completed

  - Thermal Vacuum Testing completed 08 September 2004

    - 2 Thermal Cycles

    - One Hot Deploy

    - One Cold Deploy

    - All deploys and performance Successful

- Test Fixtures

  - Redesigned take-up spool assembled and functional

  - SPB Mass Models completed and in-house

  - SPB Volume models (stereo lithography) fabrication begun; 4 units received in-house

- Facilities

  - Room 20 TV Tank ‘Bayside’ checked out and working correctly

  - Tank successfully used for SPB TV Qual with no problems.

  - Large TV Tank Development

    - All hardware being fabricated; should be in-house 15 September

- Flight Hardware	Procurement Status

  - All Flight Hardware in-house except for 3 pieces, machined magnesium structural plates (due 15 December 2004)

- Flight Units Build

  - Various Sub Assys assembly continuing

    - Motors Vacuum Burn-In completed for all units

    - Key Reel/Sphere Assy begun

    - Motor EMI Shields Assy completed

    - Electrical wiring of first 4 units started

    - 2 Motor Units sent to UCLA for stray magnetic field testing; units passed—low stray magnetic field

    - Coaxial Cable fabrication started for first 4 units

## Outstanding Issues

- Magnesium Plates holding up further flight build

## Concerns

- Preamp/Wire delivery driving entire F1 delivery at this time

#### 2.1.2.2 Axial Booms Boom Mechanisms

Written by Robert Duck

- Design

- Thermal Vac horizontal track design complete and parts currently in the machine shops.

- Stacer length is still up in the air due to Swales mass issues.  Length to be frozen this week to allow trimming and assembly.

- Deliverables

- 50% of Vibration fixtures received.

- All stacer trimming equipment is received.

- All Electrical parts received.

- All mechanical parts received for FLIGHT 1.

- Flight 1 stacers painted and received.

- ETU Assembly

- ETU masses verified.

- FLIGHT Assembly

- Ametek sensor assemblies will be taken apart due to testing issues below.

- Flight 1 DAD Door Assemblies are complete.

- AXB tube has been cut to length. ID is slightly out of spec.  Full measurements on tube mandrel will be performed and if necessary new mandrel will be machined.

- Assembly of Flight 1 sub assemblies is on going.

- Documentation

- ICD revisions completed.

- Tube delivery schedule updated for Swales integration and deadlines set for Swales tank mount design due to UC Berkeley.

- Draft assembly procedures are completed.  Initial build of first assembly is conducted with procedure and modifications are updated for final assembly procedure.

- Final assembly procedures are completed for 6 sub assemblies.

- Testing

- ETU deployment test performed for runout calculation.

- Stacer cord length reduced and runout at preamp reduced to 0.625”, which is within specification.

- Runout at sensor housing not in specification.  Tip piece diameter was too small. New larger diameter was made with taper and ETU sensor performance was excellent.  Enhancements were tried on FLIGHT sensor.

### Electro Static Analyzer (ESA)

#### 2.1.3.1 Mechanical

Written by Bill Elliott

- Continued  Assembly and Cycle Testing of Flight SMA Actuators.

- Continued Washing and Bagging FLIGHT Parts.

- Prepare Mass and Volume Mockups of the ESA + IDPU

- Ordered Last of the Short Lead Mechanical Parts.

- Received Flight Quantities of the Ebanol-C Coated Hemisphere and Related Parts.

- Inventory of Flight Parts is complete except for Release Roller Spring Assemblies and Radiation Shields, which are not yet plated.

- Continued to Work With the Electronics Group to Finalize the Mechanical-Electronic Package Interface Specifications.

- Performed T-V Test of Release Plate Assembly. Successful Actuation of the Mechanism at -40C and +50C using Both SMA’s Simultaneously.

- Performed Vibration Test of Combined ESA + IDPU 8-18-04. No Broken Parts or Excessively Low Frequencies. One SMA Failed to Fire After Test. Failure Analysis Underway.

- Prepared Analysis Predicting SMA Wire Temperatures and Cooling Times. Gathered Test Data on Actuation Times at -40C and +50C.

- This Month (September):

- Vibration Re-Test of combined ESA + IDPU to verify individual SMA Firing.

- Continue to Test Release Plate Assembly in Thermo Vacuum

- Begin Mechanical Sub-Assembly of FLIGHT ESA units.

- Next Month (October):

- Assembly of 6 FLIGHT ESA-Mechanical Units

### Solid State Telescope (SST).

Report written by Robert Lee

- Design:

- Finalized backshell designs for 26 pin high-density connector to allow for cable potting (THM-SST-MEC-605 and THM-SST-MEC-607)

- Finalized connector plate for interface with spacecraft bus (THM-SST-MEC-606)

- Attenuator dimensions finalized (THM-SST-MEC-301)

- Commercial auxiliary switch actuator replaced with custom design to eliminate friction sources (THM-SST-MEC-504)

- ICD for Integration with Bus:

- None taken

- ETU Testing:

- Unit being prepared for qualification level thermal vacuum test tentatively scheduled for September 9, 2004

- Mechanical fixturing for instrument level thermal-vacuum test ordered and received (August 18, 2004)

- Designed mechanical fixturing and support components for ion beam measurement

- Flight Units:

- Flight thermostat received (August 30, 2004)

- Flight magnets received (August 19, 2004)

- Flight collimator assembly components received for two sensor units; additional components ordered (ETA: mid September 2004)

- Flight switch assembly components received for two sensor units; additional components ordered (ETA: early September 2004)

- Flight magnet yokes ordered (ETA: early September 2004)

- Flight support structure components for three sensor units received (August 25, 2004); additional components ordered (ETA: late September 2004)

- Flight attenuator assembly cams sent out for titanium nitride coating (ETA: early September 2004)

- Flight attenuators ordered (ETA: 9/7/04)

- Flight aluminized foils ordered (ETA: mid September 2004)

### Search Coil Magnetometer (SCM).

Written by Abdel Bouabdellah, Christophe Coillot, Bertrand Delaporte, Olivier Lecontel, Alain Roux.

:

- Sensors

- EM: Manufacturing of sensors:

  - Delivery of EM sensors (with Stycast 1090SI) from Technopoint to CETP.

  - Assembly of EM sensors inside mechanical structure.

- FM:  Beginning of sensors manufacturing:

  - Winding is in progress.

- Preamplifier voltage regulator 3D+

- FM : 	Delivery from 3D+ to CETP

- Preamplifier 3D+

- FM : 	Delivery from 3D+ to CETP.

- Preamplifier

- EM:  Delivery from CETP to UCB.

- FM:  Footprint error on a component (capacitor) has been discussed & solution has been agreed: component can be placed on the footprint following rules of placement.

Cabling of component on PCB can continue.

- Preamplifier box

- All 6 FM boxes have been delivered.

- Mechanical structure of tri-axis antennas

- FM manufacturing has begun (as vibration test & thermal tests were compliant), delivery expected on October 11.

- Harness SCM to PA

- EM : Validation with sensor has been realized during full calibration of sensor at “Chambon la Foret” : compliant.

- EGSE

- Bench test has been manufactured and used for temperature tests, 3 models will be realized to support tests and integrations (CETP)

- Interface for Calibration at Chambon la Foret is under definition (CETP/GDTECH).

- EM Tests

- Following tests have been completed successfully:

  - Functional test of SC at CETP,

  - Mechanical vibration of SC (at IAS),

  - Calibration in Chambon la Forêt (PA +SC) : July 27-28,

- Following tests have been realized :

  - Thermal cycling of Sensors mounted on the mechanical structure at SOPEMEA : August 16-20.

  - A thin crack on potting has occurred (cf. photo below).

  - This crack doesn’t affect electrical behaviour of sensor.

  - Delivery of EM sensor to UCB will be done after filling the gap : end of September.

  - Three solutions are under investigation.

  - Tests (thermal cycling) will be done to validate potting under qualification level.

- Integration at UCB:

  - Date to be confirmed (UCB)

### Magnetometer Booms

Written by Tien Fak Tan

- Design.

- Completed redesign to increase clearance of mag booms over solar arrays completed.

- Released ICD.

- Investigated and mitigated impacts of harness on mag boom deployment.

- Fit check of FGM on mag booms completed successfully.

- Fabrication

- Fabrication of hinge parts in progress.

- Composite boom tube fabrication is in progress.

### 2.1.7 Facility Development

#### 2.1.7.1 Calibration Chamber (Ion Gun Facility)

Operational.

#### 2.1.7.2 Thermal Vacuum Facilities

Written by Sharon Jelinski

- Bayside (Small) T/V System, Refurbishment completion

- Peter Harvey mandates that Power Resistors must be used as a short-term solution while waiting for the Minco aluminum backed heaters.

  - Dale Resistors use silicone in the encapsulant, a contaminant in vacuum.

  - Arcol Resistors have no silicone, use approved epoxy for encapsulation.

- Arcol resistors are mounted with Thermo-Pad for better heat transfer.  Baseplate has 24, 100Watt running at 50Watts, with Al clamping bars held at 1/4-28 thru holes, sharing instrument mounting holes.  The shroud/end caps have 48 resistors overall, 50Watt running at 25Watt, using 4-40 hardware thru shroud material.

- The temp upper limit of the Power Resistors is 200 degrees C, much closer to our operating temp than the lamps and with a greater safety margin than heater strips.

- All resistors are de-rated to 50% through the wiring scheme. If controller signals 100% full on, the heaters will only run at 50%, safeguarding against overheating.

- Power resistors are baked out in an empty chamber to allow initial outgassing.  The vac chamber base pressure rises significantly when running hot temps, but this base pressure improves over successive uses, currently 2.4e-5 torr at 100C.

- The first instrument test runs successfully. The SPB engineering model was tested to profiles with temps of +75C to –60C with 2 hour soaks.  The profiles held the control surfaces to the set temps for 2.5 hours, while the instrument plate held the hot temperature for 2 hrs and the cold temperature was warm by 5 degs for 2 hrs.

- Next test should have profiles that run 5-10 degrees colder then desired cold temp.

- One dewar is used for a solid 4-5 hrs cold soak, so 2-3 dewars are needed per day.

- Upon completion of SPB test the vacuum chamber will undergo one last cleaning, (where SPB EM was known to be slightly dirty) and both TQCM and RGA measurements will be taken for a baseline level of system cleanliness.

- Outstanding Bayside system tasks that remain are:

  - Final cleaning of chamber.

  - Final measure of baseline TQCM and RGA.

  - Fine tune cooling system control for less overshooting.

  - Upgrade LN2 valves, buy larger units and build a new manifold.

  - Finalize system documentation with user procedures for the full system.

  - Eventual LN2 connection to large LN2 bulk tank on patio when available.

- We do not plan to change out Arcol power resistors when Minco heaters arrive.

- THEMIS Snout T/V System – Fabrication in progress at SSL and vendor

- The underside of baseplate is machined for Arcol resistors at SSL

- The baseplate is having square copper cooling tubes pressed in at SSL.

- The shroud is machined for Arcol resistors and being painted with Z307 at SSL.

- In the next 2 days the baseplate and shroud will be fully assembled with Arcol resistors and then returned to Tranfer Engineering for final assembly.

- The Vacuum Chamber is fully operational and working at Transfer Engineering.

- The full Snout system should be delivered on September 20, and ready to install.

- The Snout system must be fully operational at SSL by September 26th to meet Themis AXB delivery.

- Therm-X thermal system controller on order, due date of  9-13-04.

- Thermal control system to be mounted inside vacuum cart frame.

- The Snout system operation requires the SSL location supplies the following:

  - 208V single phase power for the vacuum system.

  - 208V single phase power for the heater system and control.

  - 110V power for auxillary components for thermal control system.

  - 110V power for Themis instrument operation.

  - LN2 dewars and supply lines to the LN2 manifold.

  - If the Snout goes in RmB20, eventually connect to the bulk LN2 tank.

- The Snout system preparations at SSL are in progress but we need a final decision on the location of the Snout chamber.  If located in RmB20, then we have:

  - Electrical distribution and breaker panel being installed by UC Electrician.

  - Adequate access for LN2 dewar next to vacuum system for the short term.

  - EH&S, Building Facilities, and UC Fire Marshall have given permission.

  - LN2 feed line pass-through hole in building wall has been OK’d.

  - LN2 flexible lines internal to RmB20 will be vacuum jacketed, due 10-15.

- BERTHA T/V System, Room B20, Fabrication in progress.

- All mechanical parts have arrived except the shroud and baseplate.

- LN2 feedthroughs are connected to supply and exhaust lines by Praxair.

- LN2 bulk tank supply will have 1500 gal. capacity, due in mid. October, but the current temporary configuration is set-up for multiple standard dewars.

- Baseplate and shroud are in production at outside vendors, tracked by McKee.

- Baseplate is Aluminum with groves for SSL installed sqr. copper tubing.

- Therm-X thermal system controller on order, due end of September.

- Thermal control rack and support equipment on order.

- Power resistors by Arcol on order, with 2 day delivery.

  - Baseplate: quantity 34, 200Watt resistors running at 100Watts.

  - Shroud and ends: quantity 100, 50Watt resistors running at 30Watts.

## Probe and Probe Carrier

See Reference: ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/REPORTS/thm_monthlyreport_0408_ppc.pdf

# 3  Ground Segment Development

Written by Manfred Bester

3.1 Mission Operations Development

### 3.1.1 Mission Design

Contributed by Sabine Frey

The THEMIS flight dynamics team further improved the IDL and GTDS based mission design code, which is used to develop detailed orbit placement strategies and timelines for all five probes, independent of the launch date. The orbit placement is optimized for maximum conjunction time, minimum shadow duration and minimum number of maneuvers. The maneuver sequence itself is optimized for lowest delta V with the least amount of operational complexity and built-in slack to allow for probe and instrument commissioning, orbit determination and recovery from various contingencies.

The effect of different launch RAAN values of 320, 312 and 302 deg on shadow durations, conjunctions and accumulated delta V was explored. It appears that the most favorable RAAN falls between 302 and 312 deg, resulting in longest shadows below 180 min and acceptable conjunction hours. The accumulated delta V for P1 including ascent and the first tail season is 400 - 420 m/s. Further refinement of the orbit placement is under way.

A license for AI Solutions’ FreeFlyer Engineer software has been purchased. FreeFlyer will be used to obtain the optimum trajectory and to verify the delta V usage for each maneuver.

### 3.1.2 Ground System Design

The design of the THEMIS ground data system was completed and its implementation is well on its way. The envisioned architecture for THEMIS is built on top of the existing multi-mission operations environment already in place at the Berkeley MOC. Additional software tools will be implemented to streamline data flows, to generate constellation overview displays and to populate databases with probe telemetry points. The latter will allow efficient access to telemetry archives for data trending and event analyses.

The workspace configuration for THEMIS mission operations and I&T was nearly finalized. A Linux workstation was procured and is currently configured to test the first THEMIS version of ITOS. The final design for the THEMIS Attitude Determination System is almost complete, and a requirements document will be released shortly.

### 3.1.3 Mission Operations Planning

Regular telecons between Swales, Hammers and Berkeley operations team members were held to discuss operations related matters in the areas of telemetry and command processing, flight and ground software development and configuration, I&T related issues, development of operational procedures, flight rules and recovery from contingencies. A timeline for early orbit and normal operations is currently developed in collaboration with systems engineering and pertinent instrument scientists.

Various statements of work for operations and software support by GSFC/GNCD and AI Solutions, in particular for maneuver planning, orbit and attitude determination support are being developed and will be released shortly.

### 3.1.4 Ground Station and TDRSS Support

An RF ICD covering all interfaces between the probes and the ground stations as well as TDRSS was submitted to GSFC Code 450 and is currently reviewed. A draft PSLA for 2004 covering THEMIS support activities for TDRSS and NASA/GN was submitted as well. Both documents will be signed shortly.

3.1.5 Berkeley Ground Station

Several items for hardware upgrades have been delivered and are currently tested off-line prior to integration into the ground station. These include the Carrier Doppler Measurement System, Tracking Data Formatter, 200-W transmit power amplifier, receiver IF filters to match THEMIS data rates, a precision timing system, a solid-state matrix switch for routing of baseband signals, and several serial servers that allow for remote control of RS-232 devices via TCP/IP network sockets. Plans to place the antenna subsystem under back-up power provided by a Diesel generator are developed. All systems within the MOC are connected to the back-up power circuits already.

A matter of concern is the recent gear failure of the DataLynx 11-m antenna at Poker Flat, which is the twin of the Berkeley antenna. UCB is working with GSFC Code 544 and with the antenna manufacturer to assess whether the BGS gearbox upgrades implemented in 2002 fixed the original design flaw, or if other measures need to be taken to maintain a reliable operational status. An inspection of the gearboxes will be scheduled for October 2004.

### 3.1.6 NTIA License

The Berkeley team worked with the GSFC Spectrum Management Office to prepare the application for the THEMIS NTIA license. Preliminary S-band frequencies were assigned to THEMIS and approved by the DoD. The GSFC Spectrum Management Office submitted the Stage 2 application to the NTIA, and approval is expected by late 2004.

### 3.1.7 Personnel

An additional member of the Flight Dynamics Team has been hired on September 3, 2004 to support mission design, maneuver planning and orbit determination. A second position for ground systems software support, in particular ITOS and MPS is still open and is expected to be filled by October 2004.

3.2 Ground Based Observations Developments

Written by Stewart Harris

Activities reported for August

1. Production Unit Deployments Status.

- GBO#2 - Deployed in Athabasca (Canada) 7 August.  It includes all major components of standard GBO production unit, such as GMAG, Iridium modem and Computer System Environmental enclosure.  On 9 Aug. we noticed that the imager was producing rather noisy images and concluded that the thermoelectric cooler was not operating.  This could be a wiring failure, or an electronic failure, so additional troubleshooting is required.  For now, the imager is producing satisfactory images.  The additional dark noise does not obscure the sky and the images still meet our requirements.  But on 25 Aug. we observed the ASI sunshade to be stuck in the closed position.  Poor weather prohibited the local custodian to make observations of the problem, but by 1 Sept it appeared to be operating again.  This also needs further troubleshooting.  A trip to ATHA is tentatively scheduled for October to repair these problems.

- GBO#3 - Shipped to Prince George (Canada) on 24 Aug.  It arrived on-site on 31 Aug.  Installation is scheduled for 21-24 Sept.  This unit includes GMAG and Iridium, but no system enclosure is needed for this site.

- GBO#4 - Destined for McGrath (Alaska), and scheduled for shipment in Sept.  Construction was begun and largely completed during Aug.

2. Production unit fabrication.

Construction of units is keeping apace with deployment schedule at this time.  In the process of troubleshooting ATHA problems, it was decided to add an AC Line Current monitor.  This required some design and fabrication of appropriate current sensors.  They will be easily retrofitted to fielded systems.

3. Schedule for GBO deployment.

- GBO#4 - Scheduled for installation at McGrath in early Oct.

- GBO#5 - Scheduled for installation at Lac de Gras (Canada) in early Oct.

- GBO#6 - Scheduled for installation at Flin Flon (Canada) in late Oct.

4. Software activities.

Software for both ASI and GMAG has continued to be upgraded, especially in response to field activities.  A CVS server was set up at UCB to begin logging software changes, and control versions.

5. ASI calibration completed.

Calibration of all sky imagers was completed in Aug. including one spare assembly.  The results show that all imagers exhibit very similar performance.

Planned activities for next period:

1. Deployment and construction activities will continue.

2. Since we are beginning deployments at new sites, we plan to have both Berkeley and Calgary personnel in attendance at some of the initial installations.  This will provide some training to insure that installations are done in a uniform manner.

3.3 Science Operations Centre Developments

No report this month

# 4  Education and Public Outreach

Respectfully Submitted,

THEMIS E/PO scientists Nahide Craig, Laura Peticolas

Formal Education:

First E/PO Ground Base Magnetometer is installed:

L. Peticolas traveled to Carson City, NV on August 27th where she met with D. Pierce of UCLA, R. Collier, and the IT personnel at the Western Nevada Community College and the first E/PO magnetometer is installed.  After much digging and testing and working with the computer, it worked!  Data reached the computer and displayed it and went to UCLA.

Through the Yahoo group for the THEMIS GEONS teachers comprised of an email system, a chat session, file uploading capabilities, a calendar of events, web links, and a survey function, we have established further communication with the GEONS Teachers.

GEONS teachers have begun school and are beginning to share the THEMIS magnetometer science with other teachers and their community.  Vic Trautman, the science teacher in Petersburg, AK, has done a radio interview about the THEMIS project.

The web pages for the GEONS teachers as part of the THEMIS E/PO web site is further populated with photographs of schools, teachers, and students as the teachers provide the photographs.  See: http://ds9.ssl.Berkeley.edu/themis/geons_schools.html.

We are collecting various resources that are presented at the GEONS workshop to mail to the teachers. These are VHS Movies related to Space weather and all the PowerPoint presentations made during the 3 day workshop. By the end of September they will be mailed to all the 10 schools.

L. Peticolas continued working with Stewart Harris and Jim Keenan of the accounting to communicate with and prepare a contract for the McGrath School operating under the Iditarod School District, in AK.

Public Outreach

In addition to the Formal Education THEMIS E/PO web, the front page was updated with "The Latest" containing the new GEONS pages and the THEMIS flyer.  The News and Events page was also updated with current THEMIS events.

Cross Cutting:

THEMIS E/PO plan using the proposed newly developed review guidelines was submitted as part of the ‘White Paper”. L. Peticolas and N. Craig traveled to NASA HQ and N. Craig responded to clarifying questions from the Panel as part of the Panel's overall deliberations concerning our program.

We are working with a graphic designer and the management team on the design of a THEMIS logo and patch.

We are updating the THEMIS flier for the CORE. They want 10,000 copies by the end of September.

# 5  Problems

## Outstanding Problems

## New Problems / Problem Avoidance

The probe mass exceeds its allocation and steps must be taken to effect either a mass reduction on the spacecraft, or an increase in the delta-V capabilities, or a reduction of mission fuel usage.

## Resolved Problems

The Probe thermal design was completed and reviewed during the period to everyone's satisfaction. It is no longer an outstanding problem.

# 6  Risk Management

The Risk Management Board (RMB) has been notified by the IIRT that since it's conclusions are not part of the overall mission level risk board, there is little use in its existence. As a result, the RMB is awaiting new instructions as to how to integrate into the mission level RMB, if that is what GSFC desires.

# 7  Performance Assurance

Reported by Ron Jackson

#### Equipment Calibration

Equipment calibrations proceeding on schedule.

#### Compliance to ESD requirements

Training and certification is 90% complete.

2 workstations setup and working.

ESD table top audits checkout ok.

#### Workmanship Procedures/Processes

PCB/FGE, Coupons sent for evaluation at GSFC

Approved by GSFC – BEB Coupons

ESA anode boards, THANC and TLANC sent to Valley circuits.

DCB at Dynamic Proto for board fab.

Flight assembly in process at Jackson & Tull - PCB/FGE

#### Assembly Instructions/ BOM

BEB, PCB/FGE - complete

DCB, DAP - AI and BOM 50% complete

EFI preamp - Cold temp qualification/Part control board review in process.

ESA ETU in process.

#### Evaluate/Audit Contractor Shipments

Total number of EEE items received -92 shipments

Total number of EEE items received discrepant-15%

Type of EEE part discrepancies:

Wrong part number delivered vs PO.

Missing Certificate of Conformance.

Qty shipped exceeds qty on PO.

Vendor audits - None

#### Clean Room Control

No change - Large clean room still under refurbishment.

#### Data Packages and Logbooks

BEB testing in progress

#### Nonconformance Reports and Problem Reports

None

#### Material Handling and Shelf Life Storage

- Limited shelf items in house

DAG213, Epoxy Patch 1C, Hypo EA9309, EA9361, Taco BA2151, BA2116, RTV566, and Quester Solder Paste WS750

- Mechanical group has between 95% to 98% of all items in house.

Iridite 15 Magnesium, an airborne connector has been ordered.

# 8  IV&V

Reported by David King

1. IDPU Flight Software Phase I has been delivered to IV&V for review.

2. Themis has now responded to IV&V Flight Software Requirements comments as follows:

BAU 95 of 104 (91%) and IDPU 46 0f 54 (85%).

# 9  Safety

Reported by David King

1. Feedback has been received from KSC on Section 3 of the Themis

EWR127-1 Tailoring Sheets.

2. The information to resolve the significant outstanding Themis Safety issues to be completed in September by GSFC. These outstanding issues include the following:

  - Off-loading Propellant

  - Number of Doors

  - Pyro Category Classification

  - Due Dates for Themis KSC Safety Deliverables