## Summary
IIRT CDR | Total | Open | Responded To | Closed
|  | (No Response) | (No Reviewer Concurrence) | (Reviewer Concurrence)
Instruments Action Items | 12 | 12 | 0 | 0

## Instrument
\1 Management\1.1 Management\1.1.4 Reviews and Deliverables\PhaseC_MDR\IIRT CDR RFA Status List and Folders\Themis Instrument IIRT CDR RFA Status List.xls
Action Items from THEMIS Instrument IIRT CDR June 14-18, 2004
RFA # | Status | Originator | Category | Due Date | Title | Action Requested | Supporting Rationale | Assignee | Notes
MCDR-1 | Open | L. Fantano | Systems Engineering | 2004-07-16 | Operations Requirement to Preclude >20 Minutes S/C Illumination | Verify that on-orbit launch operations requirement exists that precludes the possibility that the Sun can continuously illuminate any probe surface for time periods greater than 20 minutes from fairing deployment to probe spin initiation. Also verify that key probe surfaces that need to be solar illuminated intermittently are. | The probe thermal design does not accommodate continuous solar illumination on key probe surfaces. Solar arrays also require minimum solar exposure so that minimum temperature requirement are not violated. Verify that the mission requirements set precludes these possibilities. | Tom Ajluni
MCDR-2 | Open | R. Schnurr | Systems Engineering | 2004-10-31 | Perform Vulnerability Assessment of the Space Asset | Work with GSFC to perform a vulnerability assessment of the space asset and determine what if any protection should be implemented. | Any significant vulnerability must be identified, quantified, mitigated or included in the mission success model. | Tom Ajluni
MCDR-3 | Open | R. Schnurr | Operations | 2004-10-31 | Establish Sufficient TDRS Forward Link Margin | Revisit TDRS link margin to establish sufficient forward link margin and insure any new operational constraints are included in the operations plan. | Current Forward link margin (1.6 dB) is not sufficient at CDR. | Manfred Bester
MCDR-4 | Open | T. Ford | Testing | 2004-10-31 | Orbital Debris Assessment | Expedite submittal of updated ODA to NASA HQ. Updated ODA needs to describe the new risks associated with the re-pressurization system including those related to on-orbit explosion and new single pint failure that could jeopardize ability to perform end-of-life maneuvers. | The sooner HQ approves the plan the sooner the risk of design changes or additional justification can be retired. | Peter Harvey
MCDR-5 | Open | B. Taylor | Testing | 2004-07-16 | Re-evaluate Decision to not Perform TVAC on Redesigned AXB | UCB should reconsider not doing TVAC testing on the “redesigned” AXB. It would appear prudent, as a risk reduction item, to do this to find problems early. | It is accepted that deployment of AXB in TVAC will be done at the flight unit level; however problems found there will have a significant impact. | Paul Turin
MCDR-6 | Open | L. Fantano | Thermal | 2004-07-16 | Thermal Optical Properties | Submit thermal model optical property assumptions to the GSFC Contamination and Thermal Coatings Group for review to assure that they bound degraded optical property ranges that fully consider degradation effects caused by solar exposure, contamination, plume effects, and lifetime considerations. | It is particularly important that thermal optical property assumptions used to analyze a passive thermal design bound actual ranges that will be experienced. | Chris Smith
MCDR-7 | Open | L. Fantano | Thermal | 2004-07-09 | AXB Preamp | Investigate alternatives to resolve AXB Preamplifier minimum temperature limit violation. | Thermal model results showed that ACB Preamplifier violated its -75 C temperature limit by roughly 44 C. This issue needs to be resolved. Potential solutions include:a) Re-qualification testing that enables reduction of temperature requirement. b) Redesign mechanical packaging to introduce a thermal resistance between TO-99 can and outer shell.c) Finding an alternative external thermal control coating with a lower emittance to replace the Dag-213 black coating. Or any other solution that seems appropriate. | Chris Smith
MCDR-8 | Open | L. Fantano | Thermal | 2004-07-16 | FGM & SCM Pre-Deployment Temperature Limit Violation | Resolve FGM & SCM Pre-Deployment temperature violations. | FGM & SCM Pre-Deployment temperatures prior to deployment were shown to exceed required temperature limits. | Chris Smith
MCDR-9 | Open | L. Fantano | Thermal | 2004-07-16 | Adhesive Temperature Limits | Identify all adhesives employed in the various instrument designs. Determine temperature requirements associated with each. Verify that adhesive temperature limits are not violated and that appropriate adhesives have been chosen by the instrument leads. | Adhesive temperature limits need to be satisfied. | Chris Smith
MCDR-10 | Open | L. Fantano | Thermal | 2004-09-15 | Instrument Flight Instrumentation Plan | Develop Flight Instrumentation Plan. Provide plan. | No information was provided about the planned flight instrumentation. Temperature sensors should be located at all temperature sensitive locations deemed as being mission critical. | Ellen Taylor
MCDR-11 | Open | J. Hair | Systems Engineering | 2004-07-16 | Power Options to Avoid Over Power Conditions on Nano-Muscles | For all nano-muscle and SMA applications, evaluate whether an applied power timing scenario exists such that the duration of the power pulse sent to the SMA circuit (SMA & micro-switches) is long enough to allow for the SMA to actuate and trip the micro-switch, but short enough to not cause over-power damage to the SMA in case the micro-switch fails to open the circuit. If such a timing scenario exists, explain how it will be implemented to protect the SMA nano-muscle | SMA devices can be sensitive to over-powering where the material anneals, degrading performance. Micro-switches are not always reliable and may allow the SMA to become damaged. | Ellen Taylor
MCDR-12 | Open | J. Hair | Mechanical | 2004-07-16 | Include Harness in Magnetometer Boom Friction Assessments | For the magnetometer booms, include harness across hinge lines in hinge friction assessments. Perform tests to quantify harness friction in proper configuration, over-wrap, and temperature to support values used in assessment. Include harness or mock-up harness in hinge torque margin tests and deployment tests. | Torque margin may be high and harness friction may be low, but it must be included in assessments and tests. Otherwise, torque margin verification may not be complete. Over-wrap and over-wrap techniques can add significantly to harness resistive torques. | Paul Turin
MCDR-13 | Open | J. Hair | Systems Engineering | 2004-07-16 | SST Attenuator Mechanism Requirements | For the SST attenuator mechanism, review/coordinate the following:1) Cycles/orbit operations plan with comments on when cycles may be increased.2) Preferred open or closed state of attenuator based on orbit position (P#) to optimize life versus science in case life is concern.3) Required minimum test cycles.4) Risk assessment based on premature failure.5) QA of micro-switches. | There seems to be a disconnect between instrument scientist desires and mission level requirements. Possible schedule risk exists if additional design iterations are needed based on life tests. | Ellen Taylor
MCDR-14 | Open | J. Hair | Systems Engineering | 2004-07-16 | Evaluate Instr. Interface Interactions While Under Thermal Test | Evaluate instrument and, in particular, Mag Booms mechanical interface interactions and loading conditions while under thermal test on instrument suite test platform. In the case of the Mag Booms, axial relief should not be assumed to be provided by the V-guide at the frangibolt locations. Due to the high pre-load, friction will prevent the frangibolt or bolt from sliding I the bolt. This may apply in general in addition to this specific case, so evaluate the axial compliance assumptions for Mag Boom constraints. | The flight structure is low CTE composite, while the proposed test platform is aluminum. This difference will subject the instruments and booms to different interface loading conditions during thermal tests. | Paul Turin
MCDR-15 | Open | R. Klar | Software | 2004-07-09 | Clearly Define Test Strategy for IDPU Software | Clearly define how and when builds will be generated (in the Software Development Plan). Although it has been indicated that software will be developed in phases, it is not clear how and when requirements will be verified. It is necessary to clearly define a plan for creating builds and for verification of requirements with each build. Regression testing of requirements with each build is encouraged.Levels of testing should be clearly defined (e.g. software unit testing, software integration testing, and acceptance testing). At each level of testing, the test environment should be described in detail. It is important to state what resources will be required (i.e. ITOS, test programs, automated test procedures, instrument hardware, simulators, test equipment, etc.)Describe at what level of testing each of the component requirements will be tested. If possible, requirements should be re-tested when the software is fully integrated (for acceptance testing). Describe how test results will be captured/documented at each level. | The Test Strategy for the IDPU software is not adequately described in the CDR presentation and supporting documentation. | Peter Harvey
IV&V should be planned for software acceptance tests.
MCDR-16 | Open | R. Klar | Software | 2004-07-09 | Complete/Clarify IDPU Software Design Documents | Resolve TBDs in the design documents. This information should be complete at CDR.Document thm_fsw_204 internally is labeled (probably erroneously) thm_fsw_002. It includes descriptions of the other modules. This appears to be in error. Diagrams of important data structures appear to be missing.In some cases the design documentation simply restates the requirement (sometimes with different wording). Remove this redundancy. The word “shall” indicates a requirement and should only be used in the SRS. The SRS should serve as the basis for acceptance testing and software verification.From the dates on the design documentation, it does not appear to have been updated since March. Significant changes were made to the SRS as a result of the peer review that do not appear to be reflected in the design documentation.The design documentation should be peer reviewed and baselined. There should be a sign-off procedure to indicate that the design documentation has been reviewed and is complete. | The software design should be complete before proceeding with development of code. | Peter Harvey
The design documentation should give a description of the top-level structure and organization of the software. It should also give some details of the major data structures and interfaces between components.Since modes are referenced in the SRS, the mode definitions should be moved to the SRS. The design documentation should be derived from the SRS. The SRS should not have to refer to the design documents.
MCDR-R01 | Open | T. Ford | Systems Engineering | Recommendation | Provide Periodic Mission Design/Propellant Budgeting Insight | Project should provide periodic mission design/propellant budgeting oversight to help assure propellant usage is being best used to satisfy science mission, contingency operations, extended mission and end-of-life operations requirements and objections. | Delta-V is a critical resource which needs considerable attention through the design cycle through mission operations.