## Sheet1
VRN | Requirement | Status | Plan Date | Verification Plan | NASA Discipline | NASA Engineer | Verification Document (Ver. Doc.) Title | Ver. Doc. Number | Method | Ver. Doc. Date | Ver. Doc. Library #
3.1.1.1 | Reference Figure 3-1, Payload Coordinate System. The coordinate system is placed at the payload interface plane (launch vehicle station 413. 77) on the geometric centerline of the launch vehicle (i.e., at location [413.77, 0, 0] inches in the launch vehicle geometric coordinate frame). The Z-axis is directed forward through the probe carrier normal to the attachment plane. The X-axis runs directly under the center of the Probe A and Probe B separation rings perpendicular to the -Z-axis. The Y-axis completes a right-handed orthogonal triad. | Closed | 2006-05-01 | Verify final release of Compatibility Drawing and ICD are in agreement. | Mechanical | Gregory | Mission Compatibility Drawing, THEMIS | ID90703 | I | 2006-04-14 | ELVL-2005-0034273
3.1.1.2 | The launch vehicle coordinate system shall be as shown in Figure 3-3, Launch Vehicle Axes. Quad I alligns with the LV Y-axis. LV clocking is measured from LV Quad IV (0/360°) toward LV Quad I (90°). | Closed | 2006-05-01 | Verify final release of Compatibility Drawing and ICD are in agreement. | Mechanical | Gregory | Mission Compatibility Drawing, THEMIS | ID90703 | I | 2006-04-14 | ELVL-2005-0034273
3.1.2.1 | With the exception of components identified in this section, the payload shall remain within the allowable payload fairing envelope in accordance with Figure 3-4, Payload Fairing Envelope. | Closed | 2006-05-01 | Verify Compatibility Drawing and ICD are in agreement. | Mechanical | Gregory | Mission Compatibility Drawing, THEMIS | ID90703 | I | 2006-04-14 | ELVL-2005-0034273
3.1.2.1.1 (a) | Payload components within 2.0 inches of the envelope shall be as listed in Table 3-1, Payload Components Close to the Fairing Envelope. Reference the Payload Compatibility Drawing for details. | Closed | 2006-04-01 | Review Spacecraft Drawings. | Mechanical | Gregory | THEMIS PCA | C0101 | I | 2006-03-13
3.1.2.1.1 (b) | Payload components within 2.0 inches of the envelope shall be as listed in Table 3-1, Payload Components Close to the Fairing Envelope. Reference the Payload Compatibility Drawing for details. | Closed | 2006-08-14 | Review final payload fairing clearance analysis. | Mechanical | Gregory | Payload Fairing Clearance Analysis-THEMIS | A3-DM10-NLS-060450 | A | 2006-05-04 | ELVL-2006-0035259
3.1.2.1.2 (a) | Payload components within 2.0 inches of the envelope shall be as listed in Table 3-2, Payload Components Close to the Interface Plane Envelope. Reference the Payload Compatibility Drawing for details. | Closed | 2006-04-01 | Review Spacecraft drawings. | Mechanical | Gregory | THEMIS PCA | C0101 | I | 2006-03-13
3.1.2.1.2 (b) | Payload components within 2.0 inches of the envelope shall be as listed in Table 3-2, Payload Components Close to the Interface Plane Envelope. Reference the Payload Compatibility Drawing for details. | Open | 2007-01-30 | Review final payload pre-separation analysis. | Controls | Wikander |  |  | A
3.1.2.1.2 (c) | Payload components within 2.0 inches of the envelope shall be as listed in Table 3-2, Payload Components Close to the Interface Plane Envelope. Reference the Payload Compatibility Drawing for details. | Closed | 2006-08-14 | Review final payload fairing clearance analysis. | Mechanical | Gregory | Payload Fairing Clearance Analysis-THEMIS | A3-DM10-NLS-060450 | A | 2006-05-04 | ELVL-2006-0035259
3.1.2.1.2 (d) | Payload components within 2.0 inches of the envelope shall be as listed in Table 3-2, Payload Components Close to the Interface Plane Envelope. Reference the Payload Compatibility Drawing for details. | Closed | 2006-05-15 | Inspect as-built hardware. | Mechanical | Gregory | Delta PAF & SC Fitcheck | IT83232 | I | 2006-05-03 | ELVL-2006-0035142
3.1.2.2 (a) | The fairing shall incorporate access doors in accordance with Table 3-3, Access Doors. No RF windows are required. | Closed | 2006-10-23 | Inspect fairing production drawings. | Mechanical | Little | Fairing Assembly Drawing | 1D90778-C | I | 2006-08-04
3.1.2.2 (b) | The fairing shall incorporate access doors in accordance with Table 3-3, Access Doors. No RF windows are required. | Closed | 2006-11-03 | Inspect as-built fairing at factory. | Mechanical | Little | N/A | N/A | I |  | N/A
3.1.3.1 (1a) | The launch vehicle shall use a 3712 bolted payload attach fitting (PAF). Details of the PAF are shown in Figures 3-5, Payload Attach Fitting, and 3-6, Payload Attach Fitting/Probe Carrier Interface. | Closed | 2006-05-01 | Review final release of Payload Compatibility Drawing. | Mechanical | Gregory | Mission Compatibility Drawing, THEMIS | ID90703 | I | 2006-04-14 | ELVL-2005-0034273
3.1.3.1 (1b) | The launch vehicle shall use a 3712 bolted payload attach fitting (PAF). Details of the PAF are shown in Figures 3-5, Payload Attach Fitting, and 3-6, Payload Attach Fitting/Probe Carrier Interface. | Closed | 2006-05-15 | Witness fitcheck. | Mechanical | Gregory | Delta PAF & SC Fitcheck | IT83232 | I T | 2006-05-03 | ELVL-2006-0035142
3.1.3.1 (1c) | The launch vehicle shall use a 3712 bolted payload attach fitting (PAF). Details of the PAF are shown in Figures 3-5, Payload Attach Fitting, and 3-6, Payload Attach Fitting/Probe Carrier Interface. | Open | 2006-10-07 | Witness SC mate. | Mechanical | Gregory |  |  | I
3.1.3.1 (2a) | Boeing shall provide the 24 bolts necessary for payload mating to the PAF. | Closed | 2006-05-15 | Witness fitcheck. | Mechanical | Gregory | Delta PAF & SC Fitcheck | IT83232 | I T | 2006-05-03 | ELVL-2006-0035142
3.1.3.1 (2b) | Boeing shall provide the 24 bolts necessary for payload mating to the PAF. | Open | 2006-10-07 | Witness SC mate. | Mechanical | Gregory |  |  | I
3.1.3.2 (a) | The Probe Carrier shall be compatible with a Delta II 3712 bolted PAF by satisfying the constraints shown in Figures 3-6, Payload Attach Fitting/Probe Carrier Interface, 3-6a, Payload Attach Fitting/Probe Carrier Interface Section View, and 3-7, Probe Carrier Interface to PAF. | Open | 2006-04-01 | Review SC drawings. | Mechanical | Gregory | THEMIS PCA | C0101 | I | 2006-03-13
3.1.3.2 (b) | The Probe Carrier shall be compatible with a Delta II 3712 bolted PAF by satisfying the constraints shown in Figures 3-6, Payload Attach Fitting/Probe Carrier Interface, 3-6a, Payload Attach Fitting/Probe Carrier Interface Section View, and 3-7, Probe Carrier Interface to PAF. | Open | 2006-05-15 | Inspect during fitcheck. | Mechanical | Gregory | Delta PAF & SC Fitcheck | IT83232 | I T | 2006-05-03 | ELVL-2006-0035142
3.1.3.2 (c) | The Probe Carrier shall be compatible with a Delta II 3712 bolted PAF by satisfying the constraints shown in Figures 3-6, Payload Attach Fitting/Probe Carrier Interface, 3-6a, Payload Attach Fitting/Probe Carrier Interface Section View, and 3-7, Probe Carrier Interface to PAF. | Open | 2006-10-07 | Inspect during SC mate. | Mechanical | Gregory |  |  | I
3.1.3.3 (a) | The payload to launch vehicle PAF electrical bonding shall have a resistance of less than 2.5 milliohms. | Closed | 2006-05-15 | Verify resistance measurement during fitcheck spacecraft mate. | Electrical | Moore | Delta PAF & SC Fitcheck | IT83232 | T | 2006-04-03 | ELVL-2006-0035142
3.1.3.3 (b) | The payload to launch vehicle PAF electrical bonding shall have a resistance of less than 2.5 milliohms. | Open | 2006-10-07 | Verify resistance measurement during flight spacecraft mate. | Electrical | Moore | V(F) 132 T4 Payload Attach Fitting & Spacecraft Processing Proc, SC Mate, step which measures resistance. |  | T
3.1.3.4 (a) | A launch vehicle/payload separation system is not required. The launch vehicle shall provide a redundant, verifiable, ordnance signal at the launch vehicle/payload interface to initiate the probe separation sequence. The ordnance interface to the payload is at two manifold blocks located on the PC as shown in Figure 3-8, Separation Ordnance Interface. | Closed | 2006-04-28 | Review wiring from pyro switches to third stage TM system. | Electrical | Moore | -Pyro Switches -Instrumentation Wire Harness -Separation Signal Monitoring Wire Harness (SEPARATION SEQUENCING SYSTEM, THEMIS 1D90707) | -ID60648 - 513 -ID90822 - 1 -ID90823 - 1 | I | 2005-10-17
3.1.3.4 (b) | A launch vehicle/payload separation system is not required. The launch vehicle shall provide a redundant, verifiable, ordnance signal at the launch vehicle/payload interface to initiate the probe separation sequence. The ordnance interface to the payload is at two manifold blocks located on the PC as shown in Figure 3-8, Separation Ordnance Interface. | Open | 2006-08-15 | Testing per LPD - pyro switch activation simulated with breakout box. | Electrical | Moore | Composite Electrical Checks | G206 | T
3.1.5 (a) | The launch vehicle shall incorporate the mission insignia shown in Figure 3-9, Mission Insignia, on the Quad IV surface. The insignia will be scaled to maximize its size within an 8’ x 8’ area. | Closed | 2006-04-28 | Verify delivery of insignia graphic to LV. | IE | Reid |  |  | I
3.1.5 (b) | The launch vehicle shall incorporate the mission insignia shown in Figure 3-9, Mission Insignia, on the Quad IV surface. The insignia will be scaled to maximize its size within an 8’ x 8’ area. | Open | 2006-09-20 | Inspect insignia on LV. | Mechanical | Gregory |  |  | I
3.1.6.1 (1a) | THEMIS shall use two 61-pin interface non-separating connectors as defined in Table 3-4, Interface Connectors. | Closed | 2006-04-14 | Review SC to Blockhouse wiring diagram. | Electrical | Moore | Payload-to-Blockhouse Wiring, THEMIS | ID91913-1 Rev A | I | 2006-06-02
3.1.6.1 (1b) | THEMIS shall use two 61-pin interface non-separating connectors as defined in Table 3-4, Interface Connectors. | Open | 2006-09-15 | Verify harness during pad ring out. | Electrical | Moore | Pre test Preps | F20 | I | 2006-06-02
3.1.6.1 (2a) | The electrical connector interface shall be as shown in Figure 3-10, Payload/PAF Electrical Connectors. | Open | 2006-04-14 | Review SC to Blockhouse wiring diagram. | Electrical | Moore | Payload-to-Blockhouse Wiring, THEMIS | ID91913-1 Rev A | I | 2006-06-02
3.1.6.1 (2b) | The electrical connector interface shall be as shown in Figure 3-10, Payload/PAF Electrical Connectors. | Open | 2006-09-15 | Verify harness during pad ring out. | Electrical | Moore | Pre test Preps | F20 | I
3.1.6.1 (3) | Boeing shall furnish the THEMIS Payload three each of J1 and J2, and one each of P1 and P2, which will be shipped to Swales Aerospace. | Closed | 2005-12-15 | Verify shipment of hardware from Boeing. | Electrical | Moore | Boeing Tracking number 727792908994 ref #00536.2.2.1.2.1.01.02 |  | I | 2006-03-03
3.1.6.1 (4) | THEMIS shall furnish 10-pin connector halves P3 and J3- one plug and one socket, for a probe separation monitor telemetry interface. The electrical connector interface shall be as shown in Figure 3-[TBD], Probe Separation Monitor Electrical Connector. | Closed | 2006-04-28 | Verify shipment of hardware from Swales. | Electrical | Moore | Delta PAF & SC Fitcheck |  | I | 2006-04-03
3.1.6.2 (1a) | Connector pin assignments shall be in accordance with Tables 3-5, 3-6 and 3-[TBD] Connector Pin Assignments- P1, P2 and P3, respectively. | Closed | 2006-04-14 | Review SC to Bockhouse wiring diagram. | Electrical | Moore | Payload-to-Blockhouse Wiring, THEMIS | ID91913-1 Rev A | I | 2006-06-02
3.1.6.2 (1b) | Connector pin assignments shall be in accordance with Tables 3-5, 3-6 and 3-[TBD] Connector Pin Assignments- P1, P2 and P3, respectively. | Closed | 2006-03-23 | Review SC wiring requirements. | Electrical | Moore | LV Umbilical PL Wiring Requirements | SAI - TM- 2785 Rev A | I | 2005-07-22
3.1.6.2 (1c) | Connector pin assignments shall be in accordance with Tables 3-5, 3-6 and 3-[TBD] Connector Pin Assignments- P1, P2 and P3, respectively. | Open | 2006-09-15 | Verify harness during pad ring-out. | Electrical | Moore | Pre test Preps | F20 | I
3.1.6.2 (2a) | Maximum current through any pin shall not exceed 10 milliamps at liftoff (LV to ground connector disconnect). | Closed | 2006-04-14 | Review SC to Blockhouse wiring diagram. | Electrical | Moore | Payload-to-Blockhouse Wiring, THEMIS | ID91913-1 Rev A | I | 2006-06-02
3.1.6.2 (2b) | Maximum current through any pin shall not exceed 10 milliamps at liftoff (LV to ground connector disconnect). | Open | 2006-11-17 | Review SC launch procedure. | Electrical | Moore | SC Countdown Procedure | THM_MINT_PROC_077B | I | 2006-10-18
3.1.6.3 (a) | The 3rd Stage telemetry system shall provide confirmation that an ordnance signal was transmitted to the payload to initiate the probe separation sequence. | Closed | 2006-04-28 | Review wiring from pyro switches to third stage TM system. | Electrical | Moore | -Pyro Switches -Instrumentation Wire Harness -Separation Signal Monitoring Wire Harness Telemetry Package 1D23249 | -ID60648 - 513 -ID90822 - 1 -ID90823 - 1 | I | 2005-04-19
3.1.6.3 (b) | The 3rd Stage telemetry system shall provide confirmation that an ordnance signal was transmitted to the payload to initiate the probe separation sequence. | Open | 2006-08-15 | Testing per LPD - pyro switch activation simulated with breakout box. | Electrical | Moore | Composite Electrical Checks | G206 | T
3.1.6.4 (1a) | THEMIS shall provide circuitry to monitor each THEMIS probe separation for input to Launch Vehicle telemetry. The THEMIS to LV probe separation monitoring circuit interface is shown in Figure 3-[TBD], Probe Separation Monitor Circuit. Figure 3-[TBD]. Probe Separation Monitor Circuit | Closed | 2006-06-30 | Review wiring from Probes 1-5, to the P3 Connector. | Electrical | Moore | THEMIS USPP Schematic | C04636a | I | 2006-02-03
3.1.6.4 (1b) | THEMIS shall provide circuitry to monitor each THEMIS probe separation for input to Launch Vehicle telemetry. The THEMIS to LV probe separation monitoring circuit interface is shown in Figure 3-[TBD], Probe Separation Monitor Circuit. Figure 3-[TBD]. Probe Separation Monitor Circuit | Open | 2006-07-24 | Test per LPD during side-by-side (3rd stage and probe carrier) testing. | Electrical | Moore | TBD | TBD | T
3.1.6.4 (2a) | THEMIS shall provide a single 0-5 Volt signal at the spacecraft to PAF interface designed to represent the individual probe separations. Output voltages for the 32 probe separation configuration states shall differ by at least 3%. | Closed | 2006-06-30 | Review resistor network architecture. | Electrical | Moore | THEMIS USPP Spec | SAI - SPEC - 1272 | I | 2005-08-03
3.1.6.4 (2b) | THEMIS shall provide a single 0-5 Volt signal at the spacecraft to PAF interface designed to represent the individual probe separations. Output voltages for the 32 probe separation configuration states shall differ by at least 3%. | Open | 2006-07-24 | Test per LPD during side-by-side (3rd stage and probe carrier) testing. | Electrical | Moore | TBD | TBD | T
3.1.6.4 (3a) | Output voltages for various probe separation conditions shall differ by greater than 3%. | Closed | 2006-06-30 | Review results from USPP PWB Flight Board Testing. | Electrical | Moore | USPP Flight Data | USPP_FLIGHT_DATA.xls | I | 2006-03-14
3.1.6.4 (3b) | Output voltages for various probe separation conditions shall differ by greater than 3%. | Open | 2006-07-24 | Test per LPD during side-by-side (3rd stage and probe carrier) testing. | Electrical | Moore | TBD | TBD | T
3.1.6.4 (4) | The THEMIS probe separation monitor circuitry shall be shielded and terminated to provide protection against radiated emissions and susceptibility, in accordance with NASA-STD-8739.4. | Open | 2006-06-30 | Review shielding and termination of the probe sep monitor harness. | Electrical | Moore | THEMIS USPP Harness | C0437b | I | 2006-02-23
3.1.6.4 (5a) | The LV shall provide a 28± TBS VDC source and wiring to a connector at the spacecraft to PAF interface for THEMIS probe separation monitor circuitry. | Open | 2006-06-30 | Review Instrumentation Wire Harness Drawing. | Electrical | Moore | THEMIS Instrumentation Wire Harness | ID90822 - 1 | I
3.1.6.4 (5b) | The LV shall provide a 28± TBS VDC source and wiring to a connector at the spacecraft to PAF interface for THEMIS probe separation monitor circuitry. | Open | 2006-07-24 | Test per LPD during side-by-side (3rd stage and probe carrier) testing. | Electrical | Moore | TBD | TBD | T
3.1.6.4 (6a) | To monitor the 0-5 V output, the LV shall provide electrical wiring from the connector interface to a frequency modulated (FM) voltage controlled oscillator (VCO) on the third stage telemetry system. | Open | 2006-06-30 | Review Instrumentation Wire Harness Drawing. | Electrical | Moore | THEMIS Instrumentation Wire Harness | ID90822 - 1 | I
3.1.6.4 (6b) | To monitor the 0-5 V output, the LV shall provide electrical wiring from the connector interface to a frequency modulated (FM) voltage controlled oscillator (VCO) on the third stage telemetry system. | Open | 2006-07-24 | Test per LPD during side-by-side (3rd stage and probe carrier) testing. | Electrical | Moore | TBD | TBD | T
3.1.6.5 | The LV 3rd stage shall transmit probe separation monitor telemetry. | Open | 2006-07-24 | Test per LPD during side-by-side (3rd stage and probe carrier) testing. | Electrical | Moore | TBD | TBD | T
3.1.8.1 (a) | FUT J box to blockhouse payload GSE wiring shall be in accordance with Table 3-7, FUT J Box to Blockhouse Payload GSE Wiring. | Closed | 2006-04-14 | Review SC to Blockhouse wiring diagram. | Electrical | Moore | Payload-to-Blockhouse Wiring, THEMIS | ID91913-1 Rev A | I | 2006-06-02
3.1.8.1 (b) | FUT J box to blockhouse payload GSE wiring shall be in accordance with Table 3-7, FUT J Box to Blockhouse Payload GSE Wiring. | Closed | 2006-03-23 | Review SC wiring requirements. | Electrical | Moore | LV Umbilical PL Wiring Requirements | SAI - TM - 2785 Rev A | I | 2005-07-27
3.1.8.1 (c) | FUT J box to blockhouse payload GSE wiring shall be in accordance with Table 3-7, FUT J Box to Blockhouse Payload GSE Wiring. | Open | 2006-09-19 | Inspect during SC console installation in the blockhouse. | Electrical | Moore |  |  | I
3.1.8.3 (1a) | THEMIS shall provide cabling, with labeled conductors (per Appendix A, Payload to Blockhouse Wiring Diagram), to connect their payload GSE to the blockhouse interface panel. | Closed | 2006-04-14 | Review SC to Blockhouse wiring diagram. | Electrical | Moore | Payload-to-Blockhouse Wiring, THEMIS | ID91913-1 Rev A | I | 2006-06-02
3.1.8.3 (1b) | THEMIS shall provide cabling, with labeled conductors (per Appendix A, Payload to Blockhouse Wiring Diagram), to connect their payload GSE to the blockhouse interface panel. | Open | 2006-09-19 | Inspect during SC console installation in the blockhouse. | Electrical | Moore
3.1.8.3 (2a) | The total length of payload GSE cabling shall be at least 35 feet long. | Closed | 2006-04-14 | Review SC to Blockhouse wiring diagram. | Electrical | Moore | Payload-to-Blockhouse Wiring, THEMIS | ID91913-1 Rev A | I | 2006-06-02
3.1.8.3 (2b) | The total length of payload GSE cabling shall be at least 35 feet long. | Open | 2006-09-19 | Inspect during SC console installation in the blockhouse. | Electrical | Moore
3.1.8.3 (3a) | Boeing shall provide connectors for the blockhouse interface. THEMIS will terminate the cable using these connectors. | Closed | 2006-04-14 | Review SC to Blockhouse wiring diagram. | Electrical | Moore | Payload-to-Blockhouse Wiring, THEMIS | ID91913-1 Rev A | I | 2006-06-02
3.1.8.3 (3b) | Boeing shall provide connectors for the blockhouse interface. THEMIS will terminate the cable using these connectors. | Open | 2006-09-19 | Inspect during SC console installation in the blockhouse. | Electrical | Moore |  |  | I
3.1.8.3 (4) | The payload will position 5 umbilical racks- one for each probe, and an RF rack in the blockhouse | Open | 2006-09-19 | Inspect during SC console installation in the blockhouse. | Mechanical | Gregory |  |  | I
3.2.1.1 (1) | The payload weight shall not exceed 829 kg (1828 lb). | Open | 2006-08-01 | Review preliminary mass property report. | Mechanical | Gregory | Spin Test Report |  | T
3.2.1.1 (2a) | Payload moments of inertia (MOI), products of inertia (POI) and center of gravity (CG) shall be within the ranges shown in Tables 3-8 through 3-10. All mass properties are cases with propellant (97% fill fraction). | Open | 2006-08-01 | Review preliminary mass property report. | Mechanical | Gregory | Spin Test Report |  | T
3.2.1.1 (2b) | Payload moments of inertia (MOI), products of inertia (POI) and center of gravity (CG) shall be within the ranges shown in Tables 3-8 through 3-10. All mass properties are cases with propellant (97% fill fraction). | Open | 2006-09-26 | Review final mass property report. | Mechanical | Gregory | Spin Test Report |  | T
3.2.1.1 (2c) | Payload moments of inertia (MOI), products of inertia (POI) and center of gravity (CG) shall be within the ranges shown in Tables 3-8 through 3-10. All mass properties are cases with propellant (97% fill fraction). | Open | 2007-02-20 | Review final mass property report. Verify values are within range of CLA model. | Loads | Gerace | Spin Test Report |  | T
3.2.1.1 (2d) | Payload moments of inertia (MOI), products of inertia (POI) and center of gravity (CG) shall be within the ranges shown in Tables 3-8 through 3-10. All mass properties are cases with propellant (97% fill fraction). | Open | 2006-08-27 | Review Spacecraft weighing procedure. Make sure equipmenct can provide the required accuracy. | Mechanical | Gregory |  |  | I
3.2.1.1 (2e) | Payload moments of inertia (MOI), products of inertia (POI) and center of gravity (CG) shall be within the ranges shown in Tables 3-8 through 3-10. All mass properties are cases with propellant (97% fill fraction). | Open | 2006-09-27 | Witness weighing. | Mechanical SMA | Gregory Schreiber |  |  | T
3.2.1.2 | THEMIS shall balance the payload such that the CG does not exceed 0.05 inch offset from the launch vehicle centerline, including measurement uncertainties. | Open | 2006-09-26 | Review spin test data and verify accuracy of reported values. | Controls | Wikander | Spin Test Report |  | T
3.2.1.3 | The payload shall be balanced to produce a 3-sigma principle axis misalignment not to exceed 0.25 degrees with respect to the LV centerline, including measurement uncertainties. | Open | 2006-09-26 | Review mass property report. | Mechanical | Gregory |  |  | I
3.2.1.4.1 | The payload shall ensure the worst case nutation time constant of the combined payload/third stage stack is greater than or equal to 150 seconds at ignition. | Closed | 2004-11-08 | Review nutation time constant analysis. | Controls | Wikander | Themis Nutation Time Constant Analysis. | SAI-ANYS-437 | A | 2004-10-07
3.2.1.4.2 | The payload shall ensure the worst case nutation time constant of the combined payload/third stage stack is greater than or equal to 50 seconds at burnout. | Closed | 2004-11-08 | Review nutation time constant analysis. | Controls | Wikander | Themis Nutation Time Constant Analysis. | SAI-ANYS-437 | A | 2004-10-07
3.2.1.5 | The depleted third stage mass properties prior to probe deployment shall be as shown in Table 3-11, Third Stage Mass Properties. | Open | 2006-09-26 | Review mass property report. | Mechanical | Gregory |  |  | I
3.3.1 | The launch vehicle shall place the payload in an orbit in accordance with Table 3-12, Orbit Characteristics, with reference to the J2000 coordinate system. | Open | 2006-05-22 | Review DTO inputs and DTO Analysis. | Flight Design | Benson | DTO-THEMIS | A3-DELTA-FLTSYS-06-211 | A | 2006-04-28 | ELVL-2006-0035261
3.3.2 | The launch window shall be 19.2 minutes in duration, centered on the optimal launch time for the target. | Open | 2006-05-22 | Review DTO inputs and DTO Analysis. | Flight Design | Benson | DTO-THEMIS | A3-DELTA-FLTSYS-06-211 | A | 2006-04-28 | ELVL-2006-0035261
3.3.3.2 (1) | Telemetry coverage shall be maintained throughout all powered phases of flight, and during the 3rd stage burn. | Closed | 2006-07-28 | Review RF link analysis. | RF/EMI | Brewer | RF Link Analysis | A3-N510-DELTA-SS-06-0117 | A | 2006-06-30 | ELVL-2006-0035504
3.3.3.2 (2) | Telemetry coverage shall be maintained during probe separation. | Closed | 2006-07-28 | Review RF link analysis. | RF/EMI | Brewer | RF Link Analysis | A3-N510-DELTA-SS-06-0117 | A | 2006-06-30 | ELVL-2006-0035504
3.3.3.3 | A 1 rpm (± 0.15 rpm) thermal roll shall be conducted with the Sun-to-vehicle vector normal to the 2nd stage thrust axis during the 2nd stage coast period between SECO-1 and the 2nd Stage Restart. The period of time in which the spacecraft is in a continuous non-rolling state shall not exceed 20 minutes in length. The tolerance on the BBQ roll attitude is 90 degrees ± 15 degrees where 90 degrees is defined as when the sun-to-vehicle vector is normal to the 2nd stage thrust axis and 0 degrees is defined as when the sun-to-vehicle vector is coincident with the 2nd stage thrust axis such that the top of the payload is exposed to the sun. | Open | 2006-06-30 | Review DTO inputs and DTO. Review control software and analysis. | Flight Design | Benson | DTO-THEMIS | A3-DELTA-FLTSYS-06-211 | A | 2006-04-28 | ELVL-2006-0035261
3.3.5.1 | The launch vehicle shall deliver the payload in accordance with Table 3-14, Pre-Separation Requirements. | Closed | 2006-06-30 | Pre-Separation Analysis. | Controls | Wikander | SC Sep Analysis-THEMIS | A3-DELTA-FLTSYS-05-564 | A | 2005-10-25 | ELVL-2005-0034240
3.3.5.2 | The 3rd stage velocity imparted from residual thrust following probe separation shall not exceed 2.294 fps (3-sigma maximum). | Closed | 2006-06-30 | Pre-Separation Analysis. | Controls | Wikander | SC Sep Analysis-THEMIS | A3-DELTA-FLTSYS-05-564 | A | 2005-10-25 | ELVL-2005-0034240
3.3.6.3 (1) | Boeing shall provide launch vehicle telemetry to the NASA ELV launch site telemetry lab in accordance with applicable contract and special task assignment provisions. | Open | 2006-07-01 | Review DMR Annex. | Flight Design | Benson |  |  | I
3.3.6.3 (2) | NASA shall arrange for telemetry data transport to GSFC Flight Dynamics Facility (FDF) for use in generating acquisition assistance messages. | Open | 2006-07-01 | Review DMR Annex. | Flight Design | Benson |  |  | I
3.3.6.3 (3) | Boeing shall incorporate payload acquisition assistance message requirements in the LV DMR Annex. | Open | 2006-07-01 | Review DMR Annex. | Flight Design | Benson |  |  | I
3.3.6.4.2 (1) | Boeing shall provide probe separation monitor telemetry. | Open | 2006-07-25 | Side by Side Test. | Electrical | Moore | Side by Side test procedure |  | T
3.3.6.4.2 (2) | Data shall be recorded and confirmation of separations relayed via real-time voice communications. | Open | 2006-07-25 | Side by Side Test. | Electrical | Moore | Side by Side test procedure |  | T
3.4.1 (a) | The stiffness of the payload structure shall produce fundamental frequencies above 35 Hz in the thrust axis and 15 Hz in the lateral axes with the payload hard mounted at the payload interface plane. | Closed | 2005-12-21 | Review Craig-Bampton Model. | Loads | Yunis | FEM-THEMIS | THEMIS_1105 | A | 2005-11-10
3.4.1 (b) | The stiffness of the payload structure shall produce fundamental frequencies above 35 Hz in the thrust axis and 15 Hz in the lateral axes with the payload hard mounted at the payload interface plane. | Closed | 2006-06-30 | Review Modal Survet Test Results. | Loads | Yunis | THEMIS PCA Modal Survey and Model Correlation Report | SAI-RPT-0712 | T | 2005-10-18
3.4.2 (a) | Load factors and launch acceleration shall be in accordance with Table 3-15, Structural Load Factors. | Closed | 2005-03-17 | Review Coupled Loads Analysis. | Loads | Yunis | THEMIS PDLC | A3-DELTA-STRDYN-2005-019 | A | 2005-03-03 | ELVL-2005-0034207
3.4.2 (b) | Load factors and launch acceleration shall be in accordance with Table 3-15, Structural Load Factors. | Closed | 2006-03-14 | Review VLC. | Loads | Yunis | THEMIS VLC | A3-DELTA-STRDYN-2006-032 | A | 2006-02-28 | ELVL-2006-0035103
3.4.3 | The limit peaked tensile line load imposed by the payload on the 3712 Bolted PAF interface shall not exceed 500 lb/in. | Closed | 2006-11-13 | Review PAF Strength Analysis | Stress | Young | Strength Assesssment of THEMIS 3712 Bolted PAF | A3-STRENGTH-2004-164-R3 | A | 2005-05-27 | ELVE-2004-0034214/R3
3.4.4.1 (a) | The P95/50 maximum predicted acoustic environment shall be as defined in Figure 3-11, P95/50 Payload Acoustic Environment Maximum Flight Levels. P95/50 is defined as 95% probability with 50% confidence. | Closed | 2006-07-01 | Verify the environment listed in the ICD applies to the THEMIS Mission. | Enviroments | Yunis | THEMIS Mission Specific Acoustic Analysis |  | A | 2004-12-01
3.4.4.1 (b) | The P95/50 maximum predicted acoustic environment shall be as defined in Figure 3-11, P95/50 Payload Acoustic Environment Maximum Flight Levels. P95/50 is defined as 95% probability with 50% confidence. | Closed | 2006-08-04 | Review SC Acoustic Test Results. | Enviroments | Yunis | THEMIS PCA Acoustic Test Report | THM-MINT-RPT-061 | T | 2006-09-29
3.4.4.2 (1a) | Sinusoidal vibration at the payload attach fitting base during flight shall not exceed levels shown in Table 3-16, Maximum Flight Sinusoidal Vibration Levels. | Closed | 2006-07-01 | Verify the environment listed in the ICD applies to the THEMIS Mission. | Enviroments | Yunis | THEMIS ICD | MDC 05H0026 | A | 2005-11-01 | ELVL-2005-0033985
3.4.4.2 (1b) | Sinusoidal vibration at the payload attach fitting base during flight shall not exceed levels shown in Table 3-16, Maximum Flight Sinusoidal Vibration Levels. | Closed | 2006-08-04 | Review SC sine vibe test results. | Enviroments | Yunis | THEMIS PCA Sine Test Report | SAI-RPT-788 | T | 2006-09-18
3.4.4.2 (2a) | Equivalent sinusoidal vibration levels during MECO at the payload interface (payload attach fitting top) shall not exceed levels shown in Table 3-17, MECO Equivalent Sine Levels. | Closed | 2006-07-01 | Verify the environment listed in the ICD applies to the THEMIS Mission. | Enviroments | Yunis | THEMIS ICD | MDC 05H0026 | A | 2005-11-01 | ELVL-2005-0033985
3.4.4.2 (2b) | Equivalent sinusoidal vibration levels during MECO at the payload interface (payload attach fitting top) shall not exceed levels shown in Table 3-17, MECO Equivalent Sine Levels. | Closed | 2006-08-04 | Review SC sinusoidal vibration test results. | Enviroments | Yunis | THEMIS 3rd Stage MECO Documentation | Pankow-06 | T | 2006-09-05
3.4.4.3 (a) | The maximum allowable shock spectrum at the payload interface shall be as shown in Table 3-18, Maximum Flight Shock Levels, and Figure 3-12, Maximum Flight Payload Interface Shock Environment. | Closed | 2006-07-01 | Verify the environment listed in the ICD applies to the THEMIS Mission. | Enviroments | Yunis | THEMIS ICD | MDC 05H0026 | A | 2005-11-01 | ELVL-2005-0033985
3.4.4.3 (b) | The maximum allowable shock spectrum at the payload interface shall be as shown in Table 3-18, Maximum Flight Shock Levels, and Figure 3-12, Maximum Flight Payload Interface Shock Environment. | Closed | 2006-07-01 | Review separation shock qual report. | Enviroments | Yunis | THEMIS PC structure acoustic and shock test report | SAI-RPT-0705 | T | 2005-09-30
3.4.5.2 (a) | The theoretical free molecular heating rate (for a flat plate normal to the free stream and based on the 1962 US standard atmosphere) at fairing separation shall not exceed 0.1 Btu/ft2-sec (1135 W/m2). | Open | 2006-07-26 | Review thermal analysis based on DTO trajectory. | Thermal | O'Neil |  |  | A
3.4.5.2 (b) | The theoretical free molecular heating rate (for a flat plate normal to the free stream and based on the 1962 US standard atmosphere) at fairing separation shall not exceed 0.1 Btu/ft2-sec (1135 W/m2). | Open | 2006-09-28 | Review thermal analysis based on BET trajectory. | Thermal | O'Neil |  |  | A
3.4.5.3.1 (a) | The heat flux generated by the spin rocket plume shall not exceed 0.25 BTU/ft2-s (2840 W/m2) for a one second duration at the payload interface plane. | Open | 2006-07-26 | Review thermal analysis based on DTO trajectory. | Thermal | O'Neil |  |  | A
3.4.5.3.1 (b) | The heat flux generated by the spin rocket plume shall not exceed 0.25 BTU/ft2-s (2840 W/m2) for a one second duration at the payload interface plane. | Open | 2006-09-28 | Review thermal analysis based on BET trajectory. | Thermal | O'Neil |  |  | A
3.4.5.3.2 (a) | The heat flux generated by the STAR 48 solid rocket motor plume shall not exceed 0.15 BTU/ft2-s (1703 W/m2) for an 86 second duration at the payload interface plane.. | Open | 2006-07-26 | Review thermal analysis based on DTO trajectory. | Thermal | O'Neil |  |  | A
3.4.5.3.2 (b) | The heat flux generated by the STAR 48 solid rocket motor plume shall not exceed 0.15 BTU/ft2-s (1703 W/m2) for an 86 second duration at the payload interface plane.. | Open | 2006-09-28 | Review thermal analysis based on BET trajectory. | Thermal | O'Neil |  |  | A
3.4.5.3.3 (a) | Third stage temperatures shall not exceed the values shown in Figure 3-13, Predicted Upper Stage Temperature History. | Open | 2006-07-26 | Review thermal analysis based on DTO trajectory. | Thermal | O'Neil |  |  | A
3.4.5.3.3 (b) | Third stage temperatures shall not exceed the values shown in Figure 3-13, Predicted Upper Stage Temperature History. | Open | 2006-09-28 | Review thermal analysis based on BET trajectory. | Thermal | O'Neil |  |  | A
3.4.6.1 | The RF environment experienced by the payload at launch vehicle interface on the day of launch at the launch site shall not exceed the values shown in Table 3-19, RF Environment. | Closed | 2006-10-01 | Review EMI/EMC & RF Compatability Analysis. | RF/EMI | Brewer | DII THEMIS EMC Analysis | AC-N520-AAP-05-015 | A | 2005-10-27 | ELVL-2005-0034242
3.4.6.2 | THEMIS radiated emissions at the payload/launch vehicle interface plane shall not exceed the levels shown in Figure 3-14. | Closed | 2006-05-12 | Document payload radiated emissions. | RF/EMI | Brewer | THEMIS EMC Test Report | 5132-06-035 | A | 2006-04-27
3.4.6.3 | To preclude RF fields that could be detrimental to launch vehicle ordnance or electronics, the payload shall have two independent inhibits to prohibit inadvertent RF transmissions. | Closed | 2006-07-28 | Review MSPSP RF inhibit assessment. | Electrical | Moore | THEMIS Payload MSPSP | THM-PA-002 | I | 2006-05-26 | ELVL-2006-0036263
3.4.6.4 (1) | Payload RF characteristics shall be as shown in Table 3-20. THEMIS shall not transmit from payload RF antennas after fairing installation. Prior to fairing installation, THEMIS will conduct an RF “Chirp test” involving RF radiation from each probe’s transmitter, one at a time for a few minutes each. THEMIS will provide a portable spectrum analyzer in the white room to verify transmitter turn on, output frequency and turn off. Probes will be tested one at a time. | Closed | 2006-05-12 | Review payload EMC test report. | RF/EMI | Brewer | DII THEMIS EMC Analysis | AC-N520-AAP-05-015 | A | 2005-10-27 | ELVL-2005-0034242
3.4.6.4 (2) | The Probe A transmitter will be commanded on via TDRSS at approximately 3 minutes prior to separation. The uplink frequency is 2101.80208 MHz. | Closed | 2006-07-28 | Review MSPSP RF inhibit assessment. | RF/EMI | Brewer | THEMIS Payload MSPSP | THM-PA-002 | A | 2006-05-26 | ELVL-2006-0036263
3.4.7 (1) | The fairing internal pressure environment shall be as shown in Figure 3-15, Delta II Payload Fairing Compartment Absolute Pressure Envelope. | Open | 2006-01-17 | Evaluate PLF venting analysis. | Thermal | O'Neil Duncil | PLF Venting Analysis THEMIS | Boeing Memo A3-Delta-FltSys-05-660 | A | 2005-12-14 | ELVL-2005-0034943
3.4.7 (2) | The pressure decay rate inside the fairing shall not exceed -0.6 psi/sec. | Open | 2006-01-17 | Evaluate PLF venting analysis. | Thermal | O'Neil Duncil | PLF Venting Analysis THEMIS | Boeing Memo A3-Delta-FltSys-05-660 | A | 2005-12-14
3.5.1 (a) | The payload temperature, humidity, and cleanliness environments during ground operations at the launch pad shall be as defined in Table 3-21, Launch Pad Air Conditioning Requirements. Small deviations for short periods are permissible to accommodate air conditioning system operational characteristics. Pre-coordinated levels outside this range are permitted for limited intervals as necessary to support operations. | Open | 2006-09-15 | Review SC procesing procedures. | Mechanical | Gregory |  |  | I
3.5.1 (b) | The payload temperature, humidity, and cleanliness environments during ground operations at the launch pad shall be as defined in Table 3-21, Launch Pad Air Conditioning Requirements. Small deviations for short periods are permissible to accommodate air conditioning system operational characteristics. Pre-coordinated levels outside this range are permitted for limited intervals as necessary to support operations. | Open | 2006-09-22 | Inspect LPDs for temperature, humidity, and cleanliness levels. | Contamination | Matthias |  |  | I
3.5.2.1 | The fairing airflow shall be between 1,300 and 1,700 scfm. When the payload is in the environmental shroud, the flow rate will be between 1000 and 1400 scfm. Pre-coordinated levels outside this range are permitted for limited intervals as necessary to support operations. | Open | 2006-09-01 | Verify proposed equipment can meet requirement per AC checkout procedure. | Mechanical | Gregory |  |  | I
3.5.2.2.1 | Boeing shall provide standard handling can purge during transportation to the pad. | Open | 2006-09-01 | Review SC can-up and SC erection procedures. | Mechanical | Gregory | SC Can-up SC Erection | D2-LPD-G209 D2-LPD-F1T1 | I
3.5.2.2.2 (1) | a. After transport to the pad, Boeing shall provide dry gaseous nitrogen per MIL-PRF-27401D, Type 1, Grade B from the facility purge system. b. THEMIS shall supply payload purge equipment used to purge the PCA purge bag, which will be installed at payload mate and will be removed during closeout activities prior to fairing installation. c. Boeing shall take samples of the purge gas and provide certification prior to commencing purge operations at the pad. Gas is to be supplied at pressure between 100 and 150 psig and regulated by equipment provided by UCB. | Open | 2006-07-15 | Review SC purge plan. (LS CCP Appendix) | Mechanical | Gregory | THEMIS Instrument Purge Plan | THM-SYS-032 Rev K | I | 2006-06-06
3.5.2.2.2 (2) | a. After transport to the pad, Boeing shall provide dry gaseous nitrogen per MIL-PRF-27401D, Type 1, Grade B from the facility purge system. b. THEMIS shall supply payload purge equipment used to purge the PCA purge bag, which will be installed at payload mate and will be removed during closeout activities prior to fairing installation. c. Boeing shall take samples of the purge gas and provide certification prior to commencing purge operations at the pad. Gas is to be supplied at pressure between 100 and 150 psig and regulated by equipment provided by UCB. | Open | 2007-01-20 | Verify equipment can meet requirement per GN2 checkout procedure. | Mechanical | Gregory |  |  | I
3.5.3.2 (a) | While at Space Launch Complex 17 the payload shall be covered with an environmental shroud prior to encapsulation in the fairing. | Open | 2006-09-25 | Verify Boeing processing facilities meet cleanliness requirements. | Contamination | Matthias |  |  | I
3.5.3.2 (b) | While at Space Launch Complex 17 the payload shall be covered with an environmental shroud prior to encapsulation in the fairing. | Open | 2006-10-03 | Verify system is properly installed and inspected. | Mechanical | Gregory |  |  | I
3.5.3.2 (c) | While at Space Launch Complex 17 the payload shall be covered with an environmental shroud prior to encapsulation in the fairing. | Open | 2006-10-03 | Verify proper operation of the system. | Mechanical | Gregory |  |  | I
3.5.3.3 (1a) | The third stage motor dome, PAF, and transport canister shall be cleaned and inspected to VC-3. | Open | 2006-06-16 | Review SC contamination control plan. | Contamination | Matthias | THEMIS LSCCP | THM_SYS_052 | I | 2006-05-25
3.5.3.3 (1b) | The third stage motor dome, PAF, and transport canister shall be cleaned and inspected to VC-3. | Open | 2006-09-25 | Verify requirements of VC-3 were met. | Contamination | Matthias |  |  | I
3.5.3.3 (2a) | The fairing shall be cleaned and inspected to VC-6. | Open | 2006-06-16 | Review SC contamination control plan. | Contamination | Matthias | THEMIS LSCCP | THM_SYS_052 | I | 2006-05-25
3.5.3.3 (2b) | The fairing shall be cleaned and inspected to VC-6. | Open | 2006-07-31 | Verify requirements of VC-6 were met. | Contamination | Matthias |  |  | I
3.5.3.3 (3) | THEMIS shall be notified 72 hours prior to cleaning so a payload representative may witness the procedure. | Open | 2006-07-15 | Review fairing cleaning procedure. | Contamination | Matthias | Fairing Cleaning | D2-M540-T3 | I
3.5.4.1 (a) | Boeing shall weigh and certify the weight of the payload to within ± 0.05% with a repeatability of ± 0.02%. | Open | 2006-09-01 | Review weigh procedure. | Mechanical | Gregory | SC Weighing | D2-LPD-G208, T1 | I
3.5.4.1 (b) | Boeing shall weigh and certify the weight of the payload to within ± 0.05% with a repeatability of ± 0.02%. | Open | 2006-09-25 | Attend weighing. | Mechanical | Gregory |  |  | T
3.5.4.2 (a) | THEMIS will perform spin balancing of the fueled payload at Astrotech. | Open | 2006-09-01 | Review spin balance procedure. | Mechanical | Gregory | THEMIS Spin Balance Procedure | THM-MINT-PROC-067 | I
3.5.4.2 (b) | THEMIS will perform spin balancing of the fueled payload at Astrotech. | Open | 2006-09-22 | Attend spin balance. | Mechanical | Gregory |  |  | T
3.5.5.1 | Personnel involved in working on, near or around the spacecraft or probe carrier shall adhere to the THEMIS Magnetics Control Plan (THM-SYS-002). | Closed | 2006-07-01 | Review magnetic control plan. | RF/EMI | Brewer | THEMIS Magnetic Control Plan | THM_SYS_002 Rev D | I | 2004-04-17
3.5.5.4 (1) | The spacecraft shall not be subjected to a field greater than 2 Gauss at distance of 10cm or closer. THEMIS will conduct a magnetic survey of all mechanical equipment, support structures and tools used during spacecraft integration prior to lifting the payload to the tower. Highly magnetic sources will be demagnetized or removed. | Closed | 2006-11-01 | Review magnetic control plan. Review Magnetic Screening and Degaussing Proc. Telecon on Mag Sensitivity. | IE | Reid | THEMIS Magnetic Control Plan THEMIS Magnetic Screening and Degaussing Procedure | THM_SYS_002 Rev D THM-MINT-PROC-126, 8/31/06 | I | 2004-04-17
3.5.5.4 (2) | Boeing shall provide standard facility propellant deservicing lines and GN2 per MIL-PRF-27401D, Type 1, Grade B, for THEMIS to connect to Probes A through E. Propellant line interface is TBS. | Open | 2006-09-14 | Review Sverdrup procedure. | Mechanical | Gregory | Contingency Offload Procedure |  | I
3.5.6.1 | Boeing shall provide GSE to support telemetry interface testing with the PC and LV third stage side-by-side. This comprises cabling from the probe separation monitor payload connector (P3) to the LV interface, and LV telemetry recording equipment. | Open | 2006-07-24 | Side by side test. | Electrical | Moore |  |  | T
3.5.6.2 | In the event of a contingency, Boeing shall provide capability for THEMIS to lift and operate their Battery Charge/Discharge rack and Solar Array Simulator rack, and associated equipment, in the White Room. This capability consists of 5 pairs of CMD/TLM lines configured as RS 422 and Ethernet access routed to the Blockhouse. Required THEMIS equipment weighs approximately 587.5 lbs and consists of the following: Battery Rack (19"(W) X 36"(D) X 50"(H)) ~425 lbs. (stand-alone) 6060B Electronic Load ~13.5 lbs. 34970A Data Acquisition Unit ~10.0 lbs. Dell Console (KVM) ~10.0 lbs. Dell PC ~10.0 lbs. Powerware 5125 UPS ~61.0 lbs. Sorensen DLM 40-15 DC P.S. ~10.0 lbs Battery Electronics Module ~50.0 lbs | Open | 2006-09-01 | Verify contingency capability exists at the launch site. | Electrical | Moore
3.5.7.1 | Boeing shall provide access accommodations to the locations described in Table 3-23, Pad Access Requirements. | Open | 2006-10-10 | Inspect access provided. | Mechanical | Gregory
3.5.7.2 | Boeing shall provide accommodations per Table 3-23, Pad Access Requirements. Access will be required to close out Probe A through Probe E fill and drain valves. | Open | 2006-10-14 | Verify access provided. | Mechanical | Gregory
3.6 | The payload shall comply with the requirements of EWR 127-1 or an approved tailored version. | Closed | 2006-07-28 | Review EWR 127-1 and Tailoring. | SMA | Loftin | EWR 127-1 |  | I
3.6.1 | Distance at which RF radiation flux density equals 1m W/cm2 for all antennas shall be 1 meter. | Closed | 2006-07-28 | Review MSPSP. | SMA | Loftin | THEMIS Payload MSPSP | THM-PA-002 | I | 2006-05-26 | ELVL-2006-0036263