## Sheet1
Date | Scope | Review | Status
2003-07-08 | Mission | SRR | Complete
2003-10-29 | Spacecraft | PDR | Complete
2006-05-31 | Payload | PDR | Complete
2003-11-12 | Mission | PDR | Complete
2004-06-14 | Spacecraft | CDR | Complete
2004-06-16 | Payload | CDR | Complete
2004-06-17 | Mission | CDR | Complete
2004-11-10 | Payload | F #2,3 PSR | Complete
2004-12-09 | Payload | Test Summary | Complete
2005-03-07 | Mission | MOR | Complete
2005-04-05 | Spacecraft | Test Summary | Complete
2005-05-02 | Payload | F #1 PER | Complete
2005-08-27 | Payload | F #2,3 PER | Complete
2005-09-21 | Payload | F #1 PSR | Complete
2005-11-10 | Payload | F #4,5 PER | Complete
2005-11-17 | Spacecraft | Bus #2 PSR | Complete
2006-03-16 | Mission | P2 PER | Complete
2006-03-23 | Spacecraft | Bus #3 PSR | Complete
2006-05-04 | Spacecraft | Bus #4 PSR | Complete
2006-05-05 | Payload | F #4,5 PSR | Complete
2006-05-31 | Spacecraft | Bus #1 PSR | Complete
2006-05-31 | Spacecraft | Carrier PSR | Complete
2006-06-12 | Spacecraft | Bus #5 PSR | Complete
2006-06-23 | Mission | P1,3,4,5 PER | Complete
2006-10-04 | Mission | FOR | Complete
2006-10-26 | Mission | PSR | Complete
2006-12-05 | Mission | Delta-PSR | Complete