TITLE: Use GSFC Standard Practice for Margins and Margin History		RFA CODE:  6

REQUESTED BY:  F. Martin

SPECIFIC REQUEST:  Display margins and margin history in a way acceptable by the GSFC management (i.e. AIAA standards, JPL standards).  This is a program risk that requires a mitigation plan.

SUPPORTING RATIONALE: Mass margin on THEMIS appears tight.  All data shown indicates that the Space Sciences Laboratory (SSL) has a good history on mass performance.  This needs to be put in context of what GSFC requires.

- RESPONSE

Contingency, Margin and Margin History as presented in the THEMIS Systems Engineering Management Plan (SEMP) is summarized below:

Contingency is defined as a percentage of resource (e.g., mass or power) added to an estimate as a provision for uncertainty.  Contingency is based on the level of maturity of the item.  Each item is identified as being in one of the following groups and the appropriate %contingency applied:

1. Concept: 25%

2. Design: 15%

3. Prior Build: 7.5%

4. Fabrication: 4%

5. Flight Build: 2%

Program Managers margin is defined as the amount of resource remaining when an estimate plus the associated contingencies are subtracted from the available quantity.  Margin% that doesn’t meet the following Margin Schedule will trigger a project level risk mitigation plan, resulting in possible descope of mission objectives.

1. Phase A Concept: > 30%

2. Preliminary Design Review (PDR): > 20%

3. Conceptual Design Review (CDR): > 15%

4. Pre-Environmental Review (PER): > 10%

5. Pre-Ship Review (PSR): 2% to 5%

This schedule is consistent with guidelines historic NASA project trends.  Page 62 of the NASA Systems Engineering Handbook, SP-6105, 1995, says "As an example, spacecraft dry mass tends to grow during Phases C and D by as much as 25 to 30 percent." The JPL guidelines say that from the Phase B start to launch, total mass and power growth ranged from 20% to 48%. The AIAA Recommended Practice (R-020A-1999) doesn't give mass growth by phase, but by type of calculation, and for a "Layout" has 12-30% growth allowance.

- The following requirement has been revised in the Mission Requirements Document (MRD) Rev B to reflect adherence to this contingency and margin schedule.

| ID | Requirement Statement – Rev A | Requirement Statement – Rev B |
| --- | --- | --- |
| M-29 | All resource budgets (mass, power, data) shall show sufficient positive margin at each project milestone. | Resource budgets (mass, power, data) shall show margin at each project milestone per the Systems Engineering Management Plan (SEMP). |