## Summary
THEMIS | IIRT ACTION ITEM STATUS
Concurred
| AIMS System Status |  |  |  | Complete Un-Submitted | Filled Out | Withdwn
| Meeting | Type of Action | Total | Open |  | Submitted | Closed
| SRR | Action Items | 26 | 0 |  | 0 | 26
|  | Recommendations | 18 | 0 |  | 0 | 18
| scPDR | Action Items | 53 | 3 | 6 | 4 | 40
|  | Recommendations | 0 | 0 |  | 0 | 0
| MPDR | Action Items | 37 | 2 | 0 | 3 | 32
|  | Recommendations | 2 | 0 |  | 0 | 2
|  | TOTALS | 136 | 5 | 0 | 7 | 118

## SRR
THEMIS |  | Mission Systems Requirements Review Actions
RFA | Originator | Title | Lead | Status | File Ref |  | 0 | 26
1 | Killough | Requirements Flow-Down for Automated Test Equipment | Harvey | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response1.doc | 0 | 0 | 1
2 | Killough | State or Mode Dependent Requirements | Krauter | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response02.doc | 0 | 0 | 1
3 | Killough | Review MRD with Regard to Resolution, Accuracy & Position | Brenneman | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response03.doc | 0 | 0 | 1
4 | Killough/Barrowman | Requirements Dealing with Time Synchronization, MET, Time tagging | Angelopoulos | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_TimeSynch_RevA.doc | 0 | 0 | 1
5 | Killough | Clarify Types of Spacecraft Numbers and Identifiers | Krauter-Bester | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/MEETINGS/RFAs/thm_SRR_RFA_Response_05_RevB.doc | 0 | 0 | 1
6 | F. Martin | Use GSFC Standard Practice for Margins and Margin History | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_06_RevA.doc | 0 | 0 | 1
7 | F. Martin/Bolek | Spacecraft Visibility with Ground/TDRS | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_07.doc | 0 | 0 | 1
8 | F. Martin | Add I&T requirements Flow-Down for the Payload Carrier | Taylor-Brenneman | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response 8RevA.doc | 0 | 0 | 1
9 | B.Taylor | Assigning Responsibility for Assuring Requirements Compliance | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_09.doc | 0 | 0 | 1
10 | B.Taylor | Compliance to Interface Control Documents | Ajluni | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response10.doc | 0 | 0 | 1
11 | B.Taylor | Schedule to Release/Baseline of Level II/III Requirements Documents | Harvey | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/MEETINGS/RFAs/thm_SRR_RFA_Response11.doc | 0 | 0 | 1
12 | B.Taylor | Requirements Testing with the Ground System | Taylor-Bester | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_12.doc | 0 | 0 | 1
13 | Schnurr | Document Control, Signoff and Management | Harvey | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_13.doc | 0 | 0 | 1
14 | Schnurr | Provide Flow-down of Safety/Inhibits for Separation and Propulsion | Ajluni | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response 14RevA.doc | 0 | 0 | 1
15 | Bolek/Glubke | Process for replacing a Failed Probe with a Replacement probe | Bester-Bonnell | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_15_RevB.doc | 0 | 0 | 1
16 | Bolek | Flux Gate Magnetometer requirements | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_16.doc | 0 | 0 | 1
17 | Bolek | C&DH Capability for Writing and Retrieving from Memory | Krauter | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response17.doc | 0 | 0 | 1
18 | Hair/Mark | Add Z-Axis Center of Gravity Requirement for PCA | Lashley | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response18.doc | 0 | 0 | 1
19 | Hair | Set Limitations on the Placement of the MAG and EFI Instruments | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_19_RevB.doc | 0 | 0 | 1
20 | Hair | Add Functional Requirements to IN.BOOM Requirements | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_20.doc | 0 | 0 | 1
21 | Hair | Add Carrier De-Spin Requirement to the Launch Vehicle Requirements | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response21.doc | 0 | 0 | 1
22 | Hair | Adding Deployment Signal/Command Requirements | Ajluni | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response22.doc | 0 | 0 | 1
23 | Hair | Provide Clearer Connection Between Science and Mission Requirements | Angelopoulos | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/MEETINGS/RFAs/thm_SRR_RFA_Response23.doc | 0 | 0 | 1
24 | Fantano | Specify Temperature Requirements for all Sensitive Hardware | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_24.doc | 0 | 0 | 1
25 | Fantano | Specify Verification Test Requirements | Brenneman | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/MEETINGS/RFAs/thm_SRR_RFA_Response%2025.doc | 0 | 0 | 1
26 | Fantano | Specify Minimum and Maximum Allowable Transmitter On Times | Ajluni | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response26.doc | 0 | 0 | 1
Rec | Originator | Title | Lead | Status |  | 0 | 0 | 18
Rec | Davis | Implement Continuous Nitrogen Purge | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_Rec_Contam.doc | 0 | 0 | 1
Rec | Fantano | Re-evaluate Temperature Telemetry requirements | Ajluni | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Temp_Tel_Req.doc | 0 | 0 | 1
Rec | Fantano | Suggested Change to PB.THM-16 | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_Rec_Thermal.doc | 0 | 0 | 1
Rec | Glubke | Impact of Extended Mission | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/MEETINGS/RFAs/thm_SRR_RFA_Response_Rec_Extended%20Mission.doc | 0 | 0 | 1
Rec | Hair | Mission Life | Angelopoulos | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_MsnLife_RevA.doc | 0 | 0 | 1
Rec | Hair | Deployable Torque Ratio | Turin | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/MEETINGS/RFAs/thm_SRR_RFA_Response_DeployTorqueRatio.doc | 0 | 0 | 1
Rec | Hair | Deployment of magnetometer Booms | Turin | Closed |  | 0 | 0 | 1
Rec | Hair | MRD Configuration Management | Taylor | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Response_Rec_Config.doc | 0 | 0 | 1
Rec | J.B. Joyce | Assessment of Lunar Shadows | Bester-Frey | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/MEETINGS/RFAs/thm_SRR_RFA_response_rec_lunarshadow.doc | 0 | 0 | 1
Rec | J.B. Joyce | Detail the Processes for Orbit Determination | Bester | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/MEETINGS/RFAs/thm_SRR_RFA_Response_Rec_Orbit_Determination_RevA.doc | 0 | 0 | 1
Rec | J.B. Joyce | Provide Optimized Ground Station Strategy | Bester | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1%20Management/MEETINGS/RFAs/thm_SRR_RFA_Response_Rec_Ground_Stations_RevA.doc | 0 | 0 | 1
Rec | J.B. Joyce/ Mark | Science End Product Requirements | Angelopoulos | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_SciEndProd_RevA.doc | 0 | 0 | 1
Rec | J.B. Joyce/Mark | Add Mission Operations Requirement Regarding Probe GRI | Taylor | Closed |  | 0 | 0 | 1
Rec | Killough | Implementing a Solid State Recorder | Harvey | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Recommend_SSR.doc | 0 | 0 | 1
Rec | Killough/Mark | Add Pre-Launch Mission Mode Constraints | Ajluni | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Pre-Launch_Mission_Mode.doc | 0 | 0 | 1
Rec | Schnurr | Probe Bus EPS Requirements Modifications | Krauter | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_PB_EPS_Req.doc | 0 | 0 | 1
Rec | Schnurr | Compliance with Orbital Debris requirements | Ajluni | Closed | ftp://apollo.ssl.berkeley.edu/pub/THEMIS/1.1 Management/MEETINGS/RFAs/thm_SRR_RFA_Orbital_Debris.doc | 0 | 0 | 1
Rec | Schnurr | Need an End-to-End Data Analysis | Bester | Closed |  | 0 | 0 | 1
`

## SC_PDR
THEMIS |  |  | Probe & Probe Carrier PDR RFA Status 11/01/03
No. | Subsystem | Subject | PM | Resp. | Primary | Secondary | Proposed | Priority | Actionee | Current | Est Date to | Est Closed
|  |  | Assess. | Org | Resp. | Resp | Closure |  |  | Status | Submit | Date | RevG
[7 empty] | Date | [5 empty] | Open | Complete | Submitted | Closed | Withdrawn
1 | Systems | Orbital Debris Report | Reject | SAI | NA | NA | NA | NA |  | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
2 | Elec. Sys. | EMI/EMC | Accept | SAI | Kraeuter | Ajluni | CDR | Low |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
NA | Systems | Requirements | Accept | SAI | Ajluni | Brenneman | Mis PDR | High |  | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
3 | Power | Load Shed | Accept | SAI | Robinson | Ajluni | TBD | Low |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
4 | GN&C | Sun Sensor Op during Eclipse | Accept | SAI | LeBoeuf | Ajluni | Mis PDR | High |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
5 | Systems | Meas. Units | Accept | UCB/SAI | Taylor | Ajluni | Mis PDR | Low |  | Submitted | n/a |  | 0 | 0 | 1 | 0 | 0
6 | PMO | Peer Review Track | Accept | SAI | Cully | Leads | CDR | Low |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
7 | Systems | Mass Reporting | Accept Cond. | SAI | Ajluni | Leads | Mis PDR | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
8 | Mech. | Sep. System Loads | Accept | SAI | Lashley | Jarosz | TBD | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
9 | Mech. | Sep. System Loads | Accept | SAI | Lashley | Jarosz | TBD | Medium |  | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
10 | PMO | Subsystem Status | Accept Cond. | SAI | Cully |  | Mis PDR | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
11 | FSW/Elec. Sys. | EEPROM Design | Discuss | SAI | Kraeuter | Hammers | Mis PDR | High |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
12 | PMO/Mech. | Sep. System Risks | Accept | SAI | Cully | Lashley | Mis PDR | High |  | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
13 | Elec. Sys. | FPGA Peer Review | Discuss | SAI | Kraeuter |  | Mis PDR | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
14 | Power/Systems | Max Power Case | Accept | SAI | Robinson |  | PDR+ | Medium | Ajluni | Open | 2004-06-02 |  | 1 | 0 | 0 | 0 | 0
15 | Thermal | Load Shed Thermal Case | Accept | SAI | Zara | Ajluni | TBD | Medium | Ajluni | To UCB | 2004-06-03 |  | 0 | 1 | 0 | 0 | 0
16 | Thermal | Heat Flow/Facet | Accept | SAI | Zara | Ajluni | TBD | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
17 | Thermal | Low Emittance Interior Surfaces | Accept | SAI | Zara | Ajluni | TBD | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
18 | Thermal/Systems | VDA Usage | Discuss | SAI | Zara | Ajluni | TBD | Medium | Ajluni | To UCB | 2004-06-03 |  | 0 | 1 | 0 | 0 | 0
19 | Thermal | Transponder Operations | Accept | SAI | Zara | Ajluni | TBD | Medium | Ajluni | Open | 2004-06-02 |  | 1 | 0 | 0 | 0 | 0
20 | Quality/Thermal | Solder Joint Temps. | Discuss | SAI | Virmani | Zara | TBD | Medium | Ajluni | Open | 2004-06-02 |  | 1 | 0 | 0 | 0 | 0
21 | Thermal | OSRs | Accept | SAI | Zara |  | TBD | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
22 | Thermal/Systems | Max Solar Array Temperatures | Discuss | SAI | Zara | Ajluni | TBD | Medium | Ajluni | Open | 2004-06-02 |  | 1 | 0 | 0 | 0 | 0
23 | RF | Antenna Risk Assessment | Accept | SAI | Cully | Dod | Mis PDR | High |  | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
24 | Mech./Systems | Sep. Systems TRL #6 | Accept | SAI | Lashley | Cully | Mis PDR | High |  | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
25 | Systems/Mech | Sep Systems Requirement | Accept | SAI | Ajluni | Lashley | Mis PDR | High |  | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
26 | Mechanical | Sep. Systems Dimension | Accept | SAI | Jarosz |  | Mis PDR | High |  | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
27 | Power | Solar Array one circuit Failure case | Accept | SAI | Robinson | Ajluni | PDR+ | Medium | Ajluni | Submitted | n/a |  | 0 | 0 | 1 | 0 | 0
NA | Elec. Sys. | Poly-Fuses | Accept | SAI | Kraeuter |  | Mis PDR | Low |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
28 | Power | Lithium Ion Test Plan | Accept | SAI | Robinson |  | PDR+ | Medium | Ajluni | Open | 2004-06-02 |  | 1 | 0 | 0 | 0 | 0
29 | Systems | Rationale C&DH power up after fueling | Accept | SAI | Ajluni |  | Mis PDR | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
30 | Mech. | Sep. System Peer Review | Accept | SAI | Lashley | Jarosz | PDR+ | High |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
31 | Systems | P1 & P2 Orbit Propagation | Accept | UCB | TBD | TBD | PDR+ | TBD |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
32 | Software | Detail Schedules for FSW Build | Accept | SAI | Hammers |  | Mis PDR | Medium | Ajluni | Submitted |  |  | 0 | 0 | 1 | 0 | 0
33 | Software/Elec. Sys. | Watch Dog Timers | Accept | SAI | Kraeuter | Hammers | Mis PDR | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
34 | Software | Flight Software Requirements and Traceability | Accept | SAI | Hammers | Dorsey | TBD | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
35 | Software | FDC Requirements | Accept | SAI | Hammers | Ajluni | TBD | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
36 | Software/GN&C | GN&C & FSW Requirements Coordination | Accept Cond. | SAI | Hammers | Lebouef | TBD | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
37 | GN&C | Phasing Test Gyro | Accept | SAI | LeBoeuf |  | TBD | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
38 | Software/RCS | FDC and Thruster Firing | Accept | SAI | Hammers | McCulloiugh | Mis PDR | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
39 | Systems | Req. Verification Matrix | Accept | SAI | Brenneman | Ajluni | Mis PDR | Medium |  | Closed |  |  | 0 | 0 | 0 | 1 | 0
40 | ITOS | Groundstation upgrade for Constellation | Accept | SAI | Hammers | Faulkner | CDR | Low |  | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
41 | Mech. | Sep. System Loads | Accept | SAI | Lashley | Jarosz | TBD | Medium |  | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
42 |  | Harness Bake Out | [6 empty] | I&T | Submitted |  |  | 0 | 0 | 1 | 0 | 0
43 |  | TRL | [7 empty] | Withdrawn |  |  | 0 | 0 | 0 | 0 | 1
44 |  | Sep System Dev | [7 empty] | Closed |  |  | 0 | 0 | 0 | 1 | 0
45 |  | Contam Ctrl Plan | [6 empty] | I&T | Submitted |  |  | 0 | 0 | 1 | 0 | 0
46 |  | Rec Poly Fuses | [7 empty] | Closed |  |  | 0 | 0 | 0 | 1 | 0
47 |  | Ensure Mag Cleanliness | [7 empty] | Closed |  |  | 0 | 0 | 0 | 1 | 0
48 |  | Power Calculations | [7 empty] | Closed |  |  | 0 | 0 | 0 | 1 | 0
49 |  | Hot Flash Test | [7 empty] | Closed |  |  | 0 | 0 | 0 | 1 | 0
50 |  | Battery Shelf Life | [6 empty] | Ajluni | Open | 2004-06-02 |  | 1 | 0 | 0 | 0 | 0
51 |  | Transmitter before Shadow | [7 empty] | Closed |  |  | 0 | 0 | 0 | 1 | 0
[13 empty] | 6 | 2 | 5 | 29 | 11

## MPDR
THEMIS |  | Mission Preliminary Design Review Actions
[7 empty] | Open | Comp | Closed
RFA | System | Title | Resp | Status | Est Date to Submit | Est Closed Date | 2 | 0 | 32
MPDR-1 | Systems | Need Test Simulating On-Orbit Storage of Boom Mechanisms | Turin | Closed |  |  | 0 | 0 | 1
MPDR-2 | Systems | Provide Verification Method for each Requirement | Taylor | Closed |  |  | 0 | 0 | 1
MPDR-3 | Systems | Provide Qualification Plan(s) for all the Mechanisms | Turin | Closed |  |  | 0 | 0 | 1
MPDR-4 | Systems | Provide Design Info from the Instrument Peer Reviews | Angelop. | Closed |  |  | 0 | 0 | 1
MPDR-5 | Systems | Provide Updated Power Budget with Assumptions | PHarvey | Submitted | n/a |  | 0 | 0 | 0
MPDR-6 | Systems | Conduct DC & AC Magnetic Testing at all Levels of Integration | Taylor | Closed |  |  | 0 | 0 | 1
MPDR-7 | Systems | Improve the Reliability of Battery Charge Control | Ajluni | Closed |  |  | 0 | 0 | 1
MPDR-8 | SST | Involve PRB in Qualification of the AMTEK SST Preamp | Harvey | Closed |  |  | 0 | 0 | 1
MPDR-9 | Mechanisms | Nano-Muscle Mechanism Peer Review | Turin | Closed |  |  | 0 | 0 | 1
MPDR-10 | Mechanisms | Consider Component Level TV and Hot/Cold Functional Testing | Harvey | Closed |  |  | 0 | 0 | 1
MPDR-11 | Mechanisms | Evaluate DOF and Displacements at Magnetometer Latch I/F | Turin | Closed |  |  | 0 | 0 | 1
MPDR-12 | Systems | Document Critical Items List to Include Mitigation Plans | Taylor | Closed |  |  | 0 | 0 | 1
MPDR-13 | Systems | Expedite Closure of Existing Orbit Debris Assessment Issues | Taylor | Closed |  |  | 0 | 0 | 1
MPDR-14 | Systems | Provide End-to-End Estimates of System Performance | Taylor | Closed |  |  | 0 | 0 | 1
MPDR-15 | MOC | Detail the Roles of GSFC/Flight Dynamics Support to THEMIS | Bester | Closed |  |  | 0 | 0 | 1
MPDR-16 | MOC | Document Criteria for Selection of Probes for Operational Orbits | Bester | Closed |  |  | 0 | 0 | 1
MPDR-17 | Systems | Establish/Define the Requirement for Monitoring S/C Separation | PHarvey | Submitted | n/a |  | 0 | 0 | 0
MPDR-18 | Systems | Provide Verification Plan and Environmental Test Specification | Taylor | Closed |  |  | 0 | 0 | 1
MPDR-19 | MGMT | Allocate Contingency Time Before Planned Mate with L/V | Harvey | Closed |  |  | 0 | 0 | 1
MPDR-20 | Systems | Define Mission-Wide Oversight Responsibility of FSW Devlpt | Taylor | Closed |  |  | 0 | 0 | 1
MPDR-21 |  |  |  | Withdrawn |  |  | 0 | 0 | 1
MPDR-22 | Systems | Define Functional Responsibility for Mission-Level I&T | Harvey | Closed |  |  | 0 | 0 | 1
MPDR-23 | Systems | Define Responsibility for IDPU Product Dvlpt Function | Harvey | Closed |  |  | 0 | 0 | 1
MPDR-24 | MGMT | Provide Updated Top-Level Organizational Chart | Harvey | Closed |  |  | 0 | 0 | 1
MPDR-25 | EGSE | Spacecraft Simulator Interface Details | Fharvey | Closed |  |  | 0 | 0 | 1
MPDR-26 | EGSE | Payload/IDPU Simulator Functionality | Fharvey | Closed |  |  | 0 | 0 | 1
MPDR-27 | FSW | Software Requirements Flowdown and Detail | Fharvey | Closed |  |  | 0 | 0 | 1
MPDR-28 | FSW | Software-Related Metrics | Fharvey | Closed |  |  | 0 | 0 | 1
MPDR-29 | FSW | Software Development Plan lacks elements & Detail | PHarvey | Submitted | n/a |  | 0 | 0 | 0
MPDR-30 | MOC | Upload P# to Probe and Include in TLM | Bester | Closed |  |  | 0 | 0 | 1
MPDR-31 | Systems | Include Inst. Thermal Specs into Mission Level Requirements | Taylor | Closed |  |  | 0 | 0 | 1
MPDR-32 | Thermal | Identify Hot & Cold Cases for all Temp. Sensitive Components | Smith | Closed |  |  | 0 | 0 | 1
MPDR-33 | Contamination | Reassess Instrument & S/C Contamination Requirements | Ajluni | Open | 2004-06-07 |  | 1 | 0 | 0
MPDR-34 | Systems | Reconsider Performing T/B Testing on Probes 2-5 | Ajluni | Closed |  |  | 0 | 0 | 1
MPDR-35 | Systems | Specify a Minimum "OFF" Time for Transmitter Operation | Ajluni | Closed |  |  | 0 | 0 | 1
MPDR-36 | Systems | Refine ICD Definitions of Inst. & S/C IF Requirements | Taylor | Open | 2004-05-24 |  | 1 | 0 | 0
MPDR-37 | Systems | Ensure a Formal Worse Case Analysis (WCA) Process is in Place | Taylor | Closed |  |  | 0 | 0 | 1
Rec | Originator | Title | Lead | Status |  |  | 0 | 0 | 2
Rec-1 | Product Assurance | Impact of Potential MAR Requirement Changes | Harvey | Closed |  |  | 0 | 0 | 1
Rec-2 | Systems | Assess Inst. Teams Ability to Provide Simultaneous I&T Support | Harvey | Closed |  |  | 0 | 0 | 1