QUESTION 14. Please explain the UCB plan required to support delivering 5 instrument suites to Swales in 2005.  How are resources planned to accommodate these builds (people, facilities, test equipment, environmental chambers)?  Include your staffing plan with regard to scheduling, design, build and testing activities.  How does the “centralized parts buy/build” fit into this plan?

People.  Just as in the HESSI program, the THEMIS staffing requirement is a key challenge for the start of the project.  While we will initially find a number of SSL employees coming off CHIPS and other projects on the hill, we will advertise in local Bay Area newspapers, and continue engaging our contacts at Lockheed and Loral to supply qualified engineering.  Below are staffing charts we have in the plan organized by job category, including engineers, programmers and technicians for the design, build and test activities.

Facilities.  The THEMIS project will need a good fraction of the office and laboratory space at UCB/SSL, so it is fortunate that the lab director and the space allocation chairman are members of THEMIS project (Drs. Lin and Carlson).  THEMIS is a project of the Space Physics Research Group (SPRG), which is the largest group at SSL. The group has nearly all the necessary facilities for THEMIS, including clean rooms for ESA, SST and Instrument integration and test, and operates a centralized flight parts storage room. The only facility addition we need is one additional thermal vacuum chamber.

Test Equipment.  One of the clear strategies of building a Constellation of probes is to make early investments in the test equipment, and to make that equipment as useful as possible for the long term (i.e. from component tests all the way through to PCA testing).  Central to the instrument testing will be the IDPU and for it we have planned 2 complete GSE setups. Depending upon the sensor, test equipment is generally a mixture of unique equipment items, such as voltage references which force the sensor testing into an assembly line format.

Discussions of the importance of test equipment were initiated at the very first meeting of THEMIS team, and the team was requested to plan and cost for test equipment appropriately, rather than simply use whatever equipment was left over from the last program. Budget requests for test equipment from each cost center were included in the Phase A budget without exception.

SSL Project Loading.  While the THEMIS plan has detailed its resource requirements, and though there is considerable scientific excitement in this project, it is important to determine if there are other projects in the works which will make it difficult for THEMIS to get the resources it needs when it needs them. The following chart shows the top projects both ongoing and planned for the UCB/SSL facility.

STEREO is currently in the fabrication phase, with deliveries about the time THEMIS begins fabrication. Thus, THEMIS and STEREO collide over the engineering talents, but not for special facilities such as TV chambers. There is some likelihood that STEREO technicians and programming staff will move over to THEMIS as the STEREO instruments are delivered. However, if STEREO continues to slip its schedule, THEMIS will begin to compete for TV chambers as well as will be forced to bring in additional fabrication personnel.

SNAP and MMS are expected to be in phase A and B for some time to come and while these may impact the top level management and systems engineering available, these projects will not compete with THEMIS for fabrication facilities or personnel.  Secondly, SNAP and MMS provide a convenient offloading of THEMIS fabrication personnel.

Chamber Availability at SSL.  The SSL has a number of Thermal Vacuum, Vacuum and Thermal chambers of various sizes and capabilities. Many of the chambers have been used by the heritage instrumentation planned for THEMIS and already have special test apparatus which attach to these tanks for testing. For example, the EFI/EFW booms have deployment support GSE made for 320-L1 tank, and the ESAs have a manipulator which is designed for the 320-Cal chamber. (These are examples of unique test equipment which will serialize the test sequence at this phase.)

Due to the number of deployment units involved in THEMIS, we planned to make a copy of 320-L1, in order to enable parallel boom testing. By making the tank with identical fittings, we plan to have flexibility in scheduling the tests. However, our schedule does not take advantage of that yet.

Similarly, we noticed that the SST and ESA test plans involved considerable vacuum time and would have collided terribly for a single calibration chamber. Thus, we will need to re-fit the B20-Cal chamber for SST testing (the chamber was modified for use on another program and would be un-modified for THEMIS).

TV Plan Design.  The TV plan has been carefully considered to get the best tests we can. Our concept involves 2 TV cycles at the component level and 6 TV cycles at the instrument level. This provides two key advantages over a single TV series: [1] component tests can focus upon the proper tests they need to do, without the chamber encumbrances of other instrumentation and other GSE; [2] significant instrument-level test time in normal mode, with less down-time implementing component-specific comprehensive tests.

To gain a general measure of the TV availability, we took a look at the planned length of time in vacuum for each component and the period over which the component team had scheduled TV testing. These data are provided in the following table.

In the left column are the components, followed by the period of time, start to finish, which the team had in their schedule. The usage is the density of vacuum chamber time to total time possible. The following columns are the chambers which are planned for these tests. For example, the IDPU box has 6 weeks planned over the course of 20 weeks, which is a 31% usage.

Actual planning of TV chambers is, of course, performed by the scheduler using these chambers as resources in a resource-driven schedule. As schedules change, we can modify the plan accordingly.