QUESTION 13: What are the top risks to the THEMIS mission?

Answer: Mission schedule risk has been addressed in detail in the CSR. A vigorous program for its mitigation has been established. The top three remaining risks are:

- Probe Development Cost. Since the spacecraft represents the largest development effort (i.e., ~2.5 times that of the instrumentation), small percentage increases in that cost are directly reflected in the program margins. Such cost growth might arise from vendor pricing due to unforeseen market changes (e.g., industry acquisitions, parts discontinued etc) and replacements might be costly given the limited supplier pool available for the low mass and power requirement subsystems of the THEMIS probe bus, or if it occurs late in the development. Mitigation. THEMIS is counting on the experience of Swales, GSFC and UCB personnel with small satellite programs (e.g., SMEX Lite, EO1 at Swales, SMEX program at GSFC and prior Explorers at UCB) with such vendors. Swales has identified multiple vendors on key components (>2 in many cases) and Swales baseline cost uses domestic suppliers and highest price quotes. Additionally, UCB is capable, as a contingency plan, to support the THEMIS I&T process through involvement of its Flight Operations Team, thus taking advantage of lower overhead rates to compensate for inadvertent cost growth in other areas. This model has paid great cost dividends on HESSI, with the additional advantage of increased FOT experience with the flight system.

- Instrument Schedule Risk.

  - Historically instrumenters at (typically lean) University environments are understaffed at the beginning of large programs and have difficulty ramping up to its demands.

Mitigation: UCB is larger than ever before and THEMIS management has direct involvement in staffing. Have ramped up on FAST, HESSI before and recognize the process. Current economy environment (local Bay area Aerospace industry layoffs) helps staffing. Skilled personnel has already been identified in local industry.

  - Heritage (as in THEMIS instruments) is often accompanied by lack of current parts.

Mitigation:  Well known risk which is easy to mitigate by coordinating instrument parts early. This early coordination is in any case necessary for our common parts program. An additional benefits from such early coordination through common buy are better parts, higher screening, at a lower cost.

- Design flaws. Instrument component qualification prior to probe 1 I&T (even though instrument suite pre-I&T uses BAU simulator) may result in unforeseen problems during mission I&T. If such problems are design flaws the error is multiplied by factor of 6.

Mitigation:  Significant emphasis is placed in probe-to-instrument interface testing prior to flight build up.

As a policy, risks and risk mitigation strategies are continuously and openly discussed as they surface from developers and subcontactors as part of our healthy informal interactions, and status meetings. The risk items in the probe bus and probe carrier areas (all minor) are shown in the tables below, along with mitigation strategies: