QUESTION 11. What is the current status of the ESTEC VLSI Chip development and test program?

The ESTEC chip version N has been tested and qualified to 8kRads. STEREO is an 8kRad program, and the chip would be acceptable for STEREO. However, not enough chips are available for STEREO from the previous run and a new production run is necessary. ESTEC expects to provide the same parts to THEMIS under a common batch run with STEREO. The new production run is expected to exceed 8kRads radiation dose (ESTEC target is 80kRads) after replacement of an oscillator. The anticipated delivery time is June of 2003.

The ESTEC chip is applicable to the THEMIS environment in its current state (i.e., without the oscillator replacement) after <1mm of Ta cover, in addition to the nominal, 5mm of Al, effective shielding anticipated for all THEMIS electronics parts. The above total dose calculation assumes factor of 2 margin and additional margin arising from slab (realistic) versus sphere (computed) geometry.

In the unlikely event of unforeseen programmatic considerations the chip becomes unavailable the following strategies are available to THEMIS in order of preference:

- Use of an APL ASIC that performs the same functions as the ESTEC chip and is slated for flight in the energetic particle instrument on Pluto and which has been also flown in the energetic neutral atom imager instrument on Cassini. The cost of reproduction of the chip is minimal and the APL commitment is facilitated by virtue of APL’s participation in the science (A. T. Y. Lui is a THEMIS co-I). Since APL has already underwritten the development and qualification costs and since this option has minimal mass and no power effects to the SST instrument, this represents our first choice.

- Use of discrete electronics built at SSL, using a similar design as for the STEREO/Impact/STE investigation energetic particle instrument. This represents cost (~$300K) and mass (~50%) increase in the sensor electronics area that are not insignificant and therefore represents a solution to be exercised if other avenues fail.