QUESTION 16. Please discuss why the proposed cost reserves are adequate, and your plan for managing these reserves. What is the justification for no Phase B and E cost reserves? How are descope decisions triggered?

Reserves are Adequate at this Stage. Since no one really knows the future, it is hard to state with absolute certainty that there are enough reserves. But knowing that numerous studies were conducted during Phase A, and extensive effort was made to develop the concept, its schedule and cost, one can reasonably apply the aerospace standard figures for cost reserves.

In the THEMIS proposal, we carried 30% reserve in the budget for development items (not for Phase E, for example). Given the requirement that THEMIS maintain 20% minimum into the Confirmation Review, we had to maintain a reasonable margin above 20%. Thus, the program reserve was set at approximately 25%, the midpoint between the proposal and the CR requirement.

Finally, the recent experience from HESSI has shown that our detailed planning and our program execution methods results in very modest growth (~10%) which is mostly used towards risk reduction by anticipatory contingency planning.

Reserve Phasing. Below are the curves showing reserve funding and remaining reserve. Since THEMIS is a 5-probe constellation where design changes have a 5-fold impact, we have focused the monthly reserve allotments in the Design phase, starting a little before PDR. During Phase B while the teams are staffing up, formalizing requirements and such, we believe it unlikely to need reserve funds. The PDR design and supporting analytical work may suggest concept changes with their associated financial impacts. Thus, the reserve will become available at that time. As a practical matter, in HESSI, we were not allowed to use reserve funds in the first fiscal year, but this posed no real issue.

A second period in which we are emphasizing the reserve is the launch phase. This is because as launch approaches, work-around options are limited and added-cost options are all that is available. As pre our HESSI experience, THEMIS will maintain reserves to handle a minimum of a 2-month slip plus 15% on the cost to complete.

Finally, reserve funds not used by launch should be made available to the mission operations and data analysis efforts. No additional reserve funds are held out for Phase E since if launch is not achieved, there is no purpose for Phase E funding. In addition, Phase E has numerous non-cost workarounds if costs have been underestimated. For example, operating the spacecraft or data analysis for a slightly shorter period will affect a simple budget reduction.

Descope Trigger.  When actual cost data or schedule delays cause the estimated cost to complete to grow larger than the available reserve, management must take action. First, management must determine if there are technical, schedule or organizational changes that can lower the cost to complete such that no descope is required; i.e. find a change to the implementation which is more efficient. If no options exists, the PM, MSE and PI must identify one or more of the descopes which will affect the required budget reduction.