## Slide 1
Tom Ajluni
Swales/Systems
Over the past 20 years Tom has built, tested and launched a wide variety of instruments and spacecraft for commercial, DoD and NASA missions, most recently FUSE and MAP. On THEMIS he will be the lead systems engineer for the probes and carrier from inception through mission level I&T and launch.
Mission Integration and Test

## Slide 2
Component Manufacturing, Integration & Test Overview
Facilities
GSE
Probes and Carrier Production
I&T Flow
Environmental Testing
Launch Site Processing
Launch & Deployment
Mission Integration & Test Agenda

## Slide 3: Extensive Component Qualification Program Mitigates I&T Risks
Components are flight qualified prior to bus/probe installation
  Heritage instruments undergo thorough environmental testing individually and as a assembly
  Bus components selected from flight proven units provided by ISO 9001 certified industry leading vendors
Simple design with straightforward interfaces
  Single string bus with few components
  Single instruments to spacecraft electrical interface through IDPU
  Simulator exchange (bus and instruments) supports early testing for instruments, bus and mission
  EDU bus avionics and IDPU support early h/w and s/w development
Instrument Test Description | Box | Instrument Complement
Functional |  | 
Deployment |  | 
Self-Compatibility | - | 
Cleanliness |  | -
EMI/EMC | - | 
DC Mag Field |  | -
AC Mag Field | - | 
Electrostatic Surface Charging |  | -
Vibration |  | -
T/V (cycles) | (2) |  (6)
Instruments Qualified
Prior to Bus Integration

## Slide 4: Existing Facilities
Facilities are in place and ready to support Probe and Carrier Integration at Swales Aerospace
  Existing facilities easily lend themselves to separate work areas and multiple workstations to support our parallel probe I&T flow
NASA/GSFC facilities baselined for environmental testing
  Seven mile drive from Swales to GSFC (3 traffic lights)
  GSFC facilities are familiar to us and way more than adequate for THEMIS
  Alternate facilities within 30 miles include APL, NRL, Northrop Grumman
Swales 5015 Probe I&T Facility Operations and Floor Plan General Production
OFFICE
ANTE
ROOM
ROLLUP DOOR
S
L
I
D
I
N
G
D
O
O
R
GOWNING
ROOM
ROLLUP DOOR
HVAC/FILTER ROOM
FACILITY ROOM
LAB B
MECHANICAL
ASSEMBLY
&
BONDING
ROOM
LAB A
HARNESS
&
ELECTRICAL
ASSEMBLY
ROOM
LAB C
TESTBED
&
FLIGHT S/W
CHECKOUT
Staff Machine Shop
L
O
B
B
Y
ZONE 1
WB
CONFERENCE RM
BR
BR
IWS #2
WB
IWS #1
WB
I
N
S
T
R
U
M
E
N
T
S
T
A
G
I
N
G
A
R
E
A
C
O
M
P
O
N
E
N
T
S
T
A
G
I
N
G
A
R
E
A
W
B
ZONE 2
ZONE 3
(Hi-Bay Cleanroom)
W
B
W
B
W
B
OVERFLOW
IWS #3
E
G
S
E
1
E
G
S
E
2
W
B
WB
W
B
B
E
N
C
H
C
H
E
C
K
O
U
T
A
R
E
A
EGSE 3
SHIPPING &
RECEIVING
AREA
WB
WB
W
B
W
B
MECH ASSY
AREA (Hi-Bay)
P
P
P
P
P
WB
WB
W
B
TYPICAL
PROBE
& DOLLY
Separate 11310 Facility for PC Assembly

## Slide 5: GSE Requirements Well Understood
Ample EGSE to support all Phases of the program included in our baseline
  Three test stations for component and bus I&T
  Flatsat and probe simulator each have additional dedicated test stations
Multiple MGSE for probes include dollies, lift fixtures and individual shipping containers as required
  Small probe size and mass
  Probe MGSE not a cost or schedule driver
  Probe carrier assembly MGSE included
  (Shipping container, dolly, lift fixture)
EGSE Sets | ITOS | Virtual Sat | Base Band | RF | Umbil ical
Full Function Test System (EGSE #3) |  |  |  |  | 
Production Test System (EGSE #1&2) |  |  |  |  | 
Flatsat Simulator and Probe Simulator |  |  |  |  | 
EGSE Test #3 Configuration

## Slide 6: Probes and Carrier Production
Utilizes the resources of the full integrated team
  Bus and instrument simulators, experienced test conductors and MOT are delivered to the interfacing institution with direct participation in the subsystem and system test activities.
Probes designed for parallel volume production
  Probe 1 blazes the trail with core team that splits in two parallel teams for the following Probes
  60 days schedule slack between P1 and P2, 40 days slack between subsequent Probes
  Each highly cross trained core team supported by shared pool of technical specialists for instruments, MOT, systems and subsystems etc.
Flight spares and/or warranties for all long lead items
  Stocks at SAI include battery, tank, s/a’s and all avionics boards (thru ambient test)

## Slide 7: I&T Flow Emphasis is on Comprehensive Testing
Probe & Mission General Manufacturing, Integration, and Test and I&T Flow
Dashed Blue Area
Above Indicates
P1 thru P5 Flow
Standard Probe Flow
Structural Test Unit
Qualified
Structure
& Sep test
Harness & Thermal Integration
Avionics ETU
Qualified
Avionics
Avionics
Integration
RCS Integration
Component
Integration
Instrument
Integration
Qualified
RCS
System
Qualified
Vendor
Components
Qualified
Instrument
Suite
Baseline CPT, Probe 1 ready for environmental test
P1 T/V & Balance test
Mag
Survey
Mass
Balance
Instrument deploy & S/A Flash test
RF Perf.
test
EMC Self Compat. test
Vib tests
Tested
Probe 2
P2 T/V & CPT
Tested
Probe 3
Tested
Probe 4
P3 T/V
& CPT
P4 T/V & CPT
Tested
Probe 5
P5 T/V & CPT
Qualified Probe Carrier
Integrate Probes to Carrier
Baseline CPT, PCA ready for environmental test
Vib tests
Acoustic test
RF Perf. & Self Compat test
Bus Complete 1st CPT
Mission Sim
T/V-Launch environment test
CPT’s
Mass
Balance
Launch
Sim #1
Launch site ship
Launch pad ops
Vehicle mate & ship to pad
Probe and PCA Spin Balance
Prop
Load
CPT’s & Launch Sim
Setup at
CCAFS
Launch
IOC
Schedule based on 1shift/day, 5d/week except for TV and launch pad operations (7d/week)
I&T flow includes 6 months of scheduled, costed contingency
100 hr trouble free run time SOP

## Slide 8: Environmental Testing Start to Finish
Robust and complete environmental test plan
  Starts at the component level and ends at the integrated probe carrier
  Instruments undergo extensive environmental tests prior to bus integration
  Bus components undergo environmental testing at the vendor level prior to integration
  Integrated Probe Carrier undergoes additional environmental testing to completely envelope the launch environment

## Slide 9: Launch Site Processing Standard and Straightforward
Standard vehicle interfaces make launch site processing straightforward
Multiple NASA and commercial processing facilities available
Probes can be shipped separately or integrated on the carrier as we choose
No special services required, probes are fueled then mounted to the carrier for final spin balancing and vehicle integration
Vehicle processing follows standard Delta II flow

## Slide 10: Launch & Deployment
Delta II vehicle provides direct injection of the integrated probes and carrier
Probe deployment is preprogrammed and fully autonomous, each probe is deployed into a passively stable, safe, power, communication, and thermal positive condition
Probe activation is accomplished serially via direct ground contact under mission operations control
  The “brains” are on the ground, attitude determination and control (including all thruster burns) done via real time commands and telemetry

## Slide 11
Reserve slide for question summary