## Slide 1: Project Management
THEMIS Project Management
Peter R. Harvey
Project Manager
Space Sciences Laboratory
University of California, Berkeley

## Slide 2: Project Management
AGENDA
  Organizations
  Personnel
  Processes
  Concept
  Schedule
  Cost
  Summary

## Slide 3: Organizations

## Slide 4: Key Personnel
* : First Year Core Team if Selected for 2nd MIDEX

## Slide 5: Processes
Management Responsibilities
  Staffing and Facilities, Training and Certification
  Subcontract Generation and Tracking
  Schedule Generation and Tracking (*)
  Budget Generation and Tracking
  Cost .v. Schedule Compliance
  Risk Identification, Risk Tracking, Risk Actions (*)
  Descope Identification, Cost Evaluation, Descope Actions
  Trade Studies Identification, Evaluation, Change Implementation
  Action Item Generation, Distribution and Tracking
  Technical & Financial Report Generation
* : Crucial Elements in a Constellation Project

## Slide 6: Processes
Systems Engineering Responsibilities
  Requirements Identification and Formalization
  Design Coordination, Studies (FTA, FMEA, etc)
  Technical Review Coordination, Informal and Formal
  ICD Generation
  Configuration Control
  Verification Plan Development
  Design Compliance
  Operations Plan Development
  Action Item Management
  Weekly telecons on S/C bus, Instrumentation, Ground Systems
  Periodic On-site meetings
* : Crucial Elements in a Constellation Project

## Slide 7: Processes
Performance Assurance Responsibilities
  Assurance Requirements Identification
  Implementation Plan
  Subcontractor Assurance Plan Reviews
  System Safety Support
  Supplier On-Site Inspections of Facilities and Procedures
  Parts and Materials Research, Selection
  Parts Qualification, Procurement incl. Common Buy Program
  Verification Planning
  Inspections and Test Verifications
  Failure Report Management
  Weekly telecons on S/C bus, Instrumentation, Ground Systems
  Periodic On-site meetings
* : Crucial Elements in a Constellation Project

## Slide 8: Question 6: Parts
Question # 6:
GSFC Spec 311-INST-1A [CSR, Page 100] applies only to instruments, and calls for Grade 3 parts only for non-essential instruments with lifetimes less than one year. Please explain your decision to use Grade 3 parts (with some up-screens to Grade 2) for key parts in critical subsystems for the entire spacecraft.
Answer:
GSFC-410-MIDEX-003 Rev A section 5.2 states that “In general all parts should be selected and processed in accordance with GSFC 311-INST-001 for Grade 3 quality level. ” The THEMIS EEE parts program has established as a minimum Grade 3 quality level for both instruments and probe EEE parts..
Satellite probes critical components such as the BAU, Miniature Spinning Sun Sensor and Transponder have established a Grade 2 or better parts program. For inexpensive/short lead parts such as diodes, resistors, capacitors, small transistors etc. probe expects to have Grade 1 parts.
As in past IDPU efforts, Engineers and QA identify critical circuitry and purchase higher grade parts accordingly (e.g. CPU & LVPS).
In general, best available parts above requirement are purchased.

## Slide 9: Processes
Risk Management
  UCB/Swales Management Taking Lowest Risk Approach Overall
  Assessments Generated by Knowledgeable Engineering
  Tradeoffs Discussed with PI for Disposition
  Top Phase A Actions Taken to Retire Risk
  Simplified Probe Carrier, Launch Sequence
  Simplified Probe Maneuvering, Safing
  Scheduled Early Testing to Detect Design Flaws
  Dropped New Technology HCI and Micro-Gyro
  Improved Margins

## Slide 10: Question 13 : Risks
Question 13:
What Are the Top Risks to the THEMIS Mission?
Answer:
  Probe Development Cost
  Largest Development Effort (2.5x instrumentation)
  Limited options for Suppliers Given Low Mass/Power Reqmts
  Counting on Swales/GSFC/UCB Experience in Small S/C (see also S/C Mgmt)
  UCB FOT Involvement Could Help Lower I&T Costs (ala HESSI)
  Instrument Schedule
  Historically Instrumenters Are Understaffed at Start and Play Catch Up
  Heritage Often Means You Can’t Get the Parts Anymore
  Project Management Direct Involvement in Staffing
  Coordinate Parts Early
  Design Flaws
  Components Qualified Prior to Probe1 I&T – Could Be 6 Wrong
  ETU Probe-to-Instrument Interface Testing Prior to Flight Build Up

## Slide 11: Question 18 : ITAR
Question 18a:
Costs, risks and benefits of international participation including burdens to NASA/HQ, UCB, Swales?
Answer:
Costs/Benefits:
  High quality instruments, low mass and power, produced in high numbers before
  Low cost represents existing designs, many years of development
  Carry along tremendous scientific contribution from leaders in substorm work
Instrument complement:
  Simpler than any other space physics program UCB has participated on
  International aspect facilitated by modular production and I&T, simple interfaces
Burdens:
  HQ: LOAs a burden. Experienced THEMIS international partners will help with contacts and follow through paperwork (as on Ulysses, Cassini).
  UCB: Create TAAs as backup to mitigate risk at I&T if ITAR becomes stricter
  Swales: None (badging, escorting etc. common practice).
Risks:
  If ITAR becomes more restrictive UCB will apply for TAA (plenty of time for that).

## Slide 12: Question 18 : ITAR
Question 18b:
How do you plan to demonstrate that you meet the appropriate EAR and ITAR exclusions for fundamental research and publicly available technical data?
Answer:
The University of California, Office of the President, has registered with the Department of State, Office of Defense Trade Controls, PM/DTC Registrant Code 0802-11803 and has developed the following guidelines for compliance with EAR and ITAR as fundamental research and publicly available data:
  Publish papers in technical literature (e.g., Constellation Class missions publication, UCB/GSFC pub., 1998)
  Publish top level design, ICDs, Requirements, interfaces on the web (e.g., http://sprg.ssl.berkeley.edu/ConstellationClassMissions http://sprg.ssl.berkeley.edy/themis
  ftp://apollo.ssl.berkeley.edu/pub/hessi/HESSI%20Documents.html )
  Swales proprietary material (detailed bus design) will not be included but is not necessary to be discussed with foreign instrument providers.

## Slide 13: Question 18 : ITAR
Question 18c:
Anomaly resolution during I&T may require a license. What is the impact and how will you mitigate it?
Answer:
Spacecraft anomalies do not require license because:
  Electrical interface with instruments is through IDPU: UCB deals with that
  Mechanical interface with instruments is through booms: UCB responsible
  EMC (magnetic cleanliness) noise affecting environment dealt by UCLA
Instrument anomalies do not require license:
  Instruments interface with IDPU not probe bus subsystems
Currently presence of foreign nationals at I&T allowed under ITAR 125.4(b)3
  If ITAR starts to become more restrictive will apply for TAA (12mo prior).

## Slide 14: Concept
Essentials for Development & Operation of a Constellation
  Control Mass & Power
  Minimize Design Flaws
  Emphasize Automated Testing and Appropriate GSE
  Simple and Robust to Operate.
    Leave Complexity on the Ground.
    Minimize On-Orbit Computation (Similar to Lunar Prospector, ST-5)
    Use Ground System Computation (Similar to FAST, HESSI)

## Slide 15: Concept
Control of Mass & Power
  Prior Mission Performance Shows Good Compliance
  Large Margins on Mass, Power, Fuel and Schedule
 | Instr. Mass [kg] | Instr. Power [W] | Bus Mass [kg] | Bus Power [W] | Probe Fuel [kg] | Probe Carrier Mass [kg] | Launch Mass [kg] | Schedule [months]
Design | 21.0 | 12.1 | 41.0 | 12.4 | 21.0 | 89.7 | 505 | 42*
Reserve | 13% | 22% | 15% | 17% | 15% | 15% | 15% | 6
Margin | 41% | 42% | 41% | 42% | 43% | 33% | 40% | n/a

## Slide 16: Concept
Minimizing Design Flaws
  Good Communications Between Developers
  Phase A Developments Used Telecom and Email
  Phase B Will Expand Use of Face-to-face
  Engineering Model Tests
  Plan Includes EM Probe & Instrumentation I/F Testing
  Early Identification of Interface Issues
  Early Benefit of Operations Experience & Data Flow Tests
  Parts Control
  Common-Buy Parts Program
  Minimize Number of Different Part Types to Limit ALERT Risk
  Maximize Confidence Level in the Parts We Have

## Slide 17: Schedule
Development and Maintenance
  Bottom Up Development
  Followed Concept Development
  Developers Generated Detailed Schedules
  Each Schedule has >30-40 Items
  Iterated to Understand Schedules
  Did Not Optimize Across Schedules
  Generated a Final Master Schedule
  Schedule Maintenance
  Developers Report to Sub-schedule Monthly
  Project Scheduler Updates Master
  Provides Status to Project Management
  Non-Compliances Get Management Attention
  Workarounds include Work Reduction, Addition Support, ReOrganization

## Slide 18: Schedule
Key Features
  Possible to Support Either MIDEX Launch
  Instrument Development
  EM Instrument I/F Testing with EM Probe I/F
  Integrate Instrument Complement at UCB Prior to S/C Integration
  Instrument Complement F1 Tested First Followed by Pairs
  All Instrument Complements are Complete before S/C I&T Begins
  Instrument I&T Team Will Be Focusing Upon S/C I&T
  Added Some Facilities for Qualifying Instruments in Parallel
  Spacecraft Development
  Integration and Test of Probe1 Completed Prior to Probes 2-5
  Sufficient Manpower and Equipment for Parallel I&T
  Ground Development
  Development and Deployment of some GBOs 1 Winter Ahead

## Slide 19: Schedule
Relevant Prior Schedule Performance
  FAST Instruments (EFI, ESA, MAG, IDPU)
  Hopped in Front of SWAS
  Delivered Complement on Time
  POLAR / CLUSTER I & II (EFI)
  Polar EFI Delivered 8 months ahead of time
  Cluster EFW I & II Delivered > 45 Flight Units to WEC in time.
  HESSI (Management, IDPU)
  Phase B to JPL Environmental Tests (Est. 23 mo, Act. 23.2 mo)
  Re-Confirmation to VAFB Delivery (Est. 6 mo, Act 6.3 mo)
  EO-1 (S/C Management)
  S/C Bus (w Hyperion) delivered 6/99 on time
  Swap with IMAGE, Red Team directives, ALERT, etc Delayed 11m

## Slide 20: Schedule
Metrics
  Milestone Comparisons to HESSI
  Sufficient Definition
  Task Count ~ 1125
  Critical Paths (see Display Charts)
  Spacecraft Probe#1 (RCS), IDPU#1 (IDPU FSW testing)
  Slack
  6 months distributed and included in estimated cost to launch

## Slide 21: Question 14: Resources
Question 14:
Please explain the UCB plan required to support delivering 5 instrument suites to Swales in 2005. How are resources planned to accommodate these builds (people, facilities, test equipment, environmental chambers)? Include your staffing plan with regard to scheduling, design, build and testing activities. How does the “centralized parts buy/build” fit into this plan?
Answer:
Personnel
  Similar to HESSI, Need to Staff Significantly from Internal and External Sources
  Internal: Offloading CHIPS Development Personnel
  External: UC Personnel Hiring within Bay Area
Facilities
  Lab Director & Space Allocation Chairman are Members of THEMIS (Lin, Carlson)
  Space Physics Research Group is the Largest Group at SSL
  Clean Rooms for ESA, SST and Instrument I&T are in SPRG Allocation
  Centralized Parts Storage in Flight Parts Storage Room (Unique Sensor Parts in Labs)
Test Equipment
  IDPU has 2 GSE Setups Planned
  Sensor GSEs Are Generally a Mixture of Redundant & Special Purpose Equipment
  All Equipment Itemized in the Cost Section

## Slide 22: Question 14: Resources

## Slide 23: Question 14: Resources
Question 14 (Cont): SSL Projects
  STEREO in Conflict
  SNAP and MMS Will Help with Offload

## Slide 24: Question 14: Resources
Question 14 (Cont): Environmental Chambers
Chamber Availability at SSL
  Numerous Tanks of Varying Sizes & Types
  One New Chamber Needed for THEMIS
  One Calibration Chamber Needs Parts
TV Plan Design
  2 Component-Level TV Cycles
  6 Instrument Level TV Cycles
Chamber Usage During Relevant Performance Periods

## Slide 25: Cost
Development and Maintenance
  Bottom Up Development
  Followed Schedule Development
  Developers Submitted Detailed Requirements
  Generated Level 3 Budgets by Month
  Iterated with Developers to Understand Costs
  Removed Overlapping Efforts between WBS
  Generated a Final Master Cost
  Generated Comparison Data from Prior Projects
  Reviewed and Approved by THEMIS Board of Directors, SPO, UCOP
  Budget Maintenance
  UCB Financial Data & Subcontractor Reports Matched to Budget
  Project Management Comparison of Cost v Schedule
  Non-Compliances Get Management Attention
  Workarounds include Work Reduction, Addition Support, ReOrganization

## Slide 26: Cost
Key Features
  Possible to Support Either MIDEX Launch
  Very Modest Cost Increase if Chosen for Second MIDEX
  Use Core Team Only and Delay Ramp Up of Personnel
  Instrument Development
  Integrate & Test at UCB Using Mostly Existing Facilities
  Simplified Instrument Interfacing
  Automated Instrument Testing at S/C Lowers Extended Travel Efforts
  Spacecraft Development
  Simplified Probe Carrier Design
  Relaxed Probe Attitude Requirements and Simplified Design
  Complexity Left on the Ground
  Use of Existing Environmental Facilities at GSFC
  Ground Development
  Leverage HESSI & FAST Operations
  Incorporate GSFC/GNCD Software and Expertise

## Slide 27: Cost
Relevant Prior Cost Performance
  POLAR / CLUSTER I & II (EFI)
  Polar EFI Delivered at 37% Under Budget
  Cluster EFW I Delivered 40% Under Budget.
  Cluster EFW II Was Built using Reserve from EFW I
  HESSI (Management, IDPU)
  Completed Spacecraft & Ground Systems at 8% Under Budget
  Re-Built Spacecraft 39% Under Budget
  EO-1 (S/C Management)
  S/C Bus Delivered on Fixed Price
  NASA Directed Additional Effort
    Safe Hold & GPS (GFE) changes
    Hyperion Addition
    Launch Delays (IMAGE Swap)
    WARP (GFE) Rework
    Red Team Directed Risk Mitigations
HESSI UCB Actual Cost v Plan

## Slide 28: Cost
Metrics
  UCB Inter-Project Comparisons
  Instrument Grass Roots Estimate .v. Model at +6%
  Spacecraft Grass Roots Estimate .v. Model at +10%
  Sufficient Definition
  Detailed Cost Data ~290 pages
  Cost Changes During Phase A
  Simplified Probe Carrier by Baselining Larger LV
  Established Project Management, Systems Engineering
  Made Probe More Robust Adding Bottom S/A, Larger Battery
  Sufficient Reserve
  6% Greater than HESSI at the End of Phase A
  Able to Meet Programmatic Requirements at CR

## Slide 29: Summary
Summary
  Experienced Lead Personnel in Similar Projects
    PI mode projects, Small Spacecraft, End-to-End
  Proven Processes
    Management, Systems Engineering, Quality Assurance, Risk
  Simple and Robust Constellation Concept
    Simplified Launch Sequence, Fail-safe, Orbit Adjustment
  Comprehensive Schedule
    Either MIDEX Launch, Sufficient Time for Testing & Problems
  Detailed and Verified Cost Estimates
    Comprehensive, Verified to Models, Good Past Performance

## Slide 30: Backup Slides
Backup Slides

## Slide 31: SDB Goals
Small Disadvantaged Business Goals
  UC Office of President In Charge of SB/SDB Program
  Budget Analysis
  Accounting to Meet Federal Reporting Requirements
  Past Performance
  HESSI SDB > 33%
  THEMIS Will Meet NASA Goals
  Swales is SB > 21%, Hammers is SDB, UCLA is Minority Inst.
  UC Ordering procedure identifies business classification.

## Slide 32: Communications
Team Communications
  Day-to-Day
  Extensive use of Email Lists
  FTP sites for documents
  Web-Based Products and Video Conferencing
  Weekly Meetings
  Instrument
  Spacecraft
  Ground Systems
  Management, Systems Engineering and Science
  Monthly Meetings and Reports
  Comprehensive Meetings with Action Items
  On-site at Subcontractors
  Comprehensive Report Integrating All Internal Status
  Reports Available on the THEMIS website

## Slide 33: IV&V
Independent Verification and Validation
  Extensive Internal Review of Essential Software
  Bus Avionics Unit: Telecom, Bus Control, Minimal Autonomy
  IDPU : Instrument Control, Data Storage, Calculations
  Operations: ReUse of GSFC-supplied software
  Self Assessment using IV&V Metrics
  Loss of One Probe Yielded Consequence of Insignificant-Marginal
  Small Software Size Yielded Likelihood of 29-30
  Information Provided to IV&V for Cost Estimate/Concurrence
  Cost Assumptions
  Full IV&V Funding Included in Budget
  Assume IV&V Works with Available Documentation and Schedule