## Slide 1
THEMIS Executive Session
Peter R. Harvey
Project Manager
Space Sciences Laboratory
University of California, Berkeley

## Slide 2: Executive Session
AGENDA
  Cost Summary
  Changes in Phase A
  Cost Reasonableness
  Reserves
  Summary

## Slide 3: Cost
Cost Summary

## Slide 4: Cost
Cost Changes in Phase A
  Growth in Management, Systems Engineering
  Compared to HESSI Actual Costs Scaled to Development Task
  Now Matches within 0.2%
  Growth in Probe/Probe Carrier/LV
  Most Probe/PC Activity Directly Accountable to Risk Retirements
  Modest Growth in Defining Specific Suppliers, Spares, etc.

## Slide 5: Cost
Cost Reasonableness
  THEMIS Phase B/C/D Costs Compare Well to HESSI Actual Costs
  THEMIS Instruments Require Less Development than HESSI
  THEMIS Phase E Mission Operations Suitably Larger
  Handling 5 Probes Instead of 1; Cost Estimated at 3x

## Slide 6: Question 15: Heritage Cost
Question 15:
Many of the cited heritage instruments were significantly more expensive than the proposed instruments. What are the technical differences and why are you confident in the cost proposed for the THEMIS instruments? Please explain the THEMIS cost versus mass calculation.
Answer:
Differences are Minor
Simpler to Build
Easier to Use

## Slide 7: Question 15: Heritage Cost
Question 15 (Cont):
Instrument Mass .v. Cost Modeling
  Categorized Each Component by its Complexity
    EBOX : Electronics Box (src EFI & HESSI)
    MECH : Mechanism with Few Electronics Parts (src Cluster)
    SENSOR : Mixed Mechanical and Electronic Parts (src FAST)
  Computed Mass of Flight & Spare Units
    Grass Roots Budget is 6% Over Model So Budget is Sufficient

## Slide 8: Question 15: Heritage Cost
Question 15 (Cont):
Heritage Instruments Costs .v. THEMIS
  Typical NASA Instrument Contracts Have Greater Scope of Effort
    Science, Management, Systems Engineering, Quality Assurance
    Mission Operations and Data Analysis
    Significant Instrument Design and Development
    Instrument Sensors
    Instrument Main Electronics
    Instrument Flight Software
  THEMIS Sensor Costs
    Include Engineering for Interface-driven Modifications
    Include Sensor Fabrication and Test in Quantity
    Other Efforts are Costed in WBS 1 (Science, Management, Systems Engineering, Quality Assurance), WBS 2.1.1 (IDPU, FSW), WBS 4 (MODA)

## Slide 9: Reserve
Reserve
  Development Reserve of >25%
  Must Maintain 20% thru CR
  Emphasis on Design Phase
  Able to Meet Needs PDR/CDR
  Typically Review Team Gen’d
  Factor of 5 Impacts Foreseen
  LV Integration
  Supports 2 mo slip +15% CTC
  Performance Data from HESSI
  Ended Phase A at 19.4% Reserve but Used < 50% of it by Delivery

## Slide 10: Question 16 : Reserves
Question 16:
Please discuss why the proposed cost reserves are adequate, and your plan for managing these reserves. What is the justification for no Phase B and E cost reserves? How are descope decisions triggered?
Answer:
Reserves are Adequate at this Stage
  Believe 25% is Appropriate for the End of Phase A
  Mid-Point in Time Between Proposal and CR. Proposal Had 30%.
  HESSI Used less than 10%
Reserve Phasing
  Reserve Plan Starts in FY04, Consistent with PDR
  Prefer to Work a Complete Systemic Solution and Cost Changes by CR
  Reserves Fully Authorized through Launch.
    Minimal Options for Cost Recovery While Waiting for Launch
    Phase E Has Cost Saving Options (Limit Lifetime, Data Analysis Duration)
    If Reserve not Absolutely Needed for Launch, Will Be Available for MODA
Descope Trigger
  Estimated Cost to Complete Less Budget is Greater than Available Reserve.

## Slide 11: Question 16 : Reserves
Available Descope Options
  Modest Requirements Allow Flexibility in Instrumentation
  Cost Savings are Available

## Slide 12: Question 17: Incentives
Question 17:
The CSR Appendix Section M-8 (P. M184) indicates that at least a portion of the Swales incentive fee is an encumbrance against the project’s cost reserves. Please clarify the dollar impact of this encumbrance, and explain your rationale for this decision.
Answer:
Incentive Proposal
  2% for Probes/Probe Carrier Delivery on Time
  2% for Probes On-Orbit Performance
  Each is $750K
  Paid Only if Reserve is Available
Rationale
  On Schedule Delivery Incentive Compares to ~ 20 day Program Delay
  On-Orbit Performance Helps Keep Focus on Quality and Support in L&EO
  Used Successfully on HESSI
  Industry Standard Practice

## Slide 13: Summary
Summary
  Budget Resources are Sufficient
  Detailed, Changes Understandable and Modest
  Reserves are Adequate
  Meet Design Needs, Launch Delays, Past Performance