## Sheet1
Probe & Probe Carrier Built in Risk Mitigations
Risk/Potential Impact | Risk Mitigation in Design & Program Plan
Probe Separation System Design
Probe to Probe & Probe to Probe Carrier Recntact | 1) Redesigned PCA layout to provide more static clearance
2) Performed extensive separation analysis for Phase A
3) Conservative assumptions used in separation analysis
4) Performed nominal and multiple off nominal analysis cases
Spacecraft Bus Avionics Unit Design
Delay in design & fabrication resulting in Schedule & Cost impact | 1) Computation board design is based on heritage design (STEREO)
2) Power Control board design based on scaled down version of Swales PCE design (EO-1 & SMEX-Lite)
3) Communication Board design based on SMEX-Lite design
4) Outsource PCB Fabrication & Board Population to experienced qualified vendor.
5) EDU BDU built and tested in Phase B
S/C Mass & Power Margins
Mass and Power Growth Risk | 1) PRO-E models used to develop structural mass & subcontracted component masses based on vendor data from flight units currently in production
2) Current Mass and Power Margins exceed 40% at Phase A for Probe Bus
3) Detail power modeling with system designed for worst case eclipse.
4) EDU BDU built and tested in Phase B
Spacecraft Long Lead Times
Delay in Probe 1 procurement resulting in Schedule & Cost impact | 1) Swales has identified tanks that meet requirements and will CFE Tanks to RCS Integrator. (3 months after start of Phase B). We also have a backup stainless steel tank that could be used pending magnetic cleanliness and mass impact assessment. This will reduce the schedule by several months
- Propellant Tanks (critical path) | 2) Swales to provide coordinated tooling & flight structure to RCS Integrator to minimize schedule
- RCS Hardware Integration (critical path) | 3) Several RCS proposals to choose from that meet schedule. (Have had face to face discussions with three vendors)
4) Critical path which is Propellant Tank & RCS integration has a 32 day (working days) float assuming a March 03 start.
- S Band Transponder | 5) Have held face to face discussions with Transponder vendor on schedule.
Risk/Potential Impact | Risk Mitigation in Design & Program Plan
Probe 1 Build & Test
Delay in build & test of Probe 1 resulting in Schedule & Cost impacts for Probe 1 and subsequent Probes | 1) Detail schedule developed in Phase A for Probe procurement, fabrication and test.
2) Allocated 71 work weeks post CDR for build and test of Probe 1 with an additional 12 work weeks of contingency.
3) Full I&T Core Team assigned to build of Probe 1 prior to starting Probe 2 I&T
4) Satellite Test Bed includes BAU EDU, Battery, IDPU Simulator & ITOS for offline testing & Flight Software Development
Probe 2 - 5 Build & Test
Delay in Probes 2 - 5 build and test result in Schedule & Cost impact | 1) Ample time between the completion of Probe 1 Integration and the start of Probe 2 & 3 Integration. (Contingency 60 working days)
2) Probe 2 through 5 Bus integration have 40 working days of contingency
3) Cross train teams from Probe 1 Build are assigned to Probe 2,4 and Probe 3,5
4) Multiple sets of EGSE available for testing several Probes in parallel.
Instrument Integration
Complexity of Instrument integration could cause schedule delays resulting in higher costs | 1) IDPU and S/C BAU use identical computation board
2) Instrument suites are integrated at UCB using Swales provided Spacecraft Simulator & Bus uses Instrument Simulator.
3) Boom designs are heritage and are fully qualified prior to delivery to Swales
4) Instrument mechanical interfaces are straight forward with adequate volume/clearances.
5) IDPU and BAU processing are decoupled
Overall Schedule/Cost for Probes & Probe Carrier | 1) All contingency periods fully costed with Core Team.
2) Schedule is based on 5 day work week one shift with the exception of system level testing (CPT, TV, etc.) which is 3 shift operation. Additional shifts can be added to reduce schedule.
3) Detail costing performed down to the 5 element of the Spacecraft WBS parametric validation using SSCM.
4) Assumed serial TV testing for Probes 2 & 5. Parallel testing can be performed to reduce schedule.
5) Probe Carrier pricing based on Swales extensive experience from Aerospace Products Business
6) All major subcontracted component costs are based on qualified vendor quotes.