## Change Log
Date | POC | Details | REV
2003-03-17 | PRH/GD | CSR Baseline | G
2003-06-10 | ERT | Updated from Instrument Requirement Peer Reviews, Preliminary ICDs. Split out mass budget to track seperately. | H
2003-07-31 | ERT | Reviewed with P.Berg. Added total current and power for each service. Corrected Voltage typo. Added 3 SMA services for ESA. | I
2003-09-12 | ERT | Added Power History (Probe and Instruments). Added PCB power. Combined SST and ESA I/F to ETC. Updated BEB, DCB, ETC. | J
2003-10-10 | ERT | Updated SCM and FGM from Peer Reviews, New Allocations | K
2003-11-10 | ERT | Updated per Spacecraft and Instrument PDR numbers | L
2004-01-10 | ERT | Monthly Update | M
2004-01-31 | ERT | Changed Instrument LVPS numbers to replace LM5030. Added Current Limit Calcs. | M.1
2/31/2004 | ERT | January Monthly Update | N
2004-03-31 | ERT | February Monthly Update | O
2004-04-12 | ERT | New PCB/DCB allocations | O.1
2004-04-14 | ERT | March Monthly Update | P
2004-05-14 | ERT | April Monthly Update | Q
2004-06-20 | ERT | May Monthly Update | R
2004-07-10 | ERT | June Monthly Update | S
2004-08-13 | ERT | July Monthly Update | T
2004-09-20 | ERT | August Monthly Update | U
2004-10-11 | ERT | September Monthly Update | V
2004-11-12 | ERT | October Monthly Update | W
2004-12-11 | ERT | November Monthly Update | X
2005-01-15 | ERT | December Montly Update | Y
2005-01-27 | ERT | Updated Instrument Power - January | Z
2005-02-15 | ERT | February Monthly Update | AA
2005-05-20 | ERT | March Monthly Update | AB
2005-05-20 | ERT | April Monthly Update | AC
2005-06-15 | ERT | May Monthly Update | AD
2005-07-20 | ERT | June Monthly Update | AE
2005-08-28 | ERT | July Monthly Update | AF
2005-09-10 | ERT | August Monthly Update | AG
2005-10-31 | ERT | September Monthly Update | AH

## Power History
THEMIS Power Tracking
Instrument | Allocations | Phase A Predict |  | Rev H July-03 |  | Rev I Aug-03 |  | Rev J Sept-03 |  | Allocations | Rev K Oct-03 |  | Rev L Nov-03 |  | Rev M Dec-03 |  | Allocations | Rev N Jan-04 |  | Rev O Feb-04 |  | Rev P March-04 |  | Rev Q April-04 |  | Rev R May-04 |  | Rev S June-04 |  | Rev T July-04 |  | Allocations | Rev U August-04 |  | Rev V Sept-04 |  | Rev W Oct-04 |  | Rev X Nov-04 |  | Rev Y Dec-04 |  | Rev Z Jan-05 |  | Rev AA Feb-05 |  | Rev AB Mar-05 |  | Rev AC Apr-05 |  | Rev AD May-05 |  | Rev AE June-05 |  | Rev AF July-05 |  | Rev AG Aug-05 |  | Rev AH Sept-05
Subsystems | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont.
| (W) | (W) | % | (W) | % | (W) | % | (W) | % | (W) | (W) | % | (W) | % | (W) | % | (W) | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | %
FGM | 0.01 | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.01 | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.01 | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.01 | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11%
Sensor | 0.01 | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.01 | 0.009 | 11.11% | 0.009 | 11.11% | 0.009 | 11.11% | 0.01 | 0.009 | 11.11% | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.01 | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE! | 0.009 | #VALUE!
SCM | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5%
Pre-Amps | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.09 | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE! | 0.08 | #VALUE!
ESA | 2.01 | 1.87 | 7.487% | 1.87 | 7.487% | 1.88 | 6.915% | 1.88 | 6.915% | 2.01 | 1.88 | 6.915% | 1.88 | 6.915% | 1.88 | 6.915% | 2.01 | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 2.01 | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56% | 1.77 | 13.56%
Sensor | 2.01 | 1.87 | 7.487% | 1.87 | 7.487% | 1.88 | 6.915% | 1.88 | 6.915% | 2.01 | 1.88 | 6.915% | 1.88 | 6.915% | 1.88 | 6.915% | 2.01 | 1.77 | 13.56% | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 2.01 | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE! | 1.77 | #VALUE!
SST | 1.06 | 0.85 | 24.71% | 0.85 | 24.71% | 0.87 | 21.84% | 0 | N/A | 0.3 | 0.27 | N/A | 0.27 | N/A | 0.27 | N/A | 0.3 | 0.27 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.3 | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A | 0.32 | N/A
Sensor Electronics | 1.06 | 0.85 | 24.71% | 0.85 | 24.71% | 0.87 | 21.84% | 0 | N/A | 0.3 | 0.27 | 11.11% | 0.27 | 11.11% | 0.27 | 11.11% | 0.3 | 0.27 | 11.11% | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.3 | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE! | 0.32 | #VALUE!
EFI | 0.54 | 0.48 | 12.5% | 0.48 | 12.5% | 0.48 | 12.5% | 0.48 | 12.5% | 0.53 | 0.48 | 10.42% | 0.48 | 10.42% | 0.48 | 10.42% | 0.53 | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.53 | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22% | 0.36 | 47.22%
Radial Unit 1 | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.06 | 50% | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.09 | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE!
Radial Unit 2 | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.06 | 50% | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.09 | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE!
Radial Unit 3 | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.06 | 50% | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.09 | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE!
Radial Unit 4 | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.06 | 50% | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.09 | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE!
Axial Unit 1 | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.06 | 50% | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.09 | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE!
Axial Unit 2 | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.08 | 12.5% | 0.08 | 12.5% | 0.08 | 12.5% | 0.09 | 0.06 | 50% | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.09 | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE! | 0.06 | #VALUE!
IDPU | 11.06 | 8.85 | 24.97% | 8.83 | 25.25% | 8.861 | 24.82% | 8.861 | 24.82% | 11.825 | 9.21 | 28.39% | 9.1 | 29.95% | 9.1 | 29.95% | 11.825 | 10.64 | 11.14% | 10.2 | 15.93% | 10.175 | 16.22% | 10.175 | 16.22% | 10.175 | 16.22% | 10.175 | 16.22% | 10.175 | 16.22% | 11.825 | 10.575 | 11.82% | 10.865 | 8.836% | 11.727 | 0.8357% | 11.727 | 0.8357% | 11.727 | 0.8357% | 11.727 | 0.8357% | 11.727 | 0.8357% | 11.727 | 0.8357% | 11.727 | 0.8357% | 11.727 | 0.8357% | 11.727 | 0.8357% | 11.727 | 0.8357% | 11.727 | 0.8357% | 11.727 | 0.8357%
[4] DFB | 0.83 | 0.66 | 25.76% | 0.7 | 18.57% | 0.7 | 18.57% | 0.7 | 18.57% | 1 | 0.86 | 16.28% | 0.86 | 16.28% | 0.86 | 16.28% | 1 | 1.29 | -22.48% | 1.06 | #VALUE! | 1.055 | #VALUE! | 1.055 | #VALUE! | 1.055 | #VALUE! | 1.055 | #VALUE! | 1.055 | #VALUE! | 1 | 1.08 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE! | 1.17 | #VALUE!
[5] BEB | 2.62 | 2.09 | 25.36% | 2.09 | 25.36% | 2.09 | 25.36% | 2.09 | 25.36% | 1.765 | 1.04 | 69.71% | 1.04 | 69.71% | 1.04 | 69.71% | 1.765 | 1.04 | 69.71% | 1.33 | #VALUE! | 1.325 | #VALUE! | 1.325 | #VALUE! | 1.325 | #VALUE! | 1.325 | #VALUE! | 1.325 | #VALUE! | 1.765 | 1.37 | #VALUE! | 1.37 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE! | 1.373 | #VALUE!
[2] FGE | 1 | 0.8 | 25% | 0.57 | 75.44% | 0.6 | 66.67% | 0.6 | 66.67% | 0.9 | 0.76 | 18.42% | 0.76 | 18.42% | 0.76 | 18.42% | 0.9 | 0.96 | -6.25% | 0.76 | #VALUE! | 0.755 | #VALUE! | 0.755 | #VALUE! | 0.755 | #VALUE! | 0.755 | #VALUE! | 0.755 | #VALUE! | 0.9 | 0.76 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE! | 0.96 | #VALUE!
[2] PCB | 0 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 1.7 | 1.53 | 11.11% | 1.53 | 11.11% | 1.53 | 11.11% | 1.7 | 1.33 | 27.82% | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 1.7 | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE! | 0.88 | #VALUE!
[3] ETC | 0.74 | 0.6 | 23.33% | 0.6 | 23.33% | 0.6 | 23.33% | 0.6 | 23.33% | 0.75 | 0.62 | 20.97% | 0.62 | 20.97% | 0.62 | 20.97% | 0.75 | 0.62 | 20.97% | 0.29 | #VALUE! | 0.285 | #VALUE! | 0.285 | #VALUE! | 0.285 | #VALUE! | 0.285 | #VALUE! | 0.285 | #VALUE! | 0.75 | 0.47 | #VALUE! | 0.47 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE! | 0.64 | #VALUE!
[3] SST Interface | 0.25 | 0.2 | 25% | 0.2 | 25% | 0.2 | 25% | 0.2 | 25% | 0 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A
[3] DCB | 3.09 | 2.48 | 24.6% | 2.48 | 24.6% | 2.475 | 24.85% | 2.475 | 24.85% | 1.2 | 0.91 | 31.87% | 0.91 | 31.87% | 0.91 | 31.87% | 1.2 | 0.91 | 31.87% | 1.72 | #VALUE! | 1.715 | #VALUE! | 1.715 | #VALUE! | 1.715 | #VALUE! | 1.715 | #VALUE! | 1.715 | #VALUE! | 1.2 | 1.715 | #VALUE! | 1.715 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE! | 1.95 | #VALUE!
[1] LVPS | 2.53 | 2.02 | 25.25% | 2.19 | 15.53% | 2.196 | 15.21% | 2.196 | 15.21% | 3.45 | 2.63 | 31.18% | 2.52 | 36.9% | 2.52 | 36.9% | 3.45 | 3.35 | 2.985% | 3.3 | #VALUE! | 3.3 | #VALUE! | 3.3 | #VALUE! | 3.3 | #VALUE! | 3.3 | #VALUE! | 3.3 | #VALUE! | 3.45 | 3.3 | #VALUE! | 3.3 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE! | 3.694 | #VALUE!
[6] SST ADC | 0 | 0 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 1.06 | 0.86 | 23.26% | 0.86 | 23.26% | 0.86 | 23.26% | 1.06 | 1.14 | -7.018% | 0.86 | #VALUE! | 0.86 | #VALUE! | 0.86 | #VALUE! | 0.86 | #VALUE! | 0.86 | #VALUE! | 0.86 | #VALUE! | 1.06 | 1 | #VALUE! | 1 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE! | 1.06 | #VALUE!
TOTAL | 14.77 | 12.139 | 21.67% | 12.119 | 21.87% | 12.18 | 21.26% | 11.31 | 30.59% | 14.765 | 11.929 | 23.82% | 11.819 | 24.97% | 11.819 | 24.97% | 14.765 | 13.129 | 12.5% | 12.739 | 15.94% | 12.714 | 16.17% | 12.714 | 16.17% | 12.714 | 16.17% | 12.714 | 16.17% | 12.714 | 16.17% | 14.765 | 13.114 | 12.63% | 13.404 | 10.19% | 14.266 | 3.533% | 14.266 | 3.533% | 14.266 | 3.533% | 14.266 | 3.533% | 14.266 | 3.533% | 14.266 | 3.533% | 15.26 | -3.211% | 16.1 | -8.261% | 16.1 | -8.261% | 16.1 | -8.261% | 16.1 | -8.261% | 15.3 | -3.464%
Probe Bus | Allocations | Phase A Predict |  | Rev 2 July-03 |  | Rev 3 Aug-03 |  | Rev 4 Sept-03 |  | Allocations | Rev 5 Oct-03 |  | Rev 6 Nov-03 |  | Rev 7 Dec-03 |  | Allocations | Rev 8 Jan-04 |  | Rev 9 Feb-04 |  | Rev 10 March-04 |  | Rev 11 April-04 |  | Rev 12 May-04 |  | Rev 13 June-04 |  | Rev 14 July-04 |  | Allocations | Rev 15 August-04 |  | Rev 16 Sept-04 |  | Rev 17 Oct-04 |  | Rev 18 Nov-04 |  | Rev 19 Dec-04 |  | Rev 20 Jan-05 |  | Rev 21 Feb-05 |  | Rev 22 Mar-05 |  | Rev 22 Apr-05 |  | Rev 22 May-05 |  | Rev 23 June-05 |  | Rev 24 Jul-05 |  | Rev 25 Aug-05 |  | Rev 25 Sept-05
Subsystems | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont.
| (W) | (W) | % | (W) | % | (W) | % | (W) | % | (W) | (W) | % | (W) | % | (W) | % | (W) | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | %
ACS | 0.16 | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.16 | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.16 | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.16 | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08% | 0.13 | 23.08%
ELECTRICAL | 12.04 | 10.25 | 17.46% | 10.25 | 17.46% | 10.25 | 17.46% | 10.25 | 17.46% | 12.04 | 10.25 | 17.46% | 10.25 | 17.46% | 10.56 | 14.02% | 12.04 | 10.56 | 14.02% | 11.17 | 7.789% | 11.17 | 7.789% | 11.17 | 7.789% | 11.07 | 8.762% | 11.07 | 8.762% | 11.07 | 8.762% | 12.04 | 11.07 | 8.762% | 11.07 | 8.762% | 11.07 | 8.762% | 11.07 | 8.762% | 11.07 | 8.762% | 11.07 | 8.762% | 11.07 | 8.762% | 12.3 | -2.114% | 12.3 | -2.114% | 12.3 | -2.114% | 12.3 | -2.114% | 12.3 | -2.114% | 12.3 | -2.114% | 12.3 | -2.114%
Avionics |  | 5 |  | 5 |  | 5 |  | 5 |  |  | 5 |  | 5 |  | 6.24 |  |  | 6.24 |  | 6.24 |  | 6.24 |  | 6.24 |  | 6.1 |  | 6.1 |  | 6.1 |  |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1 |  | 6.1
Comm |  | 5.25 |  | 5.25 |  | 5.25 |  | 5.25 |  |  | 5.25 |  | 5.25 |  | 4.32 |  |  | 4.32 |  | 4.93 |  | 4.93 |  | 4.93 |  | 4.97 |  | 4.97 |  | 4.97 |  |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97 |  | 4.97
POWER
THERMAL | 2.3 | 2 | 15% | 2 | 15% | 2 | 15% | 2 | 15% | 2.3 | 2 | 15% | 2 | 15% | 4 | -42.5% | 2.3 | 2 | 15% | 2.1 | 9.524% | 2.1 | 9.524% | 2.1 | 9.524% | 3.5 | -34.29% | 3.5 | -34.29% | 3.5 | -34.29% | 8 | 7.1 | 12.68% | 7.1 | 12.68% | 7.1 | 12.68% | 7.1 | 12.68% | 7.1 | 12.68% | 7.1 | 12.68% | 7.1 | 12.68% | 5.9 | 35.59% | 5.9 | 35.59% | 5.9 | 35.59% | 5.9 | 35.59% | 5.9 | 35.59% | 5.9 | 35.59% | 5.9 | 35.59%
Control |  | 2 |  | 2 |  | 2 |  | 2 |  |  | 2 |  | 2 |  | 4 |  |  | 2 |  | 2.1 |  | 2.1 |  | 2.1 |  | 3.5 |  | 3.5 |  | 3.5 |  |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1 |  | 7.1
TOTAL | 14.5 | 12.38 | 17.12% | 12.38 | 17.12% | 12.38 | 17.12% | 12.38 | 17.12% | 14.5 | 12.38 | 17.12% | 12.38 | 17.12% | 14.69 | -1.293% | 14.5 | 12.69 | 14.26% | 13.4 | 8.209% | 13.4 | 8.209% | 13.4 | 8.209% | 14.7 | -1.361% | 14.7 | -1.361% | 14.7 | -1.361% | 20.2 | 18.3 | 10.38% | 18.3 | 10.38% | 18.3 | 10.38% | 18.3 | 10.38% | 18.3 | 10.38% | 18.3 | 10.38% | 18.3 | 10.38% | 18.33 | 10.2% | 18.33 | 10.2% | 18.33 | 10.2% | 18.33 | 10.2% | 18.33 | 10.2% | 18.33 | 10.2% | 18.33 | 10.2%
Probe 1 (Worst Case) | Allocations | Phase A Predict |  | 2003-07-03 |  | 2003-08-03 |  | 2003-09-03 |  | Allocations | 2003-10-03 |  | 2003-11-03 |  | 2003-12-03 |  | Allocations | 2004-01-03 |  | 2004-02-03 |  | 2004-03-03 |  | 2004-04-03 |  | 2004-05-03 |  | 2004-06-03 |  | 2004-07-03 |  | Allocations | 2004-08-03 |  | 2004-09-03 |  | 2004-10-03 |  | 2004-11-03 |  | 2004-12-03 |  | 2005-01-05 |  | 2005-02-05 |  | 2005-03-05 |  | 2005-04-05 |  | 2005-05-05 |  | 2005-06-05 |  | 2005-07-05 |  | 2005-09-05 |  | 2005-09-05
Elements | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Power | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont. | Pwr | Cont.
| (W) | (W) | % | (W) | % | (W) | % | (W) | % | (W) | (W) | % | (W) | % | (W) | % | (W) | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | % | (W) | %
Probe 1 Bus | 14.5 | 12.38 | 17.12% | 12.38 | 17.12% | 12.38 | 17.12% | 12.38 | 17.12% | 14.5 | 12.38 | 17.12% | 12.38 | 17.12% | 14.69 | -1.293% | 14.5 | 12.69 | 14.26% | 13.4 | 8.209% | 13.4 | 8.209% | 13.4 | 8.209% | 14.7 | -1.361% | 14.7 | -1.361% | 14.7 | -1.361% | 20.2 | 18.3 | 10.38% | 18.3 | 10.38% | 18.3 | 10.38% | 18.3 | 10.38% | 18.3 | 10.38% | 18.3 | 10.38% | 18.3 | 10.38% | 18.33 | 10.2% | 18.33 | 10.2% | 18.33 | 10.2% | 18.33 | 10.2% | 18.33 | 10.2% | 18.33 | 10.2% | 18.33 | 10.2%
Probe 1 Instruments | 14.77 | 12.139 | 21.67% | 12.119 | 21.87% | 12.18 | 21.26% | 11.31 | 30.59% | 14.77 | 11.929 | 23.82% | 11.819 | 24.97% | 11.819 | 24.97% | 14.77 | 13.129 | 12.5% | 12.739 | 15.94% | 12.714 | 16.17% | 12.714 | 16.17% | 12.714 | 16.17% | 12.714 | 16.17% | 12.714 | 16.17% | 14.77 | 13.114 | 12.63% | 13.404 | 10.19% | 14.266 | 3.533% | 14.266 | 3.533% | 14.266 | 3.533% | 14.266 | 3.533% | 14.266 | 3.533% | 14.266 | 3.533% | 15.26 | -3.211% | 16.1 | -8.261% | 16.1 | -8.261% | 16.1 | -8.261% | 16.1 | -8.261% | 15.3 | -3.464%
Probe 1 Total | 29.27 | 24.519 | 19.38% | 24.499 | 19.47% | 24.56 | 19.18% | 23.69 | 23.55% | 29.27 | 24.309 | 20.41% | 24.199 | 20.96% | 26.509 | 10.42% | 29.27 | 25.819 | 13.37% | 26.139 | 11.98% | 26.114 | 12.09% | 26.114 | 12.09% | 27.414 | 6.77% | 27.414 | 6.77% | 27.414 | 6.77% | 34.97 | 31.414 | 11.32% | 31.704 | 10.3% | 32.566 | 7.382% | 32.566 | 7.382% | 32.566 | 7.382% | 32.566 | 7.382% | 32.566 | 7.382% | 32.596 | 7.283% | 33.59 | 4.108% | 34.43 | 1.568% | 34.43 | 1.568% | 34.43 | 1.568% | 34.43 | 1.568% | 33.63 | 3.985%
Daylight Power | 41.5 | [8 empty] | 41.5 | [6 empty] | 37 | [14 empty] | 37
Daylight Power Margin |  |  | 69.26% |  | 69.39% |  | 68.97% |  | 75.18% |  |  | 70.72% |  | 71.49% |  | 56.55% |  |  | 43.31% |  | 41.55% |  | 41.69% |  | 41.69% |  | 34.97% |  | 34.97% |  | 34.97% |  |  | 17.78% |  | 16.7% |  | 13.62% |  | 13.62% |  | 13.62% |  | 13.62% |  | 13.62% |  | 13.51% |  | 10.15% |  | 7.464% |  | 7.464% |  | 7.464% |  | 7.464% |  | 10.02%
Eclipse Power | 49 | 49 |  | 49 |  | 49 |  | 49 |  | 49 | 49 |  | 49 |  | 53.4 |  | 53.4 | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4 |  | 53.4
Orbit Average | 42.4375 | 27.5791 |  | 27.5616 |  | 27.615 |  | 26.8538 |  | 42.4375 | 27.3954 |  | 27.2991 |  | 29.8704 |  | 39.05 | 29.2666 |  | 29.5466 |  | 29.5248 |  | 29.5248 |  | 30.6623 |  | 30.6623 |  | 30.6623 |  | 39.05 | 34.1623 |  | 34.416 |  | 35.1703 |  | 35.1703 |  | 35.1703 |  | 35.1703 |  | 35.1703 |  | 35.1965 |  | 36.0662 |  | 36.8013 |  | 36.8013 |  | 36.8013 |  | 36.8013 |  | 36.1013
Orbit Avg Power Margin |  |  | 53.88% |  | 53.97% |  | 53.68% |  | 58.03% |  |  | 54.91% |  | 55.45% |  | 42.07% |  |  | 33.43% |  | 32.16% |  | 32.26% |  | 32.26% |  | 27.36% |  | 27.36% |  | 27.36% |  |  | 14.31% |  | 13.46% |  | 11.03% |  | 11.03% |  | 11.03% |  | 11.03% |  | 11.03% |  | 10.95% |  | 8.273% |  | 6.111% |  | 6.111% |  | 6.111% |  | 6.111% |  | 8.168%
| Phase A | 2003-07-31 | 2003-08-31 | 2003-09-30 | 2003-10-31 | 2003-11-30 | 2003-12-31 | 2004-01-31 | 2004-02-28 | 2004-03-31 | 2004-04-30 | 2004-05-31 | 2004-06-30 | 2004-07-30 | 2004-08-30 | 2004-09-30 | 2004-10-30 | 2004-11-30 | 2004-12-30 | [8 empty] | Generated | Allocated | CBE
P1 Capability | 42.44 | 42.44 | 42.44 | 42.44 | 42.44 | 42.44 | 42.44 | 39.05 | 39.05 | 39.05 | 39.05 | 39.05 | 39.05 | 39.05 | 39.05 | 39.05 | 39.05 | 39.05 | 39.05 | [8 empty] | 32.31 | 34.7 | 26.51 | 20.5
Total Allocated | 31.74 | 31.74 | 31.74 | 31.74 | 31.74 | 31.74 | 31.74 | 31.74 | 31.74 | 31.74 | 31.74 | 31.74 | 31.74 | 31.74 | 36.49 | 36.49 | 36.49 | 36.49 | 36.49 | [8 empty] | 49 | 49 | 47.81 | 3
Total CBE | 27.5791 | 27.5616 | 27.615 | 26.8538 | 27.3954 | 27.2991 | 29.8704 | 29.2666 | 29.5466 | 29.5248 | 29.5248 | 30.6623 | 30.6623 | 30.6623 | 34.1623 | 34.416 | 35.1703 | 35.1703 | 35.1703
Margin % | [27 empty] | 35 | 35 | 61.51 | 0.5
Margin Schedule | 30% | 20% | 20% | 20% | 20% | 20% | 15% | 15% | 15% | 15% | 15% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | [8 empty] | 34.4523 | 36.4937 | 29.9017
Contingency Schedule | 10% | 10% | 10% | 10% | 10% | 7.5% | 7.5% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 6% | 4% | 4% | 4%
Instrument CBE+Cont. | 14.77 | 14.77 | 14.77 | 14.77 | 14.765 | 14.765 | 14.765 | 14.765 | 14.765 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | [8 empty] | Margin | Cont. | Total
Instrument CBE | 12.139 | 12.119 | 12.18 | 11.91 | 11.929 | 11.819 | 11.819 | 13.129 | 12.739 | 12.714 | 12.714 | 12.714 | 12.714 | 12.714 | 13.114 | 13.404 | 14.266 | 14.266 | 14.266 | [6 empty] | ORBIT AVG. |  | -5.594 | 22.0459 | 15.2186
Instrument Contingency % | 21.67% | 21.87% | 21.26% | 30.59% | 23.82% | 24.97% | 24.97% | 12.5% | 15.94% | 16.17% | 16.17% | 16.17% | 16.17% | 16.17% | 12.63% | 10.19% | 3.533% | 3.533% | 3.533% | [6 empty] | DAYLIGHT |  | -6.8876 | 30.894 | 21.8785
Contingency | 13.4273 | 13.4273 | 13.4273 | 13.4273 | 13.4227 | 13.7349 | 13.7349 | 13.9292 | 13.9292 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Probe CBE+Cont. | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 20.2 | 20.2 | 20.2 | 20.2 | 20.2
Probe CBE | 12.38 | 12.38 | 12.38 | 12.38 | 12.38 | 12.38 | 14.69 | 12.69 | 13.4 | 13.4 | 13.4 | 14.7 | 14.7 | 14.7 | 18.3 | 18.3 | 18.3 | 18.3 | 18.3
Probe Contingency % | 17.12% | 17.12% | 17.12% | 17.12% | 17.12% | 17.12% | -1.293% | 14.26% | 8.209% | 8.209% | 8.209% | -1.361% | -1.361% | -1.361% | 10.38% | 10.38% | 10.38% | 10.38% | 10.38%
CONTINGENCY: | % | 2003-08-31: MARGIN:; 2003-09-30: %
Concept | 25 | 2003-08-31: Concept; 2003-09-30: >30
Design | 15 | 2003-08-31: PDR; 2003-09-30: 15-20
Prior Build | 7.5 | 2003-08-31: CDR; 2003-09-30: 10-15
Fab | 4 | 2003-08-31: PER; 2003-09-30: 5-10
Flight | 2 | 2003-08-31: PSR; 2003-09-30: 0-5