## Sheet1
Description | Assembly | SubAssy | Component | Engineer | Swales PRB | 1 | 2 | 3 | 4 | 5 | 6 | Link | Corrective Action
PFR 001 BEB Actel/Amux Failure | IDPU | BEB | FPGA | Richard | [7 empty] | thm_pfr_001_BEBActel.pdf | Rework all 6 | bar: 1 to 6
PFR 002 SCM Calibration Level | SCM | PreAmp | Cal Circuit | Bouabdellah | [7 empty] | thm_pfr_002_SCMCal.pdf | Used as is | bar: 1 to 6
PFR 003 FGE TML Data overflow | IDPU | FGE | FPGA | Magnes | [7 empty] | thm_pfr_003_FGMData.pdf | Rework #6 | bar: 1 to 6
PFR 004 SPB Cable Damaged during Restow | EFI | SPB | Cable | Donakowski | [7 empty] | thm_pfr_004_SPB Cable Fraying.pdf | Repair #1 only | bar: 1 to 6
PFR 005 SCM FM2 Structure | SCM | Antenna | Structure | Bouabdellah | [7 empty] | thm_pfr_005_SCMstructure.pdf | Replace #2 w #4 | bar: 1 to 6
PFR 006 DFB Resistor mis-installation | IDPU | DFB | Assy | Nammari | [7 empty] | thm_pfr_006_dfb Assy.pdf | Resistors re-loaded | bar: 1 to 6
PFR 007 Actel Lead Forming | GSE | Tool | Actel | Bersch | [7 empty] | thm_pfr_007_ ActelLeadDamage1.pdf | GSE replaced | bar: 1 to 6
PFR 008 SST ETU2 Vibration | SST | Sensor | Structure | Lee | [7 empty] | thm_pfr_008_sst ETU Vibe.pdf | ETU reinforced SMA replaced | bar: 1 to 6
PFR 009 SST Attenuator in Thermal Vac | SST | Sensor | Attenuator | Lee | [7 empty] | thm_pfr_009_sst.pdf | GSE Cable replaced | bar: 1 to 6
PFR 010 SPB FM1/FM2 Tolerance Margin | EFI | SPB | Release | Donakowski | [7 empty] | thm_pfr_010_grounding sma wire.pdf | Remove screws all units | bar: 1 to 6
PFR 011 SST Reinforcement Plate Epoxy Vib Failure | SST | Sensor | Structure | Lee | [7 empty] | thm_pfr_011_SST Sensor Struct Reinforcement.pdf | Redesigned structure | bar: 1 to 6
PFR 012 EFI Preamp Ferrule/Ferrule Spring Design causing int. elect. Ctc betw. Sensor & PA input | EFI | PreAmp | Spring | Hull | [7 empty] | thm_pfr_012 _Ferrule spring ctct prblm.pdf | Redesign | bar: 1 to 6
PFR013 ESA sweep board | ESA | SWP I/F | Layout | Carlson | [7 empty] | thm_pfr_013ESA Sweep IF refab.pdf | ETU Failure, PWB remade | bar: 1 to 6
PFR014 PCB/FGE | IDPU | PCB | Assy | Chen | [7 empty] | thm_pfr_014_PCB_SN005.pdf | Loaded resistor | bar: 1 to 6
PFR015 SPB F2 inner bearing crack'd in installation | EFI | SPB | Bearings | Donakowski | [7 empty] | thm_pfr_015_bearing_failure.pdf | Replaced Bearings | bar: 1 to 6
PFR016 DFB POR when commanded | IDPU | DFB | U49 | Nammari | [7 empty] | thm_PFR_016_DFB.pdf | Added bypass capacitors | bar: 1 to 6
PFR017 FGM Data Missing | GSE | PROC | FGM.on | Chen | [7 empty] | thm_pfr_017 FGM Data Missing.pdf | Added "force on" to turn on script | bar: 1 to 6
PFR018 SPB Deploy simulation failure | GSE | Harness | SPB | Harvey | [7 empty] | thm_PFR_018Deploy simulation.pdf | New Cable | bar: 1 to 6
PFR019 EFI ETU BEB-DFB SMA Harness Failure | EFI | Harness | SMA | Richard | [7 empty] | thm_pfr_019_EFIETU SMA Harness failure.pdf | Replaced ETU w/ Flight | bar: 1 to 6
PFR020 SPB sphere key reel axle friction | EFI | SPB | Keyreel | Dalton | [7 empty] | thm_pfr_020 SPB Keyreel Spring Axle Mod1.pdf | Remachined all keyreels | bar: 1 to 6
PFR021 SPB cable damaged during proof load test (F3 SPB cable) | EFI | SPB | Cable | Schickele | [7 empty] | thm_pfr_021 SPB Cable Airborne Repair.pdf | Repaired pins | bar: 1 to 6
PFR022 FM1 Sphere Mislocation | EFI | SPB | Doors | Donakowski | [7 empty] | thm_pfr_022_SPHERE MISLOCATION1.pdf | Opened & repositioned sphere | bar: 1 to 6
PFR023 IDPU DCB Backplane Bad connection | IDPU | DCB | Backplane | Ludlam | [7 empty] | thm_pfr_23_IDPU DCB bkpln bad connex.pdf | UVF temporarily opened | bar: 1 to 6
PFR024 Uncured AXB cable Potting Compound (F3 AXBs) | EFI | AXB | Potting | Duck | [7 empty] | thm_pfr_024 AXB Cable Potting Compound.pdf | Baked & Cleaned Compund | bar: 1 to 6
PFR025 Cracked Feet in SCB Frangibolt/DAD Tower | MAG | SCB | DAD Tower | Tan | [7 empty] | thm_pfr_025Crckd feet scb frangibolt.pdf | Replaced DAD Tower | bar: 1 to 6
PFR026 Sensor Door Axle/Mount failure (F3 Lower AXB) | EFI | AXB | Sensor Door | Duck | [7 empty] | thm_pfr_26 AXB SDM Failure.pdf | Replaced F3, inspected others | bar: 1 to 6
PFR027 Cracked Base Bracket in SCB | MAG | SCB | Base | Tan | [7 empty] | thm_pfr_027cracked base bracket SCB.pdf | Replaced tower, used steel washers | bar: 1 to 6
PFR028 DFB Resistor Misplacement FM2 | IDPU | DFB | Assy | Stevens | [7 empty] | thm_pfr_028DFB resistor misplacement FM2.pdf | Loaded resistors correctly | bar: 1 to 6
PFR029 Solder Bridge On FPGA #2 on FM2 | IDPU | DFB | FPGA 2 | Stevens | [7 empty] | thm_pfr_029Solder Bridge on FPGA no2FM2.pdf | Replaced Actel | bar: 1 to 6
PFR030 Actuator Commands | IDPU | PCB | FPGA | Harvey | [7 empty] | thm_pfr_030ActuatorCommands.pdf | FSW script changed EPROM | bar: 1 to 6
PFR031 DCB sn2 SST Clock Shorted to Vcc | IDPU | DCB | FPGA | Ludlam | [7 empty] | thm_pfr_031 DCB sn2 SST Clock shorted to Vcc.pdf | Replaced Part, removed solder bridge, closed 8/5/05 | bar: 1 to 6
PFR032 FGM increased current during TV | IDPU | FGE | PROC | Aydogar | [7 empty] | thm_pfr_032_FGM_F3_electronics.pdf | Improved Thermal Cycle Proc | bar: 1 to 6
PFR033 Actel Pins Solder Bridge | IDPU | BEB | FPGA | Richard | [7 empty] | thm_pfr_033_Actel Pins Solder Bridge.pdf | Removed VDD-DGND Solder Bridge | bar: 1 to 6
PFR034 DAP SN83 tripped IDPU supply during turn-on | IDPU | PCB | CAPS | Chen | [7 empty] | thm_pfr_034DAP_SN083.pdf | Added capacitors for DAP turn on | bar: 1 to 6
PFR035 Open Vsphere Line on SPB-912 | EFI | SPB | Cable | Bonnell | [7 empty] | thm_pfr_035_open Vsphere line SPB-912.pdf | Modified soldering technique | bar: 1 to 6
PFR036 LVPS EFI Digital 2.5VD Connex Error | IDPU | LVPS | Layout | Heavner | [7 empty] | thm_pfr_036_LVPS_EFI_Digital_Connection_Error.pdf | Closed 1/3/06 per Selda | bar: 1 to 6
PFR037 SST Interference with EFI | GSE | PROC | SST-ON | Ludlam | [7 empty] | thm_pfr_037_SST_Interference.pdf | Corrected procedure to turn on SST | bar: 1 to 6
PFR038 DFB FPGA MD19 discontinuity | IDPU | DFB | PWB | Nammari | [7 empty] | thm_pfr_038_DFB FPGA MD19 discontinuity.pdf | Jumper added | bar: 1 to 6
PFR039 FGM TMH bit errors | FSW | FGM |  | Bonnell | [7 empty] | thm_pfr_039_FGM_TMH_bit_errors.pdf | closed and filed | bar: 1 to 6
PFR040 DAP variable conversion gain | IDPU | DAP | CAPS | Canario | [7 empty] | thm_PFR_40DAP variable conversion gain.pdf | closed and filed | bar: 1 to 6
PFR041 Spring spool in SCB base hinge loosened by vibration | MAG | SCB | Springspool | Tan | [7 empty] | thm_pfr_041SCB1spring spool lossened.pdf | Tightened Spool | bar: 1 to 6
PFR042 Shorted AC 14 output | IDPU | DCB | Assy | Abiad | [7 empty] | thm_pfr_042 shorted EFI clock.pdf | Remove Solder, Replace Part | bar: 1 to 6
PFR043 Damaged threads in FGB frangibolt ring | MAG | FGB | Frangibolt | Tan | [7 empty] | thm_pfr_043FGB1 damgd thread frangibolt .pdf | Repaired thread, replaced helicoil | bar: 1 to 6
PFR044 Friction increase in hinge mechanism after vibe | MAG | FGB | Base Hinge | Tan | [7 empty] | thm_pfr_044 Friction increase in hinge mech.pdf | Add lubricnat to lower friction Closed 7/19 | bar: 1 to 6
PFR045 ESA Data sequence count non sequential | IDPU | FSW | ETC module | Ingraham | [7 empty] | thm_pfr_045 ESA data sequence count non sequential.pdf | Closed 10/18/05 | bar: 1 to 6
PFR046 ESA Initialization command 6800 not executing | IDPU | FSW | ETC module | Ludlam | [7 empty] | thm_pfr_046_ESA initialisation Command 6A00 not executing.pdf | patch Closed 7/19 | bar: 1 to 6
PFR047 FM2 Low Speed FGM Data Timing Pb | GSE | Software | Decoder | Ludlam | [7 empty] | thm_pfr_047_FM2 low speed FGM data timing pb.pdf | Debugged rate code | bar: 1 to 6
PFR048 DFE low gain at -55 deg C | SST | DFE | Amptek | Canario | [7 empty] | thm_pfr_048_DFE low gain at -55 deg C.pdf | Replace Part, retest | bar: 1 to 6
PFR049 misplaced U49 Bypass capacitor on DFB sn03 | IDPU | DFB | U49 CAP | Cully | [7 empty] | thm_pfr_049 U49 bypass capacitor misplaced on DFB sn03.pdf | Reinstalled cap | bar: 1 to 6
PFR050 SPB S915 Cold TV Door release failure | EFI | SBP | Door | Dalton | [7 empty] | thm_pfr_050 SPB S915 Cold TVAC Door Release Faliure -1.pdf | corrected Assy procedure & inspection | bar: 1 to 6
PFR051 LVPS C70 reversed capacitor | IDPU | LVPS | Assy | Heavner | [7 empty] | thm_pfr_51_LVPS C70 reversed capacitor.pdf | replaced capacitor | bar: 1 to 6
PFR052 Incorrect ADC conversion | SST | IDPU | DAP | Canario | [7 empty] | thm_pfr_52 Incorrect ADC Conversion.pdf | removed the solder bridges | bar: 1 to 6
PFR053 Increased base hinge friction post vib at qual levels | MAG | SCB | Base Hinge | Tan | [7 empty] | thm_pfr_053 Increased base hinge friction post vib.pdf | Closed 7/19 | bar: 1 to 6
PFR054 SST F4 damaged during Mech/Elect Integration | SST | Attenuator | Pivet Shaft | Lee | [7 empty] | thm_pfr_054_SST sensor damaged.pdf | Fasten SST to work surface | bar: 1 to 6
PFR055 IDPU Thermal Spacer Damaged At Installation | IDPU | Thermal | Spacer | Donakowski | [7 empty] | thm_pfr_055_ESA Bushing damage.pdf | Replaced & Caution prior to install bolt | bar: 1 to 6
PFR056 FM1 Post Vibration CPT Power Disruption | Inst Suite | IDPU | Power Supply | Ludlam | [7 empty] | thm_pfr_056_FM1 Post Vibe CPT PWR disruption.pdf | closed 11/7/05 | bar: 1 to 6
PFR057 Misconx ADC Voltage ref on DFB | IDPU | DFB |  | Cully | [7 empty] | thm_pfr_057 misconx ADC volt ref on DFB.pdf | cut trace solder wire all units fixed | bar: 1 to 6
PFR058 SCB connector wire damage | MAG | SCB | Connector | Plauche | [7 empty] | thm_pfr_058 MB SCM Connector Wire Damage.pdf | New pin for FM6 bubble padded bag for FM1-FM5 | bar: 1 to 6
PFR059 cable pull test failure | EFI | CABLE | SPARE | Schickele | [7 empty] | thm_pfr_059 Cable pull test failure.pdf | FM6 is a spare no corrective action | bar: 6
PFR060 FM1 ESA Cover Monitor Readback | Inst Suite | ESA | ESA Harness | Heavner | [7 empty] | thm_pfr_60_FM1 ESA Cover Monitor Readback.pdf | Closed 1/3/06 per Selda | bar: 1 to 6
PFR061 FM1 EFI Y Floating Monitor Temperature Dependance | IDPU | LVPS | EFI Y Monitor | Ludlam | [7 empty] | thm_pfr_061._FM1_EFI_Y_monitor_Temp_Dependance.pdf | Closed 9/7/05 | bar: 1 to 6
PFR062 Inst Suite TV EFI V1 failing Funt'l Tests | Inst Suite | EFI | SPB | Bonnell | [7 empty] | thm_pfr_062 Inst-Suite-TV-EFI-V1-Failing-Functional-Tests.pdf | Closed 7/19 | bar: 1 to 6
PFR063 FM2 ESA SMA Connector wiring problem | ESA | SMA | Wiring | Ludlam | [7 empty] | thm_pfr_063 FM2 ESA SMA Connector Wiring Problem.pdf | Closed 7/19 | bar: 1 to 6
PFR064 Inst Suite TV SST Attenuator MON | Inst Suite | SST |  | Chen | [7 empty] | thm_pfr_064_SST_DIG_HSK.pdf | Closed 8/10 | bar: 1 to 6
PFR065 Bad Data & Missing & Out-of-Order Pckts Obsv'd During Cont. Mode Op | Inst Suite | EFI | FSW | Bonnell | [7 empty] | thm_pfr_065_BadDataAndMissingandOut-of-OrderPacketsDuringContinuousMode Operation.pdf | Closed 10/19/05 | bar: 1 to 6
PFR066 FM1 ESA 459 Pkts not arriving at GSE | Inst Suite | IDPU | GSE | Ludlam | [7 empty] | thm_pfr_066 FM1 ESA 459 pkts not arrvg at GSE.pdf | Closed 7/19 | bar: 1 to 6
PFR067 Temp Dependance in TV on VACT MON | IDPU | PCB | Actuator Monitor | Chen | [7 empty] | thm_pfr_067_temp_dep_ACT.pdf | closed 9/8/05 | bar: 1 to 6
PFR068 SMA Monitor Disturbance by Actuator Current | IDPU | PCB | SMA power | Chen | [7 empty] | thm_pfr_068_SMA monitor disturbance.pdf | Closed | bar: 1 to 6
PFR069 FM1 ESA current Ripple on S/C 28V | Inst Suite | IDPU | LVPS | Heavner | [7 empty] | thm_pfr_069 LVPS_ESA_Current_Ripple.pdf | Closed 7/19 | bar: 1 to 6
PFR070 FM1 GSE Disconnex & IDPU SW Corruption | GSE | NIOS |  | Ludlam | [7 empty] | thm_pfr_070 FM! GSE Discon & IDPU SW corrup.pdf | Closed 8/8/05 | bar: 1 to 6
PFR071 ESA Housekeeping Voltage Output Levels | ESA | ESA INT | HK Resistors | Ludlam | [7 empty] | thm_pfr_071 ESA Voltage output levels.pdf | Closed 5/19/06 | bar: 1 to 6
PFR072 Failed Actuation of FM2 EFI SPB Doors | EFI | SPB | Doors | Bonnell | [7 empty] | thm_pfr_072 Failed Actuation of FM2 EFI SPB Doors.pdf | Closed 11/7/05 | bar: 1 to 6
PFR073 Length Discrepancy between SCM Flight Harnesses | MAG | SCB | Harness | Taylor | [7 empty] | thm_pfr_073_SCM Harness Length Discrepancy.pdf | Closed 7/28 | bar: 1 to 6
PFR074 SST Sensor Channel 2 intermitent failure during Hot Cycle | SST | Sensor | Channel 2 | Canario | [7 empty] | thm_pfr_074 SST lost data at hot temp.pdf | Closed 8/17 un-reproducible failure | bar: 1 to 6
PFR075 ESA HV tripping on PCB during hot TV | IDPU | PCB | 28V CL | Chen | [7 empty] | thm_pfr_075 ESA HV tripping on PCB during hot TV.pdf | Closed 9/16/05 | bar: 1 to 6
PFR076 Reversed Tantalum Capacitors on BEB | IDPU | BEB | Capacitor | Richard | [7 empty] | thm_pfr_076 Reversed TantalumCapacitor on Beb.pdf | Closed 7/19, modified & closed again 8/8/05 | bar: 1 to 6
PFR077 FM1 FGB Fail to deply in Cold Vacum Test | MAG | FGB |  | Plauche | [7 empty] | thm_pfr_077 FM1 FGB fail to deploy in Cold Vac Test.pdf | Closed 7/20 | bar: 1 to 6
PFR078 Cable for FGM Mag Boom is discolored | MAG | CABLE | Insulation | Jackson | [7 empty] | thm_pfr_078_FGM Boom Harness discoloration.pdf | Closed 7/19 | bar: 1 to 6
PFR079 FGB 2 fails cold deployment 6/21/05 | MAG | FGB |  | Plauche | [7 empty] | thm_pfr_079 FM2 FGM fails to deploy in Cold Vacum Test.pdf | Closed 7/20 | bar: 1 to 6
PFR080 FGB 2 fails cold deployment 6/22/06 | MAG | FGB |  | Plauche | [7 empty] | thm_pfr_080 F2 MB falils deply cold vac.pdf | Closed 7/21 | bar: 1 to 6
PFR081 SST FM2 SST SMA Monitor failed | IDPU | DAP | SMA readbk | Chen | [7 empty] | thm_pfr_081 SST SMA monitor failed.pdf | Closed 7/19 | bar: 1 to 6
PFR082 SPB S918 Post Vibe Test PA Failure | EFI | SPB | PreAmp | Bonnell | [7 empty] | thm_pfr_082_SPB S918 Post-Vibe Test PA Failure.pdf | Closed 9/15/05 | bar: 1 to 6
PFR083 SCM X Axis Amplitude Discrepancy | SCM | DFB |  | Richard | [7 empty] | thm_pfr_083 SCM X Axis Amplitude Discrepancy.pdf | closed 8/8/05 | bar: 1 to 6
PFR084 ESA cover release mechanism nut plate design flaw | ESA | Rel Plate Assy | Micro-switch nut plate | Carlson | [7 empty] | thm_pfr_084 ESA cover rls mech nut plate dsgn flaw.pdf | Closed 7/19 | bar: 1 to 6
PFR085 AKR Band Noise Floor Exceeds Specification | IDPU | DFB/LVPS | HF Filter | Heavner | [7 empty] | thm_pfr_085 AKR Band Noise Floor Exceeds Specification.pdf | Closed 1/9/05 | bar: 1 to 6
PFR086 Incorrect Deployment Angles in FGM Design | MAG | FGB |  | Plauche | [7 empty] | thm_pfr_086 FGM Incorrect Deployment Angles in FGM Design.pdf | Closed 7/28 | bar: 1 to 6
PFR087 FM6 PCB Actel Installed on ETC | IDPU | ETC | Actel | Ludlam | [7 empty] | thm_pfr_087_FM6 PCB Actel instald on ETC Board.pdf | Closed 10/5/05 | bar: 1 to 6
PFR088 IDPU Conductive Shields Mech'l Problem | IDPU | DAP/BEB |  | Donakowski | [7 empty] | thm_pfr_088 IDPU Mech fouling issue.pdf | Closed 11/10/05 | bar: 1 to 6
PFR089 PCB 10V line drawing more current than normal | IDPU | PCB/FGE | op Amp | Chen | [7 empty] | thm_pfr_089_PCB_P10_current.pdf | closed 8/8/05 | bar: 1 to 6
PFR090 Blackout circuit to eliminate peak current (sun pulse issue) | SST | Sensor | SEA | Larson | [7 empty] | thm_pfr_090 SST sun pulse causes high current draw on supply voltages.pdf | closed 2/6/06 per Davin | bar: 1 to 6
PFR091 Non regulated bias supply voltage during sun pulse | IDPU | DAP | Bias supply | Larson | [7 empty] | thm_pfr_091 SST non-regulated bias supply voltage during sun pulse.pdf | closed 11/7/05 | bar: 1 to 6
PFR092 ESA Screw caused mechanical damage to LVPS | IDPU | LVPS | Resistor | Taylor | [7 empty] | thm_pfr_092_High Current on EFI Turn-On.pdf | closed 9/15/05 | bar: 1 to 6
PFR093 DFB Face Plate Mechanical Damage | IPDU | DFB | Face Plate | Turin | [7 empty] | thm_pfr_093_DFB Face Plate Mechanical Damage.pdf | Closed 9/15/05 | bar: 1 to 6
PFR094 SST Attenuator Monitor reads invalid at hot | IDPU | DAP | Diode | Taylor | [7 empty] | thm_pfr_094_SST Attenuator Monitor Invalid.pdf | Closed 10/3/05 | bar: 1 to 6
PFR095 Thermal Radiator Tape Adhesive Failure in TV | Inst Suite | Radiator Tape |  | Smith | [7 empty] | thm_pfr_095_thermal_radiator_tape_adhesive_failuret.pdf | Closed 11/15/05 | bar: 1 to 6
PFR096 EFI Y Imon unstable | Inst Suite | SPB/PreAmp |  | Bonnell | [7 empty] | thm_pfr_096 EFI Y Current Monitor Unstable.pdf | Closed 2/13/06 per J. Bonnell | bar: 1 to 6
PFR097 SST Heater Noise | Inst Suite | SST | Heater | Ludlam | [7 empty] | thm_pfr_097_SST_Heater_Noise.pdf | Closed 10/21/05 and again 5/26/06 | bar: 1 to 6
PFR098 SPB s/n 923 dropped during assembly | EFI | SPB | structure | Dalton | [7 empty] | thm_pfr_098 SPB S923 dropped.pdf | Closed 10/3/05 Unit fixed | bar: 1 to 6
PFR099 FM3 IDPU Reset during SST Debugging | IDPU | DCB | FSW | Ludlam | [7 empty] | thm_pfr_099_FM3_IDPU_Reset_During_SST_Debugging.pdf | Closed 10/25/05 | bar: 1 to 6
PFR100 FM5 DCB Dropped | IDPU | DCB |  | Chen | [7 empty] | thm_pfr_100_F5_DCB_Dropped.pdf | Closed 10/17/05 | bar: 1 to 6
PFR101 SST SMA damaged | SST | SMA |  | Larson | [7 empty] | thm_pfr_101-SST_SMA_damage.pdf | Closed 2/6/06 per Davin | bar: 1 to 6
PFR102 FGM Harness too short | MAG | FGB | Harness | Turin | [7 empty] | thm_pfr_102 FGS Harness Length Too Short.pdf | Closed 10/31/05 | bar: 1 to 6
PFR103 Cracked SPB Retainer Tube | EFI | SPB | Retainer Tube | Donakowski | [7 empty] | thm_pfr_103 CRACKED SPB RETAINER.pdf | Closed 11/8/05 | bar: 1 to 6
PFR104 FM2 IDPU Backplane Damaged (fixed just need paperwork) | IDPU | Backplane |  | Chen | [7 empty] | thm_pfr_104_F2_Backplane_Damaged.pdf | Closed 10/17/05 | bar: 1 to 6
PFR105 FM4 Turns Counter Switch Failure | SPB | Turns Counter | Actuator | Dalton | [7 empty] | thm_pfr_105 SPB Turns counter failure.pdf | Closed 11/7/05 | bar: 1 to 6
PFR106 FM1 ESA Recal showed noisy channel | ESA |  |  | McFadden | [7 empty] | thm_pfr_106_ESA_FM1_Noisy.pdf | Closed by CWC 2/21/06 | bar: 1 to 6
PFR107 FM3 SEA s/n16-21 dropped | SST | SEA |  | Scholz | [7 empty] | thm_pfr_107_FM3 SEA dropped.pdf | Closed 10/17/05 | bar: 1 to 6
PFR108 ETC E PROM Table not loading correctly | IDPU | DCB | EPROM | Taylor | [7 empty] | thm_pfr_108_FM2 ETC EEPROM Table not loading correctly.pdf | Closed 10/21/05 | bar: 1 to 6
PFR109 FM2 Burst Data Counter anomalously reported | IDPU | DCB | FSW | Chen | [7 empty] | thm_pfr_109_burst_memory_full.pdf | Closed 11/14/05 | bar: 1 to 6
PFR110 FM3 DCB reset during TV | IDPU | DCB |  | Chen | [7 empty] | thm_pfr_110_FM3_TV_reset.pdf | Closed 11/14/05 | bar: 1 to 6
PFR111 Accidental Connection of FM3 MAG Boom Actuator | IDPU | PCB | Actuator supply switches | Ludlam | [7 empty] | thm_pfr_111_mag_actutator.pdf | Closed 10/21/05 | bar: 1 to 6
PFR112 ESA HV Script Problem | GSE | Scripts | ESA Scripts | Ludlam | [7 empty] | thm_pfr_112_ESA_HV_Script_Problem.pdf | Closed 10/21/05 | bar: 1 to 6
PFR113 FM3 IDPU Reset during AC continuous mode | IDPU | DCB | FSW | Taylor | [7 empty] | thm_pfr_113_FM3 IDPU Reset during EFI AC Continuous Mode.pdf | Closed 11/14/05 | bar: 1 to 6
PFR114 FM2 Current Monitor Temperature Dependency found in TV | IDPU | PCB | P10 IMon | Chen | [7 empty] | thm_pfr_114_FM2_IMON_P10_DRIFT.pdf | Closed 11/09/05 | bar: 1 to 6
PFR 115 FM3 EFI V1 Failing AC Functional Test in TVAC | EFI | SPB | Sphere | Bonnell | [7 empty] | thm_pfr_115_FM3_EFI_V1_Failing_AC_Functional_Test_in_TVAC.pdf | Closed 1/19/06 per J. Bonnell | bar: 1 to 6
PFR116 ESA not correctly initialized | ESA | FSW |  | Ludlam | [7 empty] | thm_pfr_116 ESA not correctly initialized.pdf | Closed 11/10/05 | bar: 1 to 6
PFR117 DAP Power Plane short to front plate | IDPU | DAP | DAP Board | Ludlam | [7 empty] | thm_pfr_117_DAP_Power_Plane_short_to_front_plate.pdf | Closed 8/21/06 | bar: 1 to 6
PFR 118 ESC grounding issue with SPB closeout blanket | EFI | SPB | SPB Blanket | Bonnell | X PRB0198 | [6 empty] | thm_pfr_118_ESC grounding issue with SPB closeout blanket.pdf | Closed 1/17/06 per P.Turin | bar: 1 to 6
PFR 119 BAU IDPU current draw readback incorrect | ETU BAU | PCM | Itos conversion | Taylor | X PRB0157 | C | L | O | S | E | D | thm_pfr_119_BAU IDPU current draw readback incorrect.pdf | Closed 3/3/06 GSE issue doesn't apply to any unit in particular.
PFR 120 P2 Propellant Pressure decreased during shipment | RCS | Pressure Valve |  | Taylor | X PRB0156 | [6 empty] | thm_pfr_120_Propellant Pressure decreased during shipment.pdf | Closed 1/17/06 per P.Turin | bar: 1 to 6
PFR 121 Additional current draw with IDPU enabling plug in | IDPU | Harness | Enabling Plug | Taylor | X PRB 0097 | [6 empty] | thm_pfr_121_Additional current draw with IDPU enabling plug.pdf | Opened 12/5/05 GSE issue doesn't apply to any unit in particular. | bar: 1 to 6
PFR 122 Sensor 11 Attenuator Closing Anomaly | SST | Sensor | Attenuator | Larson | [7 empty] | thm_pfr_122_SST_microswitch_failure.pdf | Closed 2/9/06 | bar: 1 to 6
PFR 123 Data Link Lost during IDPU Integration | BAU | DPM | FSW | Taylor | X PRB0180 | [6 empty] | thm_pfr_123_Data drop out during IDPU Integration.pdf | Closed 3/3/06 | bar: 1 to 6
PFR124 Shorting of SPB Motor Bypass Diode to Chassis | EFI | SPB | Motor | Bonnell | [7 empty] | thm_pfr_124_ShortingOfSPBMotorBypassDiodeToChassis.pdf | Closed 1/9/06 | bar: 1 to 6
PFR 125 Commands failed during Instrument LPT | BAU | DPM | FSW | Taylor | X PRB0181 | [6 empty] | thm_pfr_125_Command failure during IDPU LPT.pdf | Closed 3/3/06 | bar: 1 to 6
PFR 126 Mag Mounting Flatness | MAG | Mount |  | Turin | X PRB0182 | [6 empty] | thm_pfr_126 Magnetometer Mount Flatness.pdf | Closed 1/17/06 per P.Turin | bar: 1 to 6
PFR 127 IDPU reset during SCT | IDPU | DCB |  | Taylor | [7 empty] | thm_pfr_127_IDPU Reset during Probe SCT.pdf | Closed 3/16/06 | bar: 1 to 6
PFR 128 Antenna Cable Routing interferes with Mag Boom Install (Coax) | Antenna | Harness |  | Turin | [7 empty] | thm_pfr_128 Antenna Coax Interferes with FGB.pdf | Closed 1/17/06 per P.Turin | bar: 1 to 6
PFR 129 SC Clock Jitter | BAU | DPM | FSW | Harvey | X PRB0185 | [6 empty] | thm_pfr_129_SC CLOCKJITTER.pdf | Closed 3/3/06 | bar: 1 to 6
PFR 130 BAU corrupted command | BAU | DPM |  | Roberts | [7 empty] | thm_pfr_130_BAU corrupting IDPU command.pdf | Closed 3/15/06 | bar: 1 to 6
PFR 131 IDPU rejecting all commands | IDPU | DCB |  | Chen | [7 empty] | thm_pfr_131_IDPU rejecting all commands.pdf | Closed 2/6/06 per Corinna | bar: 1 to 6
PFR 132 IDPU Simulator Low Rate Data Anomaly | GSE | IDPU | SIM | Taylor | X ITS326 | C | L | O | S | E | D | thm_pfr_132_IDPU Simulator Low Rate Telemetry Issue.pdf | Closed 3/15/06
PFR 133 ITOS Corrupting Retry Commands | GSE | ITOS |  | Taylor | X PRB0199 | C | L | O | S | E | D | thm_pfr_133_ITOS corrupting retry cmmands.pdf | Closed 3/3/06
PFR 134 Unable to process long uplink commands | BAU | DPM | FSW | Taylor | X PRB0200 | [6 empty] | thm_pfr_134_Unable to process long uplink commands-1.pdf | Closed 3/3/06 | bar: 1 to 6
PFR 135 IDPU DCB 5V Supply too low on DCB during SST turn-on | IDPU | DCB | 5VD Supply | Ludlam | [7 empty] | thm_pfr_135_SST_Power_On_5VD.pdf | Closed 2/9/06 | bar: 1 to 6
PFR 136 PCB Temp Dependence of Actuator Monitor | IDPU | PCB | OpAmp | Chen | [7 empty] | thm_pfr_136_FM5_VMON_ACT_DRIFT.pdf | Closed 1/27/06 | bar: 1 to 6
PFR 137 Transponder Command Dropped due to Command Collision | BAU | DPM | FSW | Taylor | X PRB0201 | [6 empty] | thm_pfr_137_Transponder command dropped due to command collision.pdf | Closed 3/3/06 | bar: 1 to 6
PFR 138 FM2 ESA LVPS Screws fell out during workmanship vibe | ESA | LVPS | Screws | Ludlam | [7 empty] | thm_pfr_138_FM2_ESA_Vibration_Screws_Loose.pdf | Closed by CWC 2/21/06 | bar: 1 to 6
PFR 139 ESA top hat nut plate interference | ESA | Top Hat | Nut Plate | Carlson | [7 empty] | thm_pfr_139_139_ESA topcap retraction.pdf | Closed 2/10/06 | bar: 1 to 6
PFR 140 Transponder not isolated | Transponder | Mounting Washer |  | Taylor | X PRB0214 | [6 empty] | thm_pfr_140_Transponder not isolated-2.pdf | Closed 3/1/06 | bar: 1 to 6
PFR 141 LVPS ESA Supply oscillation at cold Temperature | IDPU | LVPS | ESA supply | Ludlam/Berg | [7 empty] | thm_pfr_141_LVPS_ESA_Oscillation.pdf | Closed 3/28/06 | bar: 1 to 6
PFR 142 Antenna Cables required Cleaning | COMM | Antenna | Cable | Taylor | X PRB0217 | [6 empty] | thm_pfr_142_Antenna Cables Cleaning-1.pdf | Closed 3/15/06 | bar: 1 to 6
PFR 143 AEB Faulty Fuse Plugs | AEB | Connector |  | Taylor | X PRB0145 | [6 empty] | thm_pfr_143_AEB Fuse Plug-1.pdf | Closed 3/15/06 | bar: 1 to 6
PFR 144 IDPU Temp Sensors Conversion Incorrect | ETU IDPU | Temp Sensor | Itos conversion | Taylor | X PRB0224 | C | L | O | S | E | D | thm_pfr_144a_IDPU Temp Sensors Conversion Incorrect.pdf | Closed 3/3/06
PFR 145 IRU Data Inconsistent over Temp and Voltage | IRU |  |  | Taylor | X PRB0105 | [6 empty] | thm_pfr_145_IRU data inconsistent over temp and voltage.pdf | Closed 2/27/06 | bar: 1 to 6
PFR 146 SN101 BAU Showed large Magnetic Moments | BAU | Magnetics |  | Taylor | [7 empty] | thm_pfr_146_BAU found to have large magnetic moment.pdf | Closed 3/14/06 | bar: 1 to 6
PFR 147 SN101 BAU Reset during IDPU safe to mate | BAU |  |  | Stu Harris | [7 empty] | thm_pfr_147_BAU reset during IDPU Safe-to-Mate-1.pdf | Closed 3/15/06 | bar: 1 to 6
PFR 148 Code Block Errors seen during ACS Testing | BAU | FSW |  | Mark Lewis | X | [6 empty] | thm_pfr_148_Code Block Errors.pdf | Closed 5/5/06 | bar: 1 to 6
PFR 149 Separation System Screw Length | Sep | Spring | Screw | Turin | X | [6 empty] | thm_pfr_149 Separation System Screw Length.pdf | Closed 5/5/06 | bar: 1 to 6
PFR 150 Sun Sensor Baffle Chipping | ACS | MSSS | Baffles | Turin | X PRB0255 | [6 empty] | thm_pfr_150_Sun Sensor Baffle Chipping.pdf | Closed 3/17/06 P.Turin | bar: 1 to 6
PFR 151 Probe Lifting Outrigger Interference | GSE |  |  | Turin |  | C | L | O | S | E | D | thm_pfr_151 Probe Lifting Outrigger Interference.pdf | Closed per P.Turin 3/16/07
PFR 152 Incorrect APIDs in Probe Fill Packets | BAU | FSW |  | Taylor | X | [6 empty] | thm_pfr_152_Invalid APIDs in Probe Fill Packets.pdf | Closed 5/16/06 per Ellen | bar: 1 to 6
PFR 153 Receiver and RF Rack not working | EGSE | RF Rack |  | Harris | X | C | L | O | S | E | D | thm_pfr_153_receiver in RF Rack not working.pdf | Closed 5/5/06
PFR 154 Warm reset causes cold restart on DPC | BAU | FSW |  | Taylor | X PRB0248 | [6 empty] | thm_pfr_154_Warm reset causes cold restart on DPC.pdf | Closed 5/16/06 per Ellen | bar: 1 to 6
PFR 155 Commands after warm reset are locked out | BAU | FSW |  | Taylor | X | [6 empty] | thm_pfr_155_Commands after warm reset are locked out.pdf | Closed 5/16/06 per Ellen | bar: 1 to 6
PFR 156 ACS and Test connectors - replace screws | Probe | ACS Cover |  | Turin | X | [6 empty] | thm_pfr_156 ACS Test Connector Cover Clips.pdf | Closed 6/21/06 | bar: 1 to 6
PFR 157 IDPU LVPS FM4 Thermistor Shorted | IDPU | LVPS | Thermistor | Ludlam | [7 empty] | thm_pfr_157_FM4_LVPS_Thermistor_Shorted.pdf | Closed 3/27/06 | bar: 1 to 6
PFR 158 DCB Bent J301 Pin | IDPU | DCB | J301 Connector | Ludlam | [7 empty] | thm_PFR_158_DCB_Bent_J301_Pin.pdf | Closed 3/27/06 | bar: 1 to 6
PFR 159 FM3 ESA One Anode Not Counting | ESA | Ion Sensor | Anode | Ludlam | [7 empty] | thm_pfr_159_FM3_ESA_One_Anode_Not_Counting.pdf | Closed 3/27/06 | bar: 1 to 6
PFR 160 BAU connector sockets damaged. | BAU | Connector |  | Taylor | X PRB270 | [6 empty] | thm_pfr_160_BAU connector sockets damaged.pdf | Closed 6/13/06 | bar: 1 to 6
PFR 161 Intermittent receiver lock during vibration | Comm | Receiver |  | Taylor | [7 empty] | thm_pfr_161_Intermittent receiver lock during F2 vibration test.pdf | Closed 5/16/06 per Ellen | bar: 1 to 6
PFR 162 MSSS tape not grounded | MSSS | Tape |  | Bonnell | X PRB283 | [6 empty] | thm_pfr_162_MSSS_tape_not_grounded.pdf | Closed 9/25/06 | bar: 1 to 6
PFR 163 FM6 DAP dropped | DAP |  |  | Ludlam | [7 empty] | thm_pfr_163_FM6_DAP_Dropped.pdf | Closed 4/14/06 | bar: 1 to 6
PFR 164 IDPU Current Oscillation during Probe 2 TV Cold Balance #1 | IDPU | LVPS | ESA Supply | Ludlam | [7 empty] | thm_pfr_164_LVPS_ESA_Supply_Oscillation.pdf | Closed 5/9/06 | bar: 1 to 6
PFR 165 Solar Array Diode Board Conformal Coating |  |  |  | Taylor | X PRB ? | [6 empty] | thm_pfr_165_Solar Array Diode Board Conformal Coating-2.pdf | Clsoed 6/15/06 | bar: 1 to 6
PFR 166 Commanding acq sequence support fails in ITOS 703p1-5 | EGSE | ITOS |  | Roberts | X ITS432 | C | L | O | S | E | D | thm_pfr_166 Commanding acq sequence support fails in ITOS.pdf | Closed 6/20/06
PFR 167 Repeated command destination port closings in ITOS 703p1-5 | EGSE | ITOS |  | Roberts | X ITS433 | C | L | O | S | E | D | PFR_167 repeated command dest port closings.pdf | Closed 6/22/06
PFR 168 BAU Reset During TV4 due to Heaters | BAU | Heaters |  | Chen | [7 empty] | thm_pfr_168_BAU_reset_TV_cold4_heaters.pdf | Closed 4/26/06 | bar: 1 to 6
PFR 169 Plasma Discharge Damage to Ion Detectors | SST | Sensor | Detector | Larson | [7 empty] | thm_pfr_169_Plasma Discharge Damage to Ion Detectors.pdf | Closed 5/3/06 | bar: 1 to 6
PFR 170 ITOS crash when using ‘sim chg’ operator | EGSE | ITOS |  | Roberts | X ITS434 | C | L | O | S | E | D | thm_pfr_170.pdf | Closed 6/22/06
PFR 171 Mag Boom Frangibolts overheated during Tvac Pop-and-Catch | Mag Boom | Frangibolt |  | Turin | [7 empty] | thm_pfr_171_Mag Boom Frangibolts overheated during Tvac Pop-and-Catch.pdf | Closed 5/22/06 | bar: 1 to 6
PFR 172 K1 Battery relay changed state during EGSE Rack #2 check-out | EGSE | Rack |  | Taylor | [7 empty] | thm_pfr_172_K1 Battery relay changed state during EGSE Rack#2 Check-out.pdf | Closed 5/15/06 per Ellen | bar: 1 to 6
PFR 173 F2 Transponder needs resistor chg and diplexer rework |  |  |  | Taylor | X PRB280 | [6 empty] | thm_pfr_173_F2 Transponder needs resistor change and diplexor re-test.pdf | Closed 6/15/06 | bar: 1 to 6
PFR 174 F4 Transponder needs resistor change |  |  |  | Taylor | X PRB280 | [6 empty] | thm_pfr_174_F4 Transponder needs resistor change.pdf | Closed 6/15/06 | bar: 1 to 6
PFR 175 F4 Antenna Hat Coupler AL409 possible detuning following rework | [11 empty] | thm_pfr_175_Antenna Hat Coupler AL409 _F4_ possibly detuned after rework-1.pdf | bar: 1 to 6
PFR 176 F3 Antenna Hat Coupler AL409 possible detuning following rework | [11 empty] | thm_pfr_176_Antenna Hat Coupler AL408 _F3_ possibly detuned after rework.pdf | Closed 5/16/06 per Ellen | bar: 1 to 6
PFR 177 Unexpected Turn Off of Pressure Transducer | P4 | BAU EDU #2 | FSW 3100 | Harris | [7 empty] | thm_pfr_177_UnexpectedDucerTurnOff.pdf | Closed 5/15/06 | bar: 1 to 6
PFR 178 VC1 Data Packets missing 4 byte CLCW | FSW |  |  | Taylor | [7 empty] | thm_pfr_178_VC1 data packets missing 4 byte CLCW.pdf | Closed 6/15/06 | bar: 1 to 6
PFR 179 4dB Discrepancy on Probe 4 | Comm |  |  | Taylor | X | [6 empty] | thm_pfr_179_-4dB Discrepancy on Probe 4-1.pdf | Closed 6/19/06 | bar: 1 to 6
PFR 180 FM2 Battery Permed Up |  |  |  | Ludlam | X | [6 empty] | thm_pfr_180_FM2 Battery Permed Up.pdf | Closed 5/24/06 | bar: 1 to 6
PFR 181 F3 EFI SPB IMONs Unstable |  |  |  | Bonnell | [7 empty] | thm_pfr_181_F3 EFI SPB IMONs Unstable.pdf | Reopened 10/30/06 | bar: 3 to 6
PFR 182 P3 Thruster/Rollover Cart Interference | T1 ThrusterSensor |  | Detector | Dalton | [7 empty] | thm_pfr_182 Thruster Rollover Inter.pdf | Closed 6/19/06 | bar: 1 to 6
PFR 183 F3 AXB V6 DC Functional Test Anomaly |  |  |  | Bonnell | [7 empty] | thm_pfr_183_F3 AXB V6 DC Functional Test Anomaly_revA-1.pdf | Closed 9/25/06 | bar: 1 to 6
PFR 184 DAP Table Failed to write to EEPROM | EGSE | ITOS | Proc | Harvey |  | C | L | O | S | E | D | thm_pfr_184_DAP_TABLE.pdf | Closed 5/24/06
PFR 185 SCM Harness not shielded sufficiently | SCM | Harness | Shield | Taylor | [7 empty] | thm_pfr_185_SCM harness not shielded sufficiently.pdf | Closed 8/14/06 | bar: 1 to 6
PFR 186 F2 Velcro adhesive bond to thermal paint failure | Probe | Thermal Blanket | Tank Insert | Smith | [7 empty] | thm_pfr_186_thermal blanket Velcro adhesion failure.pdf | Closed 6/9/06 | bar: 1 to 6
PFR 187 F3 ESA SMA Actuator secondary failure | ESA | SMA B | Release Plate | Elliott | [7 empty] | thm_pfr_187 ESA SMA Failure.pdf | Closed 6/1/06 | bar: 1 to 6
PFR 188 ATS Tables with SUNSYNC Commands Fail to Commit | FSW |  |  | Roberts | X | C | L | O | S | E | D | thm_pfr_188 ATS Tables.pdf | Closed 6/13/06
PFR 189 Error in SUNSYNC Command PWIDTH Validation | FSW |  |  | Roberts | X | C | L | O | S | E | D | thm_pfr_189_Error in SUNSYNC.pdf | Closed 6/13/06
PFR 190 RCS Service Valve Isolator Installation Differences | RCS | Service Valves |  | Turin | [7 empty] | thm_pfr_190 RCS Service Valve Isolator Installation Differences.pdf | Closed 6/8/06 | bar: 1 to 6
PFR 191 Release Plate Mechanism Fired during Vibe Test | ESA | Release Plate |  | Elliott | [7 empty] | thm_pfr_191 Release Plate Fired Uncommanded.pdf | Closed 6/14/06 | bar: 1 to 6
PFR 192 FM1 SST elevated noise levels on electron sensors when integrated on probe | Instruments | SST | electron sensor | Ludlam | [7 empty] | thm_pfr_192_SST_F1_Noise_on_Probe.pdf | Closed 8/21/06 | bar: 1 to 6
PFR 193 Reed-Solomon Errors at 32-64kbps Data Rate | GSE |  |  | Taylor |  | C | L | O | S | E | D | thm_pfr_193_Reed-Solomon Errors at 32-64 kbps.pdf | Closed 8/14/06
PFR 194 Tin Lug replaced on F1 Transponder | Comm | Transponder | Lug | Taylor | [7 empty] | thm_pfr_194_Tin Lug replaced on F1 Transponder.pdf | Closed 6/19/06 | bar: 1 to 6
PFR 195 ESA SN3 Redundant Cover Firing Failure | ESA sn3 | Firing mechanism | redundant side | Ludlam | [7 empty] | thm_pfr_195_ESA SMA B Firing Failure.pdf | Closed 6/19/06 | bar: 1 to 6
PFR 196 FM3 SCM, wrong unit installed onto spacecraft. | InstrumentsSCM |  | SCM PA | Ludlam | [7 empty] | thm_pfr_196_FM3_SCM_wrong_preamp_installed.pdf | Closed 6/22/06 | bar: 1 to 6
PFR 197: Microdyne Receiver (PSK Modulator) on RF EGSE Rack #1 not working | EGSE | RF Rack 1 | Microdyne | Taylor |  | C | L | O | S | E | D | thm_pfr_197_Microdyne Receiver _PSK Modulator_ on RF EGSE ..pdf | Closed 8/14/06
PFR 198: EGSE Rack #4 Software logic flipped for Uplink Attenuation | EGSE | RF Rack 2 |  | Taylor |  | C | L | O | S | E | D | thm_pfr_198_EGSE Rack #4 Software logic flipped.pdf | Clsoed 8/22/06
PFR 199: Receiver Signal Strength decreased significantly during F5 CPT RF Test | EGSE | RF Rack 2 |  | Taylor |  | C | L | O | S | E | D | thm_pfr_199_Receiver Signal Strength decreased significant..pdf | Opened 6/23/06
PFR 200 Flair Saver dropped in F5 | Probe 5 | RCS Testing GSEGSE Flair Saver |  | Donakowski | [7 empty] | thm_pfr_200_flair saver dropped in F5.pdf | Closed 7/11/06 | bar: 1 to 6
PFR201 Errors in VC4 thrust history telemetry | FSW v3.160 |  |  | Roberts | X | C | L | O | S | E | D | thm_pfr_201_error in VC4 thrust.pdf | Closed 8/22/06
PFR 202 Errors in FSW 3160 RTS's | FSW v3.161 |  |  | Roberts | X | C | L | O | S | E | D | thm_pfr_202_errors in FSW 3160 RTS.pdf | Closed 8/22/06
PFR 203 FM1 noise problems seen during pre-ship CPT | Instruments | FGM | FGS | Ludlam | [7 empty] | thm_pfr_203_FM1_FGM_Noise_Preship_CPT-1.pdf | Closed 8/15/06 | bar: 1 to 6
PFR 204 FM3 noise problems seen during pre-ship CPT | Instruments | FGM | FGS | Ludlam | [7 empty] | thm_pfr_204_FM3_FGM_Noise_Preship_CPT-1.pdf | Closed 9/29/06 | bar: 1 to 6
PFR 205 F2 RCS thermostat closes below specification (<3 degrees) | Thermal | Thermostat |  | Taylor | [7 empty] | thm_pfr_205_F2_RCS_Line1_TSTAT.pdf | Closed 10/19/06 | bar: 1 to 6
PFR 206 F4 AXB temperature sensor reading anomolous (1052C) | EFI | AXB | Temp Sensor | Bonnell | [7 empty] | thm_pfr_206_F4 AXB temperature sensor reading anomolous _1052C_.pdf | Reopened 10/30/06 | bar: 1 to 6
PFR 207 F4 EFI +/-X cables swapped during TV Installation | EFI | Cables |  | Taylor | [7 empty] | thm_pfr_207_F4 EFI SPB Cable swapped during TV installatio..pdf | Closed 8/22/06 | bar: 1 to 6
PFR 208 F5 SCM Sensor connected during Magnetics Test Deguass | Magnetics | SCM Pre-Amp |  | Ludlam | [7 empty] | thm_pfr_208_SCM Sensor connected during degauss.pdf | Closed 9/25/06 | bar: 1 to 6
PFR 209 Spin Balance mass greater than expected | Structure | Balance Mass |  | Turin | [7 empty] | thm_pfr_209 Spin Balance Mass Greater Than Expected.pdf | Closed 8/23/06 | bar: 1 to 6
PFR 210 First Pulse of Sun Synch Manuevers not executed during TV ACS CPT | FSW |  |  | Lewis |  | C | L | O | S | E | D | thm_pfr_210.pdf | Closed 10/17/06
PFR 211 Bit 3 of MSSS greycode stuck high during last cycles of F3/4 TV Test | EGSE | VSat |  | Taylor |  | C | L | O | S | E | D | thm_pfr_211_Bit 3 of MSSS greycode stuck high during TV.pdf | Closed 10/2/06
PFR 212 ESA Radiation source not installed correctly for F3/4 TV Test | GSE | Radiation Source |  | Taylor |  | C | L | O | S | E | D | thm_pfr_212_ESA Radiation source not installed correctly f..pdf | Closed 8/22/06
PFR 213 ESA APID 459 data all zeros (most likely ETC Table Load problem) | FSW | ETC Tables |  | Taylor |  | C | L | O | S | E | D | thm_pfr_213_ESA APID 459 data all zeros.pdf | Closed 8/22/06
PFR 214 Full scale readback (FF) of ESA MCP Voltage at nominal setting | ESA | Analog |  | Ludlam |  | C | L | O | S | E | D | thm_pfr_214_Full scale readback of ESA MCP voltage at..pdf | Closed 8/22/06
PFR 215 F3 TV Test - transponder primary and secondary heater services swapped | Thermal | Heaters |  | Smith | [7 empty] | thm_pfr_215_F3_Primary_Secondary_XPNDR.pdf | Closed 9/28/06 | bar: 1 to 6
PFR 216 Probe 5 ETC Rev 5 Table did not load correctly | IDPU | ETC |  | Ludlam | [7 empty] | thm_pfr_216_Probe5_ETC_Tables-1.pdf | Closed 8/15/06 | bar: 1 to 6
PFR 217 Probe 5 SCM Filter values lower than typical during Cal Signal Test | SCM | Filter Bank |  | Ludlam | [7 empty] | thm_pfr_217_SCM Cal signal lower than expected.pdf | Close 9/25/06 | bar: 1 to 6
PFR 218 Burst memory readback not correct after transition to slow survey | IDPU | DCB | FSW | Harvey | [7 empty] | thm_pfr_218_Burst_Packet_Count.pdf | Closed 9/28/06 | bar: 1 to 6
PFR 219 SST counters get cleared every 24 seconds | IDPU | DCB | FSW | Harvey | [7 empty] | thm_pfr_219_SST_Engineering-1.pdf | Closed 9/28/06 | bar: 1 to 6
PFR 220 Probe 5 ESA Energy Table not written correctly during TVAC | ESA |  |  | Ludlam | [7 empty] | thm_pfr_220_One instance of Probe 5 ESA Energy Table not w..pdf | Closed 10/13/06 | bar: 1 to 6
PFR 221 Piece of mirror found in Probe 1 | QA |  |  | Dalton | [7 empty] | thm_pfr_221 Mirror Piece In F1.pdf | Closed 8/23/06 | bar: 1 to 6
PFR 222 Overhead crane breakdown at JPL building 179 TVAC area | GSE | Crane |  | Donakowski |  | C | L | O | S | E | D | thm_pfr_222 crane non-functioning.pdf | Closed 8/22/06
PFR 223 RCS Inhibit Status incorrect | EGSE | Monitor |  | Harris |  | C | L | O | S | E | D | thm_pfr_223_RCS_Inhibit_Status.pdf | Closed 9/19/06
PFR 224 SCM MagBoom did not deploy during post Env. CPT | MagBoom | SCM | Harness | Taylor | [7 empty] | thm_pfr_224_SCM MagBoom did not deploy.pdf | Closed 8/22/06 | bar: 1 to 6
PFR 225 P3 Sun Sensor Primary and Secondary service switched | Thermal |  |  | Smith | [7 empty] | thm_pfr_225_P3_Sunsensor_Heater_Service.pdf | Closed 9/28/06 | bar: 1 to 6
PFR 226 P1 BTMPRCSLN1 and BTMPRCSSVC mnemonics swapped | Thermal |  |  | Smith | [7 empty] | thm_pfr_226_P1_TMP_Mnemonic_Switch.pdf | Closed 9/28/06 | bar: 1 to 6
PFR 227 SCM saturation at -3.3V instead of -5V | SCM |  |  | Ludlam | [7 empty] | thm_pfr_227_SCM_Yaxis_saturation_problem.pdf | Closed 10/16/06 | bar: 1 to 6
PFR 228 F4 FGM Harness shorted to Boom | Instrument | FGM | Harness | Ludlam | [7 empty] | thm_pfr_228_F4_FGM_Harness_Problem.pdf | Closed 10/23/06 | bar: 1 to 6
PFR 229 Memory Checksum Errors during Maneuv Sims | BAU | FSW |  | Taylor |  | C | L | O | S | E | D | thm_pfr_229a_Memory Check Sum Errors.pdf | Closed 12/4/06
PFR 230 Thruster 20Hz Counter not accurate | BAU |  |  | Taylor |  | C | L | O | S | E | D | thm_pfr_230_Thruster 20Hz Counter not accurate.pdf | Closed 10/16/06
PFR 231 Command Uplink Timer Inaccurate | BAU | FSW | Counter | Taylor | [7 empty] | thm_pfr_231_Command uplink timer inaccurate.pdf | Closed 10/23/06 | bar: 1 to 6
PFR 232 AXB Contamination |  |  |  | McCauley | [7 empty] | thm_pfr_232_AXB_Contamination.pdf | Closed 11/16/06 | bar: 1 to 6
PFR 233 IDPU Sep Loop Wiring Exhibits Open Circuit | Harness | Umbi | Prob Extenstion | Harris | [7 empty] | thm_pfr_233_IDPUSepLoopWiring.pdf | Closed 12/16/06 | bar: 1 to 6
PFR 234 EGSE Power Supply Blown Fuse | EGSE | Umbi Rack #3 | Agilent 6633B | Harris |  | C | L | O | S | E | D | thm_pfr_234_EGSEBlownFuse.pdf | Closed 12/27/06
PFR 235 F2 Servics Valves SV2 & SV3 lost torque | RCS | Valves | SV2 & SV3 | Sholl | [7 empty] | thm_pfr_235 F2 Service Valves SV2 & SV3 lost torque.pdf | Closed 12/27/06 | bar: 1 to 6
PFR 236 Thermal Tape on F3 +X Solar Array | Thermal | Tape |  | Smith | [7 empty] | thm_pfr_236 Thermal Tape on F3 +X Solar Array.pdf | Closed 12/27/06 | bar: 1 to 6
PFR 237 Limit Monitor Warm Reset | BAU | FSW |  | Lewis |  | C | L | O | S | E | D | thm_pfr_237 LM Warm Reset.pdf | Closed 12/28/06
PFR 238 VOID
PFR 239 Open Latch Valve Indications
PFR 240 RTS60 Failed
thm_pfr_241 Open latch valve indic.pdf