## Milestones
THEMIS |  |  |  | MILESTONES
Start | End | Location | Description | Media
2006-06-29 | 2006-06-29 | JPL | Probe (1-3) Arrival
2006-07-05 | 2006-07-05 | JPL | Probe (4-5) Arrival
2006-07-10 | 2006-07-10 | JPL | Integration of Probes to Probe Carrier
2006-07-12 | 2006-07-18 | JPL | Vibration
2006-07-25 | 2006-07-28 | JPL | Probes Magnetic Tests Complete
2006-08-07 | 2006-08-15 | JPL | Spin Balance Complete
2006-12-11 | 2006-12-11 | ASO1 | PC & Probes Arrive and Unpack | KSC PAO
2006-12-12 | 2006-12-22 | ASO1 | Probe Final Tests
2007-01-03 | 2007-01-08 | ASO2 | Probe Fueling
2007-01-09 | 2007-01-14 | ASO2 | Probe Carrier Assembly
2007-01-15 | 2007-01-15 | ASO2 | PCA Spin Balance | Invited Media Reps
2007-01-24 | 2007-01-24 | ASO2 | PCA Mate to Third Stage
2007-02-01 | 2007-02-01 | ASO2 | Encapsulation
2007-02-02 | 2007-02-02 | ASO2 | Transport to PAD
2007-02-05 | 2007-02-05 | PAD | PCA Launch Rehearsal
2007-02-08 | 2007-02-08 | PAD | Fairing Installation | KSC PAO
2007-02-15 | 2007-02-15 | PAD | Launch
Blue indicates completed tasks
Date: 12/06/2006
Formulas:
End = [Start]
End = [Start]+10
Start = [Start, row below]-1
Public Affairs Details
Probe Unpack: Probes will be Unpacked in Clean Room. Cameras will be allowed. We expect to unload the trucks around 0800, clean probe shipping containers by 1000, move probes into clean room by 1030, and remove probe covers around 1100.
Spin Balance : Probes will be on Carrier in launch configuration, spinning just as in launch. Possible interviews with the payload in view.
Fairing Installation: Probe Carrier Assembly will be unbagged, all red tag and green tag items processed, and the fairing installed. This is a short opportunity for photos since the PCA is off purge
and subject to contamination.
Project References:
- Peter Harvey, THEMIS Project Manager, 510-229-7975 (cell)
- Rick Sterling, THEMIS Integration Manager, 510-277-2877 (cell)
- Daniele Meilhan, THEMIS Scheduler, 510-520-7205 (cell)

## Events
THEMIS |  |  |  |  | EVENTS
Start | End | LOC | Event | Description | Status
2006-06-23 | 2006-06-23 | UCB | MPER | Mission Pre Environmental Review
2006-06-27 | 2006-06-27 | Telecon | GOWG | Ground Operations Working Group
2006-06-28 | 2006-06-28 | Telecon | GOR | Ground Operations Review | Complete
2006-07-11 | 2006-07-12 | GSFC | Pre-FOR | Pre Flight Operations Review | Complete
2006-07-13 | 2006-07-13 | JPL | MIWG# 6 | Mission Integration Working Group | Complete
2006-10-04 | 2006-10-05 | UCB | FOR | Flight Operations Review | Firm
2006-10-26 | 2006-10-26 | UCB | PSR | Pre Ship Review | Firm
2006-11-15 | 2006-11-16 | UCB | SWT | Science Working Team | Firm
2006-11-29 | 2006-11-29 | ASO | MIWG# 7 | MIWG/GOWG TIM /Delta-GOR | Firm
2006-12-11 | 2006-12-11 | UC/NASA | PR | Press Release on Arrival at KSC | Firm
2007-01-03 | 2007-01-03 | HB | PREVOS | Pre-Vehicle on Stand | Firm
2007-01-04 | 2007-01-04 | GSFC | MRR | Mission Readiness Review at GPMC | Firm
2007-01-12 | 2007-01-12 | KSC | LVRR | Launch Vehicle Readiness Review | Firm
2007-01-17 | 2007-01-17 | Telecon | SMSR | Systems and Safety Mission Assurance R | Firm
2007-01-17 | 2007-01-17 | Telecon | PC | L-30 Press Conference | Firm
2007-01-23 | 2007-01-23 | HQ | MRB | Mission Readiness Review | Firm
2007-02-01 | 2007-02-01 | CCAFS | LSRR | Launch Site Readiness Review | Firm
2007-02-12 | 2007-02-12 | KSC | FRR | Flight Readiness Review (S/C Readiness) | Firm
2007-02-13 | 2007-02-14 | KSC | SWT | Science Working Team | L-2 days
2007-02-13 | 2007-02-13 | KSC | LMCM | Launch Management Coordination Meeting | L-2 days
2007-02-13 | 2007-02-13 | KSC | MDR | Mission Dress Rehearsal | L-2 days
2007-02-13 | 2007-02-13 | KSC | LRR | Launch Readiness Review | L-2 days
2007-02-14 | 2007-02-14 | KSC | PLPC | Pre-Launch Press Conference | L-1 days
2007-02-15 | 2007-02-16 | KSC | ILC | Initial Launch Countdown
Formulas:
End = [Start]
End = [Start]+1